## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [ Summary of teleconferences previous to the November meeting ]
Date Submitted: [ November 9th, 2015 ]
Source: [ Marco Hernandez ]
Company: [NICT]
Address: [3-4 Hikarino-oka, Yokosuka, 239-0847, Japan]
Voice:[+81 46-847-5439] Fax: [+81 46-847-5431] E-Mail:[]
Re: [In response to call for technical contributions TG8]
Abstract: [ ]
Purpose: [Material for discussion in 802.15.8 TG]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Teleconference on October 7th
Brief teleconference: only HB Li informed that the UWB proposers will present a common mode proposal for the UWB PHY.
Prof. Lee suggested to switch to Skype for the teleconferences.

## Slide 3: Teleconference on October 27th
We revised the status of assignments in Doc. 695r1.
  We expect contributions from Marco, Igor, Billy, BJ, HB Li and Dr. Juu for the November meeting.
  Review of assignments in Doc. 695r2.
The idea is to finish the 1st Draft after the November meeting. So we can review such Draft (comment/resolution) by the Group by the January meeting.