## IEEE_Cover
April 2016 | DCN: 15-16-0162-04-003e | P802-15_3e_Consolidated_Comments_04.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 Letter Ballot Comment Submission
Date Submitted | Friday, April 1, 2016
Source | Ko Togashi
Toshiba Corporation
Re:
Abstract | Cnsolidated Comments for Letter Ballot
Purpose | [This document is used to submit comments for an 802.15 Letter Ballot (TG 3e).]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Old Word Page | Sub-clause | Line # | Comment | Proposed Change | E/T | Must Be Satisfied? | Resolution Status | Resolution Detail | Frame Maker Page | Other2 | Other3 | Draft Update Status | Assigned
1 | Andrew Estrada | Sony | n/a | n/a |  | Need to make various remaining editorial changes | Identify the issues and make corrections | E | Yes | Accepted |  |  |  |  | n/a | Togashi
2 | Andrew Estrada | Sony | 22 | 4.5a.1 |  | Pre-coded GMSK appears suddenly with no description | Add description for GMSK or remove GMSK from the modulation | T | Yes | Revised | Delete GMSK and MSK. |  |  |  | done | Togashi
3 | Andrew Estrada | Sony | 50 | 6.5. | 15 | Table 6-22a does not contain Array Training Command. | Insert as shown in 15-16-0982r01. | T | Yes | Accepted | Modify table as described in 15-16-0187-01 (in progress). Assume comment is referring to missing Array Training Feedback command. |  |  |  | Done | Hiraga
4 | Andrew Estrada | Sony | 55 | 6.5.9. | 21 | I cannot find description of the array training feedback command that was proposed in 15-16-0982r01. | Insert as shown in 15-16-0982r01. | T | Yes | Accepted | Insert new section 6.5.9.6 as described in 15-16-0187-01 (in progress) |  |  |  | Done | Hiraga
5 | Andrew Estrada | Sony | 105 | 11a.2.8.3 | 1 | Figure 11a-11 does not contain Array Training Feedback command as commented above. | In the figure, insert the Array training feedback and ACK for that command after the last array training command. | T | Yes | Accepted | Replace figure 11a-11 with new figure as described in 15-16-0188-01 (in progress) |  |  |  | Done | Togashi (Hiraga)
6 | Andrew Estrada | Sony | 104 | 11a.2.8.3 | 9~41 | This description does not contain the Array training feedback command. | Insert descriptions into this subclause. | T | Yes | Accepted | Add new text as described in 15-16-0188-01 (in progress) |  |  |  | done | Hiraga
7 | Andrew Estrada | Sony | 107 | 11a.2.8.5.3 11a.2.8.5.4 | 1~21 | BPSK-modulated Ga128 signal leads to division by zero when frequency-domain equalization (as mentioned in line 8) is applied at the receiver. | Correct the MIMO CES sequence as needed. Change Figure 11a-13 if necessary. | T | Yes | Revised | See document 0325-01, Hiraga will prepare doc and figure |  |  |  | WIP | Hiraga
8 | Andrew Estrada | Sony | 106 | 11a.2.8.5. | 10 | Change Figure11a-13 if necessary along with the revision by comment above. | Change if necessary. | T | No | Rejected
9 | Andrew Estrada | Sony |  |  |  | Define method to send MCS info to the upper layer | Confirm why MLME channel status request has disappeared (6.3.18) | T | Yes | Accepted | See document DCN (292 Akiyama and 325 Hiraga), Resolution still pending. May want to know the MCS |  |  |  | done | Hiraga/Akiyama
10 | Andrew Estrada | Sony | 94 | 11a.1.5 |  | Transmit mask should be relaxed | Revise channel mask to align better with regulatory limits | T | Yes | Accepted | (under discussion) results ready after 4/27 |  |  |  | WIP | Maekawa
11 | Andrew Estrada | Sony | 93 | 11a.2.3.1 | 19 | Use of preamble, payload, and command frame are confusing | Delete "a PHY short preamble shall be used for the payload" | T | Yes | Revised | Change text as proposed in document 15-16-0235-01. |  |  |  | done | Kondou
12 | Andrew Estrada | Sony | 34 | 6.3.1 | 28 | IE length in beacon may be insufficient to transport higher-layer info | Expand IE in beacon to add more information | T | Yes | Revised | Change text as proposed in document 15-16-0273-00 |  |  |  | done | Togashi
13 | Andrew Estrada | Sony |  | 6 |  | Beacon and Unassociated Phase should use mandatory MCS | As commented | T | Yes | Accepted | Change text as proposed in document 15-16-0274-00, 15-16-0292-00 |  |  |  | done | Akiyama
14 | Andrew Estrada | Sony | 101 | 11a.2.5.2 | 6 | Section number has not been provided for "Receiver maximum input level". | Provide a section number such as 11a.2.5.3. | E | Yes | Accepted | See duplicate CID 130 | 89 |  |  | done - SA | Togashi
15 | Andrew Estrada | Sony | 24 | 5.3 | 1 | MLME.start has not been not defined for P2Plink in the current MAC-SAP. | Change the word "piconet" to PNPP and "PNC" to "PNCC", and clarify which parameters are used for HRCP DEVs in 5.3.3 and Table 5-8. See document 15-16-0276-00. | T | Yes | Revised | See document 15-16-0276-00 page 4 to 8. |  |  |  | done | Toshimitsu/Togashi
16 | Andrew Estrada | Sony | 94 | 11a.2.3.1.1 | 3 | The length of PHY-long preamble is shorter than that in 15.3c.This will make the system less robust. | Increase the number of code repetitions to 28 for the PHY-long preamble, which is the same value as that in 15.3c. | T | Yes | Accepted | On line 3, change 20 to 28. |  |  |  | done | Togashi
17 | Andrew Estrada | Sony | 98 | 11a.2.3.3 | 11 | PCES has not been not defined in HRCP-SC PHY | Change PCES to PPRE. | E | Yes | Accepted |  | 86 |  |  | done | Togashi
18 | Andrew Estrada | Sony | 108 | 11a.2.8.8 | 22 | PCES has not not been defined in HRCP-SC PHY MIMO | Change PCES to PPRE. | E | Yes | Accepted |  | 96 |  |  | done | Togashi
19 | Andrew Estrada | Sony |  |  |  | No description of antenna/RF control | Add description | T | Yes | Rejected
20 | Andrew Estrada | Sony |  |  |  | Link Layer Control (LLC) not defined. | Define LLC | T | Yes | Rejected
21 | Andrew Estrada | Sony | 35 | 6.3.1.1a, 6.5.1.1, 6.5.1.2 | 3 | What is the definition of the values of the ATP fields, for a) Beacon, b) Association Request and c) Association Response. | Add clear definition | T | Yes | Revised | See document 15-16-0297-00 |  |  |  | done | Jason/Togashi
22 | Andrew Estrada | Sony | 42 | 6.4.11a | 4 | How does the LLPS mode work when the LLPS Capable flag is set in a) PPC Capability IE or b) DEV Capability IE? | Add detail description to enable LLPC mode. | T | Yes | Revised | Change LLPS capability to LLPS allowed in the PPC capability field. In the DEV and Pair capability fields, make all LLPS fields reserved but make sure to reserve all the same bits that are used for LLPS in the PPC cability field. See document 15-16-0284-01 and 15-16-0338-01. |  |  |  | WIP | Togashi/Kondou
23 | Andrew Estrada | Sony | 52 | 6.5.1.2 | 20 | It is desirable to add description such as "HRCP Pair Capability shall be included in IEs field of Association Response command". | Add the description "HRCP Pair Capability shall be included in IEs field of Association Response command" or equivalent. | T | Yes | Rejected | Proposed text already appears on page 47, line 18-19.
24 | Andrew Estrada | Sony | 64 | 7.14a | 16 | Is it possible to issue a sleep request from either PPC or DEV? | Make clear the start condition and definition of the HRCP DEV. | T | Yes | Revised | Change DEV to HRCP DEV. Make clear that DEV means both DEV and PPC. Apply changes as shown in document 15-16-0284-01 |  |  |  | WIP | Togashi
25 | Andrew Estrada | Sony | 56 | 7.3a.1 | 2 | What is the expected value of "Last Received Sequence Number" field of Stk-ACK in reply to an Association Response command before receiving any data frame? | Add clear description | T | Yes | Revised | Add clarifying sentence to sub-clause 6.2.10. Togashi prepared text specifying a dual counter approach. See document 15-16-0275-00. |  |  |  | WIP | Toshimitsu/ Kondou
26 | Andrew Estrada | Sony | 56 | 7.3a.1 | 2 | Cannot distinguish between command and data ACK frames. | Devise method to distinguish the two frame types. | T | Yes | Accepted | TBD |  |  |  | WIP | Toshimitsu
27 | Andrew Estrada | Sony | 56 | 7.3a.1 | 2 | (1) For PPC, what is the behavior when ACK is not received after sending an Association Response? (2) For DEV, what is the behavior when ACK is not received after send an ACK to PPC in reply to an Association Response? | (1) PPC should change the state to Asynchronous phase and resend Association Response after a RIFS period. (2) DEV should change the state to Asynchronous phase and resend ACK after a RIFS period. | T | Yes | Accepted | As in comment for CID 27 |  |  |  | WIP | Toshimitsu
28 | Andrew Estrada | Sony | 60 | 7.8.3 | 2 | Association is not clear. | Add clear description | T | Yes | Rejected
29 | Andrew Estrada | Sony | 63 | 7.9.8.2 | 10 | Recovery Process (Asynchronous Phase), 7.4.1 Interframe Space (IFS) Figure 4-2a – One cycle of PPAP | Add reference. | T | Yes | Rejected
30 | Andrew Estrada | Sony | 61 | 7.8.3 | 9 | It appears redundant to send empty data frames to adjust the subframe number and subframe length. There should be a better way to do this. | Clarify meaning. | T | Yes | Revised | Delete paragraph. In Fig 7-54a and 7-54b, Change "More fragment flag is set to 1 to indicate the corresponding subframe is not a final frame of fragmentation." to "Last fragment flag is set to 1 to indicate the corresponding subframe is a final frame of fragmentation." Change "More fragment" to "Last fragment" in all other appropriate locations in the draft. Add new text to explain the size requirement for each subframe. Apply changes as shown in document 15-16-0284-01 |  |  |  | Done | Ko (Maekawa)
31 | Andrew Estrada | Sony | 62 | 7.9.8.1 | 6 | The procedure for aggregation length control is not clear. | Consider adding explanation of aggregation length control | T | Yes | Rejected | Aggregation length control is up to the implementation. The receiver provides information in the buffer full and buffer empty flags. It is up to the transmitter to adjust its length accordingly. |  |  |  | 0276 not finished
32 | Andrew Estrada | Sony | 24 | 5.3 |  | There are places where actual parameters are either specified or not specified. There are also SAPs such as those for data transmission/reception which are not specified. If specifications are not necessary and parameters can be added with no restrictions during implementation, then there are no issues, but the SAPs should be re-examined. | Please specify all parameters and SAPs or explain why the definition is not needed. See document 15-16-0276-00. | T | Yes | Revised | Add required parameters and SAP definition for data. Add required parameters and SAP definition for MLME. Change as recommended in 15-16-0276-00 |  |  |  | WIP | Akiyama will add param and SAP def for data. Toshimitsu will add param and SAP def for MLME.
33 | Andrew Estrada | Sony |  | 6.2.1.2 |  | Isn't a mechanism to select the logical channel for the higher layer needed (embedded in the frame format) to deliver data properly to the higher layer? | Consider whether such a mechanism is required. | T | Yes | Accepted | Add new text describing logical channel mechanism. See document 15-16-292-00 slides 8 and 9. |  |  |  | done | Akiyama
34 | Andrew Estrada | Sony | 49 | 6.4.38 | 22 | What is the "Unique ID"? This sentence refers to 6.4.7 but the subclause 6.4.7 which exists in the baseline (roll-up) version doesn't mention unique ID. | Define "Unique ID" in 6.4.7 | T | Yes | Rejected | "Unique ID" already defined in the base standard. Check with James Gilb. See document 15-16-292-00)
35 | Andrew Estrada | Sony | 46 | 6.4.11a |  | "0.1mss" in Table 6-17d should be "0.1 ms". | Correct to 0.1 ms. | E | Yes | Accepted |  | 33 |  |  | done - SA | Togashi
36 | Andrew Estrada | Sony | 46 | 6.4.11a |  | Table titles shall not be positioned within the table itself. | Correct table titles | E | Yes | Accepted |  |  |  |  | done - SA | Togashi
37 | Andrew Estrada | Sony |  | 7 |  | Beacon and Command frame shall be transmitted as mandatory MCS. | Clarify the mandatory behavior | T | Yes | Rejected
38 | Andrew Estrada | Sony | 64 | 7.9.8.2 |  | Clarify definition of PHY error in Figure7-57b TIME#4. | Clarify as needed | T | Yes | Revised | Change "PHY Error" to "Receiver Error" in Fig 7-57b |  |  |  | done | Togashi
39 | Andrew Estrada | Sony | 65 | 7.9.8.2 |  | Sleep flag in Figure 7-22a shall be changed to HRCP Sleep field. | Change to HRCP Sleep field | T | Yes |  | Change all instances of "Sleep Flag = 1" in Fig 7-72a to "HRCP Sleep field = 1" |  |  |  | done | Togashi
40 | Andrew Estrada | Sony | 65 | 7.14a | 3,5 | "Sleep Request" shall be changed to "sleep request". | Correct the capitalization | T | Yes | Accepted |  |  |  |  | done | Togashi
41 | Andrew Estrada | Sony | 65 | 7.14a |  | Correct mistake in Figure 7-22a. In top left, the FCS should be shown to align with Sub-F# N. | Correct the Figure | E | Yes | Accepted | This change applies to Figure 7-72a | 53 |  |  | done | Togashi
42 | Andrew Estrada | Sony | 96 | 11a.2.3.2.1 | 12 | Should the Frame Length field indicate the MAC frame length not excluding FCS? | Correct as needed | T | Yes | Revised | Change "subheader(s) in the aggregated frames" to "subheader(s) and padding octets in the aggregated frames". Make this correction on page 121, line 17, and page 126 line 6. Also page 102, line 16 should be corrected. -> (in progress) |  |  |  | done | Kondou
43 | Andrew Estrada | Sony |  | 7.9.8.2 |  | During recovery, is the MCS of the ACK frame defined? | Confirm and correct as needed. | T | Yes | Rejected | This should be up to the implemention
44 | Andrew Estrada | Sony | 99 | 11a.2.4.1 |  | Considering P2P communication with equal-basis transceivers, allowable EVM for a transmitter seems to be too strict. Referring to page 33 in IEEE802.15-15-0662-01-003e, target EVM balance between transmitter and receiver should be revisited. | Target EVM for a transmitter and a receiver has to be confirmed for deciding allowable EVM for a transmitter. | T | Yes | Accepted | Target EVM is confirmed as described in document 15-16-0236-01. Therefore, no change is required. |  |  |  | done | Kondou
45 | Andrew Estrada | Sony | 99 | 11a.2.4.1 |  | There are many possible situations where EVM will be measured via a build-in antenna at 60 GHz band. Proposals for measurement methods should be considered, either in this spec or in a separate conformance test plan. | Insert text as follows: when measuring EVM by capturing a transmit signal via an antenna, frequency response of the antenna can be compensated. | T | Yes | Revised | Add a new sentence after the sentence on line 24 as follows: "Note that this requirement assumes a conducted measurement." See document 15-16-0236-01, page 4. |  |  |  | done | Togashi
46 | Andrew Estrada | Sony | 100 | 11a.2.4.2 |  | Can we relax this spec e.g. up to 30*10^(-6)? | Discuss and change. | T | Yes | Accepted | Change the spec as requested in the comment to +/- 30 ppm. |  |  |  | done | Kondou
47 | Andrew Estrada | Sony | 100 | 11a.2.4.4 |  | Power-on ramp and power-down ramp of 9.3 nsec are difficult to achieve in practice. A minimum of 100 nsec should be considered for ramp up/down for standard RF transceivers. | Confirm whether the spec values are practical or not. | T | Yes | ?? | Practical therefore no changes required. |  |  |  | done | Kondou
48 | Andrew Estrada | Sony | 101 | 11a.2.5.2 |  | Receiver maximum input level should be relaxed. | Specs should be revised considering usage scenario and process potential for advanced CMOS circuit. | T | Yes | Revised | Change max input level to -30 dBm for mandatory MCS? |  |  |  | done | Kondou
49 | Andrew Estrada | Sony | 101 | 11a.2.6 |  | In Table 11a-19, the minimum pPHYSIFSTime of 0 usec is not feasible in practice. | A lower non-zero limit should be inserted. | T | Yes | Revised | Change minimum value from 0 us to 0.5 us. | 7 |  |  | done | Togashi
50 | Keiji Akiyama | Sony | 17 | 4 | 1 | Line numbers must be indicated in the draft | As commented | E | No | Accepted |  | 7 |  |  | done | Togashi
51 | Keiji Akiyama | Sony | 22 | 4.5a.1 | 12 | "pre-coded MSK and pre-coded GMSK" should be removed | As commented | E | No | Accepted | Same as CID #2 |  |  |  | done | Togashi
52 | Keiji Akiyama | Sony | 29 | 6.2 | 24 | "Figure 6-3 3", the last "3" should be removed. | As commented | E | Yes | Accepted | Error appears in line 25 | 23 |  |  | done-SA | Togashi
53 | Keiji Akiyama | Sony | 37 | 6.3.3a.1 | 13 | Should be insert the sentence like a "Non-secure Command frame shall be formatted as shown in Figure 6-56a". | As commented | T | No | Accepted |  |  |  |  | done | Togashi
54 | Keiji Akiyama | Sony | 37 | 6.3.3a.1 | 18 | "Figure 6-56a" should be corrected as "Figure 6-56b" | As commented | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
55 | Keiji Akiyama | Sony | 38 | 6.3.3a.2 | 9 | "Figure 6-56c" should be corrected as "Figure 6-56b" | As commented | E | Yes | Accepted |  | 28 |  |  | done-SA | Togashi
56 | Keiji Akiyama | Sony | 41 | 6.4 | 2 | "an IE" should be "IEs" | As commented | E | Yes | Accepted | TBD |  |  |  | done | Togashi
57 | Keiji Akiyama | Sony | 42 | 6.4 | 1 | Duplicate Table6-13a | For Page 42, the caption should be "Table 6.13-b Requirements for supporting IEs" | E | Yes | Accepted |  |  |  |  | done | Togashi
58 | Keiji Akiyama | Sony | 44 | 6.4.11a | 2 | The font of the caption of Figure 6-88e should be corrected | change to Arial font (not Times New Roman) | E | No | Accepted |  |  |  |  | done-SA | Togashi
59 | Keiji Akiyama | Sony | 56 | 7.3a.1 | 13 | To short letter spacing or font is incorrect ?? | fixed like as same as other part ?? | E | No | Accepted | Framemaker issue, in progress |  |  |  | done | Togashi
60 | Keiji Akiyama | Sony | 58 | 7.4.1 | 29, 30 | TBD exists like as 11.2.x.x and 11a.3.x.y | 11a.2.6.1 and 11a.3.6.1 respectively | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
61 | Keiji Akiyama | Sony | 62 | 7.9.8.1 | 17 | DEV.B is undefined | DEV.B should be "DEV" | E | Yes | Accepted |  |  |  |  | done | Togashi
62 | Keiji Akiyama | Sony | 83 | 11a.1 | 4 | Outline level in 11a.1(a) and (b) is not appropriate | a)d) must be lower then section 11a.2.3.2 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
63 | Keiji Akiyama | Sony | 87 | 11a.2 | 1 | Duplicate 11.a.2 | remove redunduncy | E | Yes | Accepted |  |  |  |  | done | Togashi
64 | Keiji Akiyama | Sony | 95 | 11a.2.3.2 | 4 | Outline level in 11a.2.3.2(a)-(d) is not appropriate | a)-d) must be lower then section 11a.2.3.2 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
65 | Keiji Akiyama | Sony | 98 | 11a.2.3.3 | 6 | Outline level in 11a.2.3.3(a)-(f) is not appropriate | a)-f) must be lower then section 11a.2.3.3 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
66 | Keiji Akiyama | Sony | 108 | 11a.2.8.8 | 6 | Outline level in 11a.2.8.8(a)-(g) is not appropriate | a)-g) must be lower then section 11a.2.8.8 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
67 | Keiji Akiyama | Sony | 116 | 11a.3.2.7 | 6 | Outline level in 11a.3.2.7(a),(b) is not appropriate | a) and b) must be lower then section 11a.3.2.7 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
68 | Keiji Akiyama | Sony | 120 | 11a.3.3.2 | 15 | Outline level in 11a.3.3.2 is not appropriate | a),b) and c) must be lower then section 11a.3.3.2 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
69 | Keiji Akiyama | Sony | 122 | 11a.3.3.3 | 16 | Outline level in 11a.3.3.3 is not appropriate | a),b) and c) must be lower then section 11a.3.3.3 | E | Yes | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
70 | Keiji Akiyama | Sony | 34 | 6.3 | 27 | 6.2 should be 6.3 | As commented | E | Yes | Accepted |  |  |  |  | done | Togashi
71 | Keiji Akiyama | Sony | 99 | 11a.2.4.1 | 24 | Table 11-38 should be corrected as Table 11a-17 | As commented | E | Yes | Accepted |  |  |  |  | done | Togashi
72 | Keiji Akiyama | Sony | 105 | 11a.2.8.3 | 1 | Figure 11a-11 is hard to read | Large font, simple description | E | No | Revised | Replace figure 11a-11 with new figure as described in 15-16-0188-01. In progress. |  |  |  | done | Togashi/Hiraga
73 | Keiji Akiyama | Sony | 93 | 11a.2.3.1 | 19 | Delete "A PHY short preamble shall be used for the payload" | As commented | T | Yes | Revised | See resolution of CID 11. |  |  |  | done | Togashi
74 | Brian Weis | Cisco Systems | 76 | 9a.2.4 | 21 | CGM IV nonce ("IV") rquirements differ widely from the CCM Nonce format. Although the GCM IV format specified here is likely to guarentee uniqueness, it does not conform to the GCM specification (NIST SP800-38D). SP800-38D has very specific rules in how the nonce can be constructed. Due to this variance, an implementation that does not follow those rules is highly unlikely to be usable by any organization requiring implementations to have a NIST FIPS 140 certificate. Please note that NISP FIPS 140 guidance is often carried into other security requirements, such as Common Critiera profiles, so this is an international consideration (This is an issue the 802.1 group has recently dealt with regarding MACsec frame security.) | To meet the deterministic IV construction requirements in Clause 8.2.1 of SP800-38D, the IV should be formed of just two fields: a fixed field and an invocation field. The SrcID could meet the requirement of the fixed field and the invocation field could be the secure frame counter (but together they would need to compose 12 octets). Additionally, the SrcID should be chosen by the station itself and be guarenteed to be globally unique. The Time Token should be placed within the authenticated portion of the frame (in either the AAD or the encrypted data, whichever is appropriate). | T | Yes | Revised | Modify draft as recommended in document 15-16-0264-0 2 (Jason) |  |  |  | done | Jason/Togashi
75 | Brian Weis | Cisco Systems | 77 | 9a.3.1 | 9 | Encrypting a key with GCM requires a unique nonce, and network security systems typically send the nonce with the key. The Encrypted Key value here only consists of the 16 octets of key. | There should be a note describing how the nonce is guarenteed to be unique OR that the key encrypting the key is never used more than once (which makes nonce reuse moot). (I cannot find this note anywhere else in 802.15.3 or this document). | T | Yes | Revised | Modify draft as recommended in document 15-16-0264-02 |  |  |  | done | Jason/Togashi
76 | Brian Weis | Cisco Systems | 79 | 9a.4.1 | 3 | Is the heading for the table intended to be inputs for "GCM" rather than "CCM"? | Change CCM to GCM, if applicable | E | No | Accepted | Modify draft as recommended in document 15-16-0264-02 |  |  |  | done | Jason/Togashi
77 | Brian Weis | Cisco Systems | 79 | 9a.4.2 | 26 | This comment is from this line until the end of thes section. The text seems to re-state the text in SP800-38D describing how GCM works. It would be much easier to analyze for correctness if it simply pointed to the definitive algorithm specification (either SP800-38D or an equivilent ISO document) rather than re-writing the algorithm. | Replace the description of how the encyption and decyrption algorithms work with a reference to an authoritative crypto algorithm reference. | T | Yes | Revised | Modify draft as recommended in document 15-16-0264-02 |  |  |  | done | Togashi
78 | Tero Kivinen | INSIDE Secure |  |  |  | PDF Index is broken. There are entries like a) after section 4, and b) which has subsection 4.3.5 etc. | Fix the index | E | No | Accepted | Framemaker issue |  |  |  | done-SA | Togashi
79 | Tero Kivinen | INSIDE Secure | 36 | 6.3.1.2a | 22 | The SEC field is very badly named, as there is already SEC field in the Frame Control Field. In other places this field is called SFC or Secure Frame Counter | Change “SEC” with “SFC” | E | No | Accepted |  |  |  |  | done | Togashi
80 | Tero Kivinen | INSIDE Secure | 40 | 6.3.4a.2 | 13 | In the aggregated frame we use the default MAC subheader, which contains 9-bit sequence number, and I think that sequence number is used as 8-bit secure subframe counter when generating the nonce. This is not really specified anywhere, the secure subframe counter is specified to be incremented for every subframe, but nothing is said whether it needs to match the sequence number of the frame. Sequence number in the subframe is NOT specified to be strictly increasing or anything like, it is just sequence number of the subframe. Also the sequence number is 9-bit field, but the secure subframe counter is only 8-bit field, so there can be only 256 subframes in secure subframe, even when the sequence number field would allow 512 subframes. | Add text limiting the number of subframes in the secure aggregated data frames to 256 subframes. Specify whether the sequence number and secure subframe number needs to match or not. | T | Yes | Revised | Modify draft as recommended in document 15-16-0264-02 |  |  |  | done | Jason/Togashi
81 | Tero Kivinen | INSIDE Secure | 43 | 6.4.11a | 4 | Figure 6-88b does not really follow the editing conventions. It should really say bits: b0-b10 is for SC supported Channel Aggretaion Pattern etc. That would make the figure much shorter and understandable. Also now you specify the bit numbers twice. First in the fgireu 6-88b, and then second time in the 6-88c, 8-88d etc. | Change to use normal figure format, and for subformats do not list the original bit pattern, but start numbering from the beginning of the subfield. | E | No | Revised | Change the figure format to be more like Figure 6-6 on page 70 of the revision spec 802.15.3RevA-D02.pdf. On line 11, correct the name of the field to "SC Supported Channel Aggregation Pattern". Make the same correction to the header of Figure 6-88c. Clarify the Figure 6-88c using ones instead of X's. In progress. |  |  |  |  | Togashi/Estrada
82 | Tero Kivinen | INSIDE Secure | 43 | 6.4.11a | 13 | Are only those bit-patterns specified in the 6-88c allowed. What happens if you receive bit pattern not listed in the 6-88c. Are you allowed to send such? | Specifying 4 different values would be much more efficient to use 2-bit field for it, and provide the mapping from the values 1-4 to specific bits. Now there is nothing telling what does b0 mean in the table. | T | Yes | Revised | The figure is correct but the meaning is not well described. Revise the text to clarify. See document 0333-01 and 15-16-0338-01 |  |  |  |  | Togashi/Kondou
83 | Tero Kivinen | INSIDE Secure | 44 | 6.4.11a | 25 | The way table 6-17a, 6-17b etc are expressed would indicate that bit b22 is the MSB of the value from the table, i.e. it is 0 for 1ms-50ms and 1 for 100ms and reserved values. This means that the bit patterns needs to be formatted as bit patterns, it must not be expressed as numbers, as then the order would be LSB first, i.e. bit 22 would be the LSB of the number. Is this intended? | It would be better to really then separate the bits i.e. make one column for bit b22, another for b23 etc so it would be really clear that we are not talking about integers here. | E | No | Accepted | Change the table to one column per bit. See document 15-16-0333-00-003e |  |  |  | done | Akiyama/Estrada
84 | Tero Kivinen | INSIDE Secure | 49 | 6.4.28 | 22 | Why is this text in red? | Change to be normal black text. | E | No | Accepted |  |  |  |  | done-SA | Togashi
85 | Rick Roberts | Intel | 17 | 4.1 |  | I think changing the definition of a piconet to PNPP is unnecessary and actually is out-of-scope for an amendment. The point-to-point configuation has always been part of the piconet definition. An amendment is only allowed to add text to support new functionality; not to go changing definitions that have already been letter balloted and approved. | Keep piconet definition and don't use PNPP nor explicitly call out P2Plink. The P2P function is already part of the piconet concept. Restore all impacted text in the complete document. | T | yes | Revised | Update draft as recommended in document 15-16-0306-00-003e Change P2Plink to Pairnet (throughout document) |  |  |  | done | Togashi
86 | Rick Roberts | Intel | 17 | 4.1.2 |  | Do not use the term P2Plink because P2P is not something new for 802.15.3, it has been in the standard for years. | I'd suggest instead of P2Plink you call it something like "HRCPlink", but don't imply that you are adding P2P capability to the 15.3 standard. | T | yes | Revised | Update draft as recommended in document 15-16-0306-00-003e Change P2Plink to Pairnet (throughout document) |  |  |  | done | Togashi
87 | Rick Roberts | Intel | 16 | 3.2 |  | Remove or modify inappropriate acronyms and abbreviations. | Remove PNPC and PNPP from the list and use the original notation of piconet and PNC. Replace P2Plink, PPAP, PPC and PPID with something like HRCPlink, HRCPAP, HRCPC and HRCPID. | E | yes | Revised | Update draft as recommended in document 15-16-0306-00-003e |  |  |  | done | Togashi
88 | Rick Roberts | Intel | 42 | 6.4 |  | In regards to the information elements, and in particular Table 6-13a, why is 15.3e adding text with regards to non HRCP PHYs? I don't see a comparable table in the current 15.3 document. | Remove the middle column from Table 6-13a. I believe it is within the scope of 802.15.3e to add a table that addresses the HRCP (keep just the first and third columns). | T | yes | Accepted | Note: there are 2 tables named 6-13a. This comment applies to the 2nd table 6-13a that appears on page 42. Delete the 2nd column in this table. Change the name of the 2nd table to table 6-13b. |  |  |  | done | Togashi
89 | Rick Roberts | Intel | 51 | 6.5 |  | In regards to the MAC commands, and in particular Table 6-22b, why is 15.3e adding text with regards to non HRCP PHYs? I don't see a comparable table in the current 15.3 document. | Remove the middle column from Table 6-22b. I believe it is within the scope of 802.15.3e to add a table that addresses the HRCP (keep just the first and third columns). | T | yes | Accepted | Delete the 2nd column in this table. |  |  |  | done | Togashi (SA)
90 | Rick Roberts | Intel | 84 | 11a.1.5 |  | In Figure 11a-1 please provide units for the labelled pairs in the spectrum mask. | I believe the pairs shown in the spectrum mask are GHz and dBr. Add a note something like (GHz, dBr). | E | no | Accepted | Add a note or add units to the pairs in the figure. Replace figure. |  |  |  | done | Kondou
91 | Jae Seung Lee | ETRI | 20 | 4.3.4 | 6 | Change "with the PNC, in a piconet, or with PPC" to "with the PNC in a piconet, or with the PPC in a P2Plink". | Change "with the PNC, in a piconet, or with PPC" to "with the PNC in a piconet, or with the PPC in a P2Plink". | E | No | Accepted |  |  |  |  | done | Togashi
92 | Jae Seung Lee | ETRI | 20 | 4.3.4 | 9 | "i.e.,-when" : Remove "-". | Remove "-". | E | No | Accepted |  |  |  |  | done | Togashi
93 | Jae Seung Lee | ETRI | 29 | 6.2 | 26 | Remove ".". | Remove ".". | E | No | Accepted |  |  |  |  | done | Togashi
94 | Jae Seung Lee | ETRI | 35 | 6.3.1.1a | 32 | Text located from line 32 of page 35 to line 2 of page 36 is part of the NOTE. The text style should be changed. | Change the style of the text located from line 32 of page 35 to line 2 of page 36 accordingly. | E | No | Accepted |  |  |  |  | done | Togashi
95 | Jae Seung Lee | ETRI | 47 | 6.4.11c | 17 | HRCP Pair Capability IE indicates the parameter to be used in the current session that was decided by the PPC, so it is better to use the name "HRCP Operation Parameter IE". | Consider to change the name of the IE to "HRCP Operation Parameter IE" | T | No | Revised | Change the name as requested. See document 15-16-0338-01 |  |  |  | done | Togashi
96 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 6 | Each field references the field definition of the HRCP PPC Capability IE, but the meaning is not clear in the current text, since each field in the HRCP PPC Capability IE indicates the supported capabilities of the PPC, but the fields in the HRCP Pair Capability IE should indicate the selected (or negotiated) parameter by the PPC. | In each field definition, clearly state that the field indicates the parameter that should be used in the current session. | T | No | Revised | See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
97 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 9 | "OOK spreading" is not a parameter that has to be explicitly negotiated or chosen by the PPC. It indicates whether the DEV supports spreading or not. It is necessary to indicate it in the HRCP PPC Capability and HRCP DEV Capability, but no need to indicate it in the HRCP Pair Capability IE. | Remove "OOK Spreading" from the Pair Capability field | T | No | Accepted | Note: if both DEV and PPC support both spreading and not spreading, the choice is up to the transmitter and the choice is reflected in the preamble. See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
98 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 10 | "Pilot Symbol capable" is not a parameter that has to be explicitly negotiated or chosen by the PPC. It indicates whether the DEV can decode the frame with pilot symbols. It is necessary to indicate it in the HRCP PPC Capability and HRCP DEV Capability, but no need to indicate it in the HRCP Pair Capability IE. | Remove "Pilot Symbol Capable" from the Pair Capability field | T | No | Accepted | Note: there is a field indicating the use of pilot symbols in the PHY header. See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
99 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 11 | The current description on the field is not clear. Change the field name to "OOK Channel Bonding" and state that this field indicates the number of channel bonding that is used in the current session. | Change the field name to "OOK Channel Bonding". Change "The Supported OOK Channel Bonding field is defined in xxx" to "The OOK Channel Bonding field indicates the number of bonded channels that shall be used in the current session. 00 indicates no channel bonding, 01 indicates 2 channel bonding, 10 indicates 3 channel bonding, and 11 indicates 4 channel bonding is used in the session". Change the number of bits from 3 to 2 bits. | T | No | Revised | This comment applies to the "Supported OOK Channel Bonding field" only in the Pair capability field(s) in Fig 6-88 and the corresponding descriptive text following the figure. See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
100 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 16 | Since only one PHY mode is used during one session, it is not necessary to have both "SC Capable" and "OOK capable" in the Pair Capability field | Merge "SC capable" and "OOK capable" to 1 bit field and name it "PHY mode" field. Change the field definition as follows: "The PHY mode field indicates which PHY mode is used in the session. 0 indicates SC PHY is used, and 1 indicates OOK PHY is used." | T | No | Accepted | See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
101 | Jae Seung Lee | ETRI | 48 | 6.4.11c | 18 | "Supported Unit of Subframe Padding" is indicated by the HRCP PPC Capability and HRCP DEV Capability, and no need to indicate it in the HRCP Pair Capability. The unit of subframe padding that should be used is determined by the rules specified in clause 7.8.3 and it is not necessary to make the PPC to explicitly indicate it in the HRCP Pair Capability. | (Figure 6-88b) Remove "Supported Unit of Subframe Padding" field from the HRCP Pair Capability. Remove "HRCP pair Capability" from line 17 of page 60. | T | No | Accepted | See document 15-16-0338-01 |  |  |  | WIP | Togashi/Kondou
102 | Jae Seung Lee | ETRI | 52 | 6.5.1.2 | 24 | Typo. Change "nonHRCP" to "non-HRCP" | Change "nonHRCP" to "non-HRCP" | E | No | Accepted |  |  |  |  | done | Togashi
103 | Jae Seung Lee | ETRI | 52 | 6.5.1.2 | 33 | change "hundreds of milliseconds" to "500 ms" | change "hundreds of milliseconds" to "500 ms" | T | No | Accepted |  |  |  |  | done | Togashi
104 | Jae Seung Lee | ETRI | 75 | 9a | 6 | SFC has been increased to 4 octets, but it may not be sufficient for 100 Gbps peak throughput. | Consider to increase the SFC to 6 octets | T | No | Revised | Modify draft as recommended in document 0264-02 |  |  |  | done | Togashi
105 | Jae Seung Lee | ETRI | 108 | 11a.2.8.8 | 3 | Style mismatch | Correct the style mismatch | E | No | Revised | Change red font on this page back to black font. |  |  |  | done-SA | Togashi
106 | Jae Seung Lee | ETRI | 127 | Annex C | 1 | Annex C (Security consideration) has to be cleaned up for HRCP. | Update the Annex C Security) of the baseline (rollup) | T | No | Revised | See document 15-16-0291-01 |  |  |  | done | Togashi
107 | Jae Seung Lee | ETRI | 127 | Annex E | 1 | Annex E (PICS) has to be updated for HRCP | Update the Annex E (PICS proforma) of the baseline (rollup) | T | No | Accepted | tabled (since 3m rollup does not yet contain Annex for 3c)
108 | Thomas Kürner | TU Braunschweig | 16 | 3.1 | 4 | space between ")" and "." | remove space | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
109 | Thomas Kürner | TU Braunschweig | 16 | 3.2 | 15 | typos in point to point Link | point-to-point link | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
110 | Thomas Kürner | TU Braunschweig | 17 | 4.1.2 | 20/21 | TG3d adresses other point-to-point links as HRCP. With current description this may cause further changes in the future. | Rearrange the tow last last sentences as follows: "An HCRCP Dev always connects as P2P link. A typical communciation distance for an HRCP DEV is 10 cm or less. | T | Yes | Revised | Make clear that 10 cm applies to HRCP, not to the P2PLink (now called pairnet). This will allow future amendments (like 3d) to reuse the concept of a pairnet. |  |  |  | done | Togashi
111 | Thomas Kürner | TU Braunschweig | 18 | 4.2.2 | 8-11 | TG3d adresses other point-to-point links as HRCP. With current description this may cause further changes in the future. | Rearrange t paragraph: "An 802.15.3 P2Plink consists of two DEVs at most as components. (…) Once a connection is etsablished for an HRCP DEV, the beacon…" | T | Yes | Revised | Make clear that turning off the beacon applies to HRCP, not necessarily to P2PLink (now called pairnet). |  |  |  | done | Togashi
112 | Thomas Kürner | TU Braunschweig | 20 | 4.3.5 | 23 | "link" is missing after P2P | "P2Plink | E | Yes | Accepted | Will change with new pairnet terminology |  |  |  | done | Togashi
113 | Thomas Kürner | TU Braunschweig | 22 | 4.5a.2 | 30 | "connects" is wrong | "connect" | E | Yes | Accepted |  |  |  |  | done | Togashi
114 | Thomas Kürner | TU Braunschweig | 37 | 6.3.1.2a | 8 | "shown and shown" sounds strange | delete the last two words in the line | E | Yes | Revised | Change "shown and shown" to "follows" |  |  |  | done | Togashi
115 | Thomas Kürner | TU Braunschweig | 52 | 6.5.1.1 | 8 | Figure 6-127 should be Figure 1-126 | replace numbering | E | Yes | Revised | Check this figure against the latest version of the .3 revision |  |  |  | WIP | Toshimitsu/Kondou
116 | Thomas Kürner | TU Braunschweig | 52 | 6.5.1.1 | 8 | in figure the "device utility" field form 802.15.3 is missing | add device utiity field or add two different figures (one of HRCP DEV and one for none-HRCP DEV) | T | Yes | Revised | Accept the comment. Add Figure 6-126a for pairnet without DEV utility field. Change the 5th paragraph including description for Association request fcommand format for pairnet. Also check lines 11-14 against the latest version (D02) of the .3 revision -> See document 0333-01 |  |  |  | WIP | Akiyama/kondou
117 | Thomas Kürner | TU Braunschweig | 53 | 6.5.1.2 | 7 | undeline is missing for the term in brackets | add underlining for the term in brackets | E | Yes | Accepted |  |  |  |  | done | Togashi
118 | Thomas Kürner | TU Braunschweig | 55 | 6.5.9.5 | 6 | unclear, what an antenna cell is | cleaify the meaning of an antenna cell | T | Yes | Revised | Change "antenna cells" to "antenna elements" |  |  |  | done | Togashi
119 | Dave Evans | Philips Lighting | 16 | 3.1 |  | There is no line numbering! |  | E | No | Accepted | (See duplicate CID 50) |  |  |  | done-SA | Togashi
120 | Dave Evans | Philips Lighting | 16 | 3.1 |  | Space/period incorrect "close proximity (HRCP) .Carrier" | Interchange the space and period | E | Yes | Accepted |  |  |  |  | done | Togashi
121 | Dave Evans | Philips Lighting | 20 | 4.3.4 |  | Unnecessary space "Mode 0 —Open..." | Remove space | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
122 | Dave Evans | Philips Lighting | 42 | 6.4 | 1 | Table 6.13a, column 2 row 28, unwanted "y" in "mmyWave" | Remove y | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
123 | Dave Evans | Philips Lighting | 44 | 6.4.11a | 18 | Figure 6.88b shows that b19, b20 and b21 indicate the OOK supported channels bounding whereas Figure 6-88f shows that b18, b19 and b20 indicate the bonding | Change Figure 6-88f to be consistent with Figure 6.88b | E | Yes | Revised | Correct Fig 6-88f, Change b18 to b19. Change b19 to b20. Change b20 to b21. |  |  |  | done | Togashi
124 | Dave Evans | Philips Lighting | 44 | 6.4.11a | 25 | Likewise, b22, b23 & b24 in Table 6.17a are not consistent with Figure 6.88b | Change Table 6.17a to be consistent with Figure 6.88b | E | Yes | Revised | In Fig (Table?) 6-17a, change b22-24 to b23-25 |  |  |  | done | Togashi
125 | Dave Evans | Philips Lighting | 45 | 6.4.11a | 1 | The caption is missing from Table 6.17b | Insert caption | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
126 | Dave Evans | Philips Lighting | 45 | 6.4.11a |  | b25 & b26 in Table 6.17b are not consistent with Figure 6.88a | Change Table 6.17b to be consistent with Figure 6.88b | E | Yes | Revised | In Fig 6-17b, change b24-25 to b26-27 |  |  |  | done | Togashi
127 | Dave Evans | Philips Lighting | 45 | 6.4.11a | 4 | The caption is missing from Table 6.17c | Insert caption | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
128 | Dave Evans | Philips Lighting | 45 | 6.4.11a | 4 | b27, b28 & b29 in Table 6.17c are not consistent with Figure 6.88a | Change Table 6.17c to be consistent with Figure 6.88b | E | Yes | Revised | In Fig 6-17c, change b27-29 to b28-30 |  |  |  | done | Togashi
129 | Dave Evans | Philips Lighting | 46 | 6.4.11a | 1 | The caption is missing from Table 6.17d | Insert caption | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
130 | Dave Evans | Philips Lighting | 101 | 11a.2.5.2 | 6 | Is this a clause heading "Receiver maximum input level"? If yes then this needs a clause number and appropriate formating | Format accordingly | E | Yes | Accepted | See duplicate CID 14 |  |  |  | done-SA | Togashi
131 | Dave Evans | Philips Lighting | 103 | 11a.2.8.3 | 5 | First word in the sentence "At first Beacon is sent..." probably needs to be "A" | Change At to A | E | Yes | Revised | Change "At first" to "As a first step," |  |  |  | done | Togashi
132 | Dave Evans | Philips Lighting | 107 | 11a.2.8.6 | 24 | Missing definite article "At Tx side," | Change to "At the RX side," | E | Yes | Revised | Change "At Tx side" to "At the Tx side" |  |  |  | done | Togashi
133 | Dave Evans | Philips Lighting | 107 | 11a.2.8.6 | 24 | The sentence "Same in channel aggregation." does not read well | Change to "The same applies to channel aggregation" | E | Yes | Revised | The recommended text is an improvement but more detail needed for using channel aggregation. (Hiraga-san to propose resolution). See doc 15-16-0332-01 |  |  |  | done | Togashi
134 | Dave Evans | Philips Lighting | 107 | 11a.2.8.6 | 25 | Missing definite article "At Rx side," | Change to "At the Rx side," | E | Yes | Accepted |  |  |  |  | done | Togashi
135 | Dave Evans | Philips Lighting | 107 | 11a.2.8.6 | 26 | The sentence "PHY header for the…" does no read well | Change to "A PHY header for the…" | E | Yes | Accepted |  |  |  |  | done | Togashi
136 | Dave Evans | Philips Lighting | 110 | 11a.3.2.1 | 21 | Missing period at the end of the sentence "...specified in 11a.3.2.5.1" | Insert a period | E | Yes | Accepted |  |  |  |  | done-SA | Togashi
137 | Jussi Haapola | Centre for Wireless Communications / University of Oulu | 36 | 6.3.1.1a | 5 | The 'b3' bit field missing in Figure 6-50c | Include 'b3' bit field | T | Yes | Revised | Change header text from "Bits: b0-b2" to "Bits: b0-b3" |  |  |  | done | Togashi
138 | Jussi Haapola | Centre for Wireless Communications / University of Oulu | 46 | 6.4.11a | 1 | Table 6-17d field value combination '00' unit should be 'ms' not 'mss' | Correct it. | E | Yes | Accepted | (See duplicate CID 35) |  |  |  | done | Togashi
139 | Jussi Haapola | Centre for Wireless Communications / University of Oulu | 62 | 7.9.8.1 | 15 | Figure 7-20d should be Figure 7-57a | Correct it. | E | Yes | Accepted |  |  |  |  | done | Togashi
140 | Jussi Haapola | Centre for Wireless Communications / University of Oulu | 95 | 11a.2.3.2 | 1 | Figure 11a-6 'HCS caluculation' box should be 'HCS calculation' | Correct it. | E | Yes | Accepted | Redo Figure 11a-6 and 11a-8 |  |  |  | WIP re-create figures | kondou