## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [SG4v Closing Report for March 2016 Session]
Date Submitted: [17 March 2016]
Source: [Kunal Shah] Company [Silver Spring Networks]
Address [Redwood City, CA]
Voice:[], E-Mail:[kshah@silverspringnet.com]
Re: [SG4v closing report for March 2016 Session.]
Abstract: [Status update of SG4v March Session]
Purpose: [Report of SG4v activities during March 2016 Macau Plenary Meeting]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: SG4v Closing Report
March 17, 2015
Kunal Shah
SG4v Chair

## Slide 3
802.15 SG4v (Regional SUB 1GHz Bands)
  Project:
    Draft a PAR and CSD for formation of an 802.15 TG4v for development of usage of Regional Sub-GHz bands.
Notes: Jul 12, 2010
Page 3

## Slide 4: Meeting Objectives
Review PAR and CSD
Review received comments on PAR and CSD
Resolve comments received for PAR and CSD
Prepare Provisional Timeline
Next Steps

## Slide 5: Achievements
3 time slots used at this meeting
PAR & CSD Comments resolved - included in document 15-16-0265-00-0000-802-15-responses-to-15-4v-par-csd-comments
Provisional Timeline agreed – see slide 7

## Slide 6: Plan for May Interim
Hear Proposals

## Slide 7: Timeline
TG formation March 2016
Call for Proposals March 2016
Presentation of Proposals May 2016
Start Letter Ballot July 2016
LB comment resolution + 2 recirculations Aug – Nov 2016
Sponsor Ballot Nov 2016
SB comment resolution + 2 recirculations Dec – March 2017
RevCom submission March 2017

## Slide 8: Study Group approval of PAR and CSD
Request that the PAR and CSD contained in documents 15-16-0130-02 and 15-16-0131-01, respectively, be approved for submission to the WG for its approval and that the EC be requested to forward the PAR to NesCom
Moved by: Clint Powell
Seconded by: Frank Poegel
Approved by unanimous consent

## Slide 9: WG approval of PAR and CSD
Request that the PAR and CSD contained in documents 15-16-0130-02 and 15-16-0131-01, respectively, be approved by the IEEE 802.15 WG and that the EC be requested to forward the PAR to NesCom. The 802.15 working group chair and technical editor are authorized to make additional modifications to the PAR and CSD as needed to reflect EC discussion at its closing meeting.
Moved by: Kunal Shah
Seconded by: Tero Kivinen
Y: 42, N: 0, A: 0
Approved by unanimous consent

## Slide 10
Thank You