## Slide 1
Date: 2017-03-27
Author(s):
Suggested time lines for SG MG

## Slide 2
Suggested timeline for SPEC generation
March 2017 (Vancouver) - PAR and CSD for TG13 got approved, new contributions discussed | April 2017 Additional comments against 15.7m submission | May 2017 (Daejeon ) - Comments resolution against D1 of TG7r1 | June 2017 Generate D0 of TG13 Comment submission
July 2017 (Berlin) Commen resolution Decision on LC in 802.11  MAC Ad-hoc meeting in Berlin after Plenary | August 2017 Comment submission against D0 | September 2017 (Kona) Finalize comment resolution against D0 | October 2017 Generate D1 of TG13 Comment submission
November 2017 (Orlando) General discussion about PHY and MAC, Work on text | December 2017 - Comment submission against D1 until 1st January 2018 | January 2018 (Irvine) Comment resolution against D1 General discussion on MAC, PHY and document structure | February 2018 Generate D2 of TG13 Comment submission

## Slide 3
Suggested timeline for SPEC generation
March 2018 (Rosemont) Resolution of first comments | April 2018 - Sumbit further comments | May 2018(EU) Finalize comment resolution against D2 Start WG letter ballot process | June 2018 Create D3 Submit for letter ballot
July 2018 Resolve WG LB comments Start recirculation Start SB process | August 2018 Generate D4 Submit for SB | September 2018 Resolve SB comments Start submission to RevCom Get on the agenda of telco | 
November 2018 Hopefully standard is published Have party |  |  | 

## Slide 4
Thank you！