PHY VI schedule

Oct. 1 All the supplemental text for the D4 comment resolution will be uploaded to the Mentor

Oct. 15 Clean and complete text and text of PHY VI based on the D4 comment resolution to be provided to the Mentor by SNUST

Oct 17 Submit feedbacks against the above text to the Mentor

Oct 20 SNUST will revise their part of PHY VI text based on the feedback and will send it to the Mentor

Oct 20 – Oct 26 Technical Editor will revise the draft and release D5

Oct 27 – Nov. 2 submit comments against D5

Nov 3 – Nov 5 consolidate all the comments by Technical Editor

Nov 6 – Nov. 9 resolve comments

Nov 10 - proceed to WG Letter Ballot

Motion:

The committee accepts the above schedule.

Moved by Soo-Young Chang

Seconded by Hideki Aoyama

Yes 5

No 0

Abstain 0