## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [TG4s Closing Report for November 2017]
Date Submitted: [7 November 2017]
Source: [Shoichi Kitazawa] Company [Muroran IT]
Address [Hokkaido Japan]
Voice[], FAX: [], E-Mail:[kitazawa@ieee.org]
Re: []
Abstract: [Closing report for the TG4s November 2017.]
Purpose: [Closing report.]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: TG4s Closing Report for November 2017
Shoichi Kitazawa

## Slide 3: TG4s schedule for the week
 | Monday | Tuesday | Wednesday | Thursday
AM1 |  |  | Canceled | 
AM2 |  |  |  | 
PM1 |  |  |  | 
PM2 | TG4s Boca I | Canceled |  | Canceled

## Slide 4: Agenda
TG4s meeting call to order
Call for essential patents and policies & procedures reminder
Agenda Setting
Approve KOA meeting minutes
Comment resolution of Recirc. SB
Formation of BRC and approval to submit to RevCom
Plan for next meeting
Report on progress to WG

## Slide 5: Contributions
TG4s November 2017 Agenda (15-17-549r1)
TG4s September 2017 Meeting Minutes (15-17-619r0)
TG4s Opening information for November 2017 (15-17-617r0)
TG4s BRC Teleconference Minutes for November 2017 (15-17-572r2)
802.15 TG4s Consolidated Sponsor Ballot Comments (15-17-569r2)
802.15 TG4s Consolidated 1st recirculation Sponsor Ballot Comments (15-17-593r0)
TG4s Closing report for November 2017 (15-17-625r0)

## Slide 6: Time planning
TG Kickoff November 2014
Editing1st Draft May 2015
Motion for Letter Ballot July 2016
Initial Sponsor Ballot July 2017
Submission to RevCom December 2017
Timeline of TG4s (15-14-0559-r2)

## Slide 7
Year |  | 2014 |  | 2015 |  |  |  |  |  | 2016 |  |  |  |  |  | 2017 |  |  |  |  |  |  | 2018 | 
Month |  | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 12 | 1 | 3
TG Work Items | Start TG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Use Cases & TGD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Editing Draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Letter Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Initial Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Submission to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8: Result of Initial SB
Initial Ballot
Ballot Open Date: 04-Sep-2017
Ballot Close Date: 04-Oct-2017
Comments: 28
Must Be Satisfied Comments: 4
RESPONSE RATE
This ballot has met the 75% returned ballot requirement.
98 eligible people in this ballot group.
76 affirmative votes 1 total negative votes with comments 1 negative votes with new comments 1 negative votes without comments 3 abstention votes: (Conflict of Interest: 1, Lack of time: 2) 81 votes received = 82% returned
3% abstention
APPROVAL RATE
The 75% affirmation requirement is being met.
76 affirmative votes
1 negative votes with comments 77 votes = 98% affirmative

## Slide 9: Result of Recirc. SB
Recirculation #1 Initial Ballot
Ballot Open Date: 24-Oct-2017
Ballot Close Date: 03-Nov-2017
Comments: 2
RESPONSE RATE
This ballot has met the 75% returned ballot requirement.
98 eligible people in this ballot group.
77 affirmative votes
1 total negative votes with comments
0 negative votes with new comments
0 negative votes without comments
3 abstention votes: (Conflict of Interest: 1, Lack of time: 2)
81 votes received = 82% returned
3% abstention
APPROVAL RATE
The 75% affirmation requirement is being met.
77 affirmative votes
1 negative votes with comments
78 votes = 98% affirmative

## Slide 10: Next step
RevCom
January meeting
  1 meeting slots

## Slide 11: TG Motion #1
Motion for TG Approval to Form a TG4s BRC.
TG4s requests that 802.15 WG approve the formation of a Ballot Resolution Committee (BRC) for the SB balloting of the P802.15.4s-D07 with the following membership: Shoichi Kitazawa, Hidetoshi Yokota and Chris Calvert, Benjamin A. Rolfe and James Glib. The 802.15 TG4s BRC is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
Moved by: Hidetoshi Yokota Seconded by: Noriyuki Sato
Discussion: No
Objections: No

## Slide 12: WG Motion #1
Motion for WG Approval to Form a TG4s BRC.
Move that 802.15 WG approve the formation of a Ballot Resolution Committee (BRC) for the SB balloting of the P802.15.4s-D07 with the following membership: Shoichi Kitazawa, Hidetoshi Yokota, Ben Rolfe and James Glib. The 802.15.4s BRC is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P
Moved By: Seconded By
Discussion:
Objections:

## Slide 13: TG Motion #2
Motion for WG to Seek Unconditional Approval from EC to move to RevCom.
Motion: TG4s requests that 802.15 WG review and approve the CSD [15-14-0175-05-0sru] and requests unconditional approval from the EC to submit P802.15.4s/D07 to RevCom.
Moved by: Hidetoshi Yokota Seconded by: Noriyuki Sato
Discussion: No
Objections: No

## Slide 14: WG Motion #2
Motion for WG to Seek Unconditional Approval from EC to move to RevCom.
Motion: 802.15 WG has reviewed and approves theCSD [15-14-0175-05-0sru] and requests unconditional approval from the EC to submit P802.15.4s/D07 to RevCom.
Moved by: Seconded by:
Discussion:
Objections: