## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: WG Motion
Date Submitted: May 16, 2022
Source: Yeong Min Jang[Kookmin University]
Address
Voice: +82-2-910-5068 E-Mail: yjang@kookmin.ac.kr
Re:
Abstract: Material for discussion in 802.15.7a TG
Purpose: [Report progress to WG]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
802.15 WG motions

## Slide 3
Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for unconditional approval to send IEEE P802.15.7a/D2 to Letter Ballot.
The TG has resolved 11 comments received on drafts P802.15.7a/D1, resolved 11 comments received on draft P802.15.7a/D2.
The WG motion to request unconditional approval was approved during the May session of the 802.15 Working Group on 11 May 2022.
  Passed in the Working Group xx yes, xx no, xx abstain

## Slide 4
P802.15.7a Timeline
 | Open | Close
First Letter Ballot (LB1) | June 10, 2022 | July 10, 2022
Start LB1 comment resolution | July 10, 2022 | July 15, 2022
Finalize LB1 draft D3 Second Letter Ballot (LB2) | August 1, 2022 | September 15, 2022
LB2 comment resolution Finalize LB1 draft D3 Third Letter Ballot (LB2) | October 1, 2022 | November 15, 2022
Start LB2 comment resolution Prepare D5 for SB1 | December 1, 2022 | January 15, 2023
Finish SB1 comment resolution Prepare D6 for submittal for SA SB2 | February 1, 2022 | March 15, 2023
Prepare Draft D7 for SA submittal final approval | April 1, 2023 | May 15, 2023
Resolve final SA editorial comments Prepare final draft D7 for submittal for publication | June 1, 2023 | July 15, 2023

## Slide 5
Motions
WG:
  IEEE 802.15 has reviewed and requests unconditional approval to submit “Draft D2: Merged Document for IEEE 802.15.7a” to Standards Association ballot.
  Moved by Yeong Min Jang
  Vote: xx/xx/xx (Y/N/A)