## IEEE_Cover
January 2023 |  | Doc: 15-23-0056-10-006ma
IEEE P802.15
Wireless Speciality Networks
Project | IEEE P802.15 Working Group for Wireless Speciality Networks (WSNs)
Title | Progess report of 802.15.6ma TOC
Date Submitted | January 19th, 2023
Source | Marco Hernandez1,3, Ryuji Kohno1,2, Takumi Kobayashi1,2, Minsoo Kim1
1YRP-IAI, Japan; 2YNU, Japan. 3CWC Oulu Univ. Finland
Re: | In response to Call for Proposals.
Purpose | Material for discussion.
Notice | This document has been prepared to assist the IEEE P802.15.6ma. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.6ma.

## TOC
Contents | Status | Progress | Notes
1. Overview | Done | 100%
1.1 Scope | Done | 100%
1.2 Purpose | Done | 100%
1.3 Word usage | Done | 100%
2. Normative references | Done | 100%
3. Definitions, acronyms, and abbreviations | In progress | 90% | Introduction of new terms and revision of old terms for next release
3.1 Definitions | In progress | 90%
3.2 Special terms | In progress | 90%
3.3 Acronyms and abbreviations | In progress | 90%
4. General framework elements | Done | 100%
4.1 General | Done | 100%
4.2 Network topology | Done | 100%
4.3 Reference model | Done | 100%
4.4 Time base | In progress | 60% | Define group superframe duration. Simulations
4.5 MAC and security state diagrams | Done | 100%
4.6 Security paradigm | Done | 100%
4.7 Main revisions | Done | 100%
5. MAC frame formats | In progress | 90% | HRP MAC frame formats mostly done
5.1 Conventions | Done | 100%
5.2 HRP MAC frame formats | In progress | 90% | HRP MAC frame formats mostly done
5.3 MAC frame formats legacy | Done | 100%
5.4 General format | Done | 100%
5.5 Management type frames | Done | 100%
5.6 Control type frames | Done | 100%
5.7 Data type frames | Done | 100%
5.8 MAC/PHY Capability fields | Done | 100%
5.9 Information elements | Done | 100%
6. MAC functions | Done | 100%
6.1 HRP MAC | In progress | 60% | Advancing HRP MAC functionality
6.2 General | In progress | 60% | Advancing HRP MAC functionality
6.3 Superframe structure | In progress | 60% | Advancing HRP MAC functionality
6.4 MAC functions legacy | Done | 100% | The legacy MAC-2012 seems to generate confusion between implementers. As it is in the main body with "shall" sentences it looks normative. Potential solutions: 1) Move the MAC-2012 to an Annex. 2) Move MAC-2012 to a new clause and clarify is normative for BANs 2012 implementations, and the new MAC clause is for BANs 2024 implentations (dependable BANs). 3) Delete the MAC-2012 as nobody implements it anyway and the revision allows such depecration.
6.5 General | Done | 100%
6.6 Frame processing | Done | 100%
6.7 Access classification and division | Done | 100%
6.8 BAN creation/operation and node connection/disconnection | Done | 100%
6.9 Random access | Done | 100%
6.10 Improvised access and unscheduled access | Done | 100%
6.11 Scheduled access and scheduled-polling access | Done | 100%
6.12 Access continuation, termination, and timeout | Done | 100%
6.13 MICS band communication | Done | 100%
6.14 Two-hop star topology extension | Done | 100%
6.15 Clock synchronization and guard time provisioning | Done | 100%
6.16 Power management | Done | 100%
6.17 Coexistence and interference mitigation | Done | 100%
6.18 MAC/PHY capability handling/interaction and Application Specific IE usage | Done | 100%
6.19 MAC sublayer parameters | Done | 100%
7. Security services | Done | 100%
7.1 Security association and disassociation | Done | 100%
7.2 PTK creation and GTK distribution | Done | 100%
7.3 Message security | Done | 100%
7.4 Optional cipher functions | Done | 100%
8. Narrowband PHY specification | Done | 100%
8.1 Data-rate-dependent parameters | Done | 100%
8.2 PLCP preamble | Done | 100%
8.3 PLCP header | Done | 100%
8.4 PSDU | Done | 100%
8.5 Constellation mapping | Done | 100%
8.6 General requirements | Done | 100%
8.7 PHY layer timing | Done | 100%
8.8 Transmitter specifications | Done | 100%
8.9 Receiver specifications | Done | 100%
9. UWB PHY specification | In progress | 90% | HRP UWB PHY timing parameters. Interference mitigation. FEC parameters
9.1 HRP UWB PHY | In progress | 90% | HRP UWB PHY timing parameters. Interference mitigation. FEC parameters
9.2 Legacy UWB PHY | Done | 100% | The legacy PHY-2012 seems to generate confusion between implementers. As it is in the main body with "shall" sentences it looks normative. Potential solutions: 1) Move the PHY-2012 to an Annex. 2) Move PHY-2012 to a new clause and clarify is normative for BANs 2012 implementations, and the new PHY clause is for BANs 2024 implentations (dependable BANs). 3) Delete the PHY-2012 as nobody implements it anyway and the revision allows such depecration.
10. Ranging. Relative positioning, and localization | In progress | 10% | Missing text
10.1 General | In progress | 10% | Missing text
10.2 Ranging requirements measurements by two-way ranging | In progress | 10% | Missing text
Annex A (informative) Bibliography | Done | 100%
Annex B (informative) Coexistence applicability guide | Done | 100%
Annex C (informative) Ultra wideband | Done | 100%
C.1 On-off signaling and group pulse position modulation | Done | 100%
C.2 Soft detection | Done | 100%
C.3 Shortened BCH codes | Done | 100%
C.4 Receiver sensitivity | Done | 100%
C.5 Effective transmit power | Done | 100%
Annex D (informative) Pulse shapes | Done | 100%
D.1 Chirp pulse shape | Done | 100%
D.2 Chaotic pulse waveform | Done | 100%
Annex E (informative) Bibliography | Done | 100%