## IEEE_Cover
March 2025 |  | Doc: 15-23-0056-12-006ma
IEEE P802.15
Wireless Speciality Networks
Project | IEEE P802.15 Working Group for Wireless Speciality Networks (WSNs)
Title | Progess report of 802.15.6ma TOC
Date Submitted | March 13th, 2025
Source | Marco Hernandez1,3, Ryuji Kohno1,2, Takumi Kobayashi1,2, Minsoo Kim1
1YRP-IAI, Japan; 2YNU, Japan. 3CWC Oulu Univ. Finland
Re: | In response to Call for Proposals.
Purpose | Material for discussion.
Notice | This document has been prepared to assist the IEEE P802.15.6ma. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.6ma.

## TOC
Contents | Status | Progress | Notes
1. Overview | Done | 100%
1.1 Scope | Done | 100%
1.2 Purpose | Done | 100%
1.3 Word usage | Done | 100%
2. Normative references | Done | 100%
3. Definitions, acronyms, and abbreviations | Done | 100%
3.1 Definitions | Done | 100%
3.3 Acronyms and abbreviations | Done | 100%
4. General framework elements | Done | 100%
4.1 General | Done | 100%
4.2 Network topology | Done | 100%
4.3 Reference model | Done | 100%
4.4 Time base | Done | 100% | Defined group superframe duration by simulations
4.5 MAC and security state diagrams | Done | 100%
4.6 Security paradigm | Done | 100%
4.7 Rrevision overvieew | Done | 100%
5. MAC frame formats | Done | 100%
5.1 Conventions | Done | 100%
5.2 MAC frame format revision and legacy | Done | 100%
5.3 HRP MAC frame formats | Mostly Done | 90%
5.4 Control frames | Done | 100%
5.5 Data frames | Done | 100%
5.6 Management frames | Done | 100%
5.7 MAC frame formants legacy | Done | 100%
5.8 Management type frames | Done | 100%
5.9 Control type frames | Done | 100%
5.10 Data type frames | Done | 100%
5.11 MAC/PHY Capability fields | Done | 100%
5.12 Information elements | Done | 100%
6. MAC functions | Done | 100%
6.1 MAC functions and IEEE Std 802.15.6-2012 | Done | 100%
6.2 HRP MAC | Mosty Done | 90%
6.3 Channel access | Done | 100%
6.4 MAC services | Done | 100%
6.5 MAC functions legacy | Done | 100%
6.6 Access classification and division | Done | 100%
6.7 BAN creation/operation and node connection/disconnection | Done | 100%
6.8 Random access | Done | 100%
6.9 Improvised access and unscheduled access | Done | 100%
6.10 Scheduled access and scheduled-polling access | Done | 100%
6.11 Access continuation, termination, and timeout | Done | 100%
6.12 MICS band communication | Done | 100%
6.13 Two-hop star topology extension | Done | 100%
6.14 Clock synchronization and guard time provisioning | Done | 100%
6.15 Power management | Done | 100%
6.16 Coexistence and interference mitigation | Done | 100%
6.17 MAC/PHY capability handling/interaction and Application Specific IE usage | Done | 100%
6.18 MAC sublayer parameters | Done | 100%
7. Security services | Done | 100%
7.1 Security association and disassociation | Done | 100%
7.2 PTK creation and GTK distribution | Done | 100%
7.3 Message security | Done | 100%
7.4 Optional cipher functions | Done | 100%
8. Narrowband PHY specification | Done | 100%
8.1 Data-rate-dependent parameters | Done | 100%
8.2 PLCP preamble | Done | 100%
8.3 PLCP header | Done | 100%
8.4 PSDU | Done | 100%
8.5 Constellation mapping | Done | 100%
8.6 General requirements | Done | 100%
8.7 PHY layer timing | Done | 100%
8.8 Transmitter specifications | Done | 100%
8.9 Receiver specifications | Done | 100%
9. UWB PHY specification | Done | 100%
9.1 HRP UWB PHY | Mostly Done | 90%
9.2 Legacy UWB PHY | Done | 100%
Annex A (informative) Bibliography | Done | 100%
Annex B (informative) Coexistence applicability guide | Done | 100%
Annex C (informative) Ultra wideband | Done | 100%
C.1 On-off signaling and group pulse position modulation | Done | 100%
C.2 Soft detection | Done | 100%
C.3 Shortened BCH codes | Done | 100%
C.4 Receiver sensitivity | Done | 100%
C.5 Effective transmit power | Done | 100%
Annex D (informative) Pulse shapes | Done | 100%
D.1 Chirp pulse shape | Done | 100%
D.2 Chaotic pulse waveform | Done | 100%
Annex E (informative) Bibliography | Done | 100%