## IEEE Cover page
January 2023 |  | 15-23-0083-00-0mag
IEEE P802.15
Wireless Specialty Networks
Project | IEEE SC Maintenance
Title | Template for the project task list
Date Submitted | 2023-01-19
Source | Tero Kivinen | kivinen@iki.fi
Re:
Abstract | Project task list
Purpose | Provide template for the projects to use as their task list
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Project process
# | Step | Date completed | Comments or Motions | Notes | Operation manual reference
S1 | Start interest group |  | optional | WG Chair will create IG if there is enough interest | OM 8
S2 | Start study group |  | optional but recommended |  | OM 6
S2.01 | WG motion to form a SG |  | WG Motion 13.1.1 |  | OM 6.2
S2.02 | LMSC approval of the SG
S2.03 | Only for between two planeries, if going on longer, request extension |  | WG motion 13.1.2 |  | OM 6.3
S2.04 | Report SG progress to LMSC in every plenary |  |  |  | OM 6.6.2
S2.05 | Create PAR |  |  | Project Authorization Request
S2.06 | Create CSD |  | if needed | Criteria for standards development
S2.07 | SG approval of PAR and CSD |  | SG Motion 13.1.3
S2.08 | WG motion to approve PAR and CSD |  | WG Motion 13.1.4
S2.09 | The PAR needs to be put to the LMSC agenda 30 days before meeting
S2.10 | Receive comments to the PAR |  |  | Comments from other working groups
S2.11 | Process comments to the PAR and respond to them
S2.12 | TG motion to approval of comment responses for PAR and CSD |  | SG Motion 13.1.5
S2.13 | WG motion to approval of comment responses for PAR and CSD |  | WG Motion 13.1.6
S2.14 | LMSC approval of the TG
S2.15 | NesCom approval of the TG |  |  | TG can start its work even before this.
S3 | Start task group |  |  |  | OM 4
S3.1 | TG chair selection |  |  | Appointed by WG chair, confirmed by a TG | OM 4.2
S3.2 | TG vice chair selection |  | optional | Appointed by TG chair, confirmed by a TG | OM 4.3
S3.3 | TG secretary selection |  |  | Appointed by TG chair | OM 4.4
S3.4 | TG technical editor selection |  |  | Appointed by TG chair, confirmed by a TG | OM 4.5
S4 | Task group working
S4.1 | Work on the draft and get it ready.
S4.2 | Create CA Document |  | if needed | Coexistance Assessment
S5 | Task group management
S5.1 | WG approval to extend a par |  | WG Motion 13.1.7 | Do this early enough before the actual PAR expires.
S6 | Initial letter ballot |  |  | Initial ballot is 30 days | OM 3.10
S6.1 | Verify whether WG chair has assigned TEG (Techincal Export Group) for the TG, and if so send the draft to them 4 weeks before
S6.2 | WG technical editor review
S6.3 | TG motion when draft completed and ready for letter ballot |  | TG Motion 13.2.1.1 | If draft is ready use this motion, if it needs to be edited, use next one.
S6.4 | TG motion when draft needs to be editied prior letter ballot |  | TG Motion 13.2.1.2 | If comment resolutions are ready, but not all changes are made to the draft yet.
S6.5 | Draft needs to be posted to the private area |  |  | TG technical editor sends the clean version of the draft in PDF format to the WG chair. WG Chair will post it in private area.
S6.6 | Draft needs to be announced in the 802.15 WG reflector |  |  | TG chair needs to send email announcing that draft is posted in the private area.
S6.7 | WG motion when draft completed and ready for letter ballot |  | WG Motion 13.2.2.1 | If draft is ready use this motion, if it needs to be edited, use next one.
S6.8 | WG motion when draft needs to be editied prior letter ballot |  | WG Motion 13.2.2.2 | If comment resolutions are ready, but not all changes are made to the draft yet.
S6.9 | WG chair or designee starts the letter ballot
S6.10 | WG chair sends a list of ballot pool to the TG chair
S6.11 | TG chair will keep track of all votes cast, and marks them up in the ballot pool sheet. |  |  | Can also delegate iit to some of the other officer
S6.12 | TG chair collects all comments submitted during the letter ballot period
S6.13 | After the ballot closes the TG chair will submit current tally of the votes cast to the WG chair, and WG chair announces it to the 802.15 WG reflector. |  |  | Record results on the “Letter ballot results” tab in this sheet.
S6.14 | TG chair or techincal editor creates a combined sheet of comments received and posts it to mentor |  |  | Remove email addresses, phone numbers etc before posting
S6.15 | After ballot closes resolve the comments either in or during the meeting.
S6.16 | TG/CRG motion to approve of comment responses.
S6.17 | Create new version of the draft
S7 | Letter ballot recirculations |  |  | Recirculations are 15 days | OM 3.10
S7.1 | TG motion when draft is completed and ready for 1st recirculation letter ballot |  | TG Motion 13.2.1.x | If draft is ready use this motion, if it needs to be edited, use next one.
S7.2 | TG motion when draft needs to be editied prior 1st recirculation letter ballot |  | TG Motion 13.2.1.x | If comment resolutions are ready, but not all changes are made to the draft yet.
S7.3 | Draft needs to be posted to the private area |  |  | TG technical editor sends the clean version of the draft in PDF format to the WG chair. WG Chair will post it in private area. It is recommended to include the redline version showing changes between the this version and previous version.
S7.4 | WG motion when draft is completed and ready for 1st recirculation letter ballot |  | WG Motion 13.2.2.3 | If draft is ready use this motion, if it needs to be edited, use next one.
S7.5 | WG motion when draft needs to be editied prior 1st recirculation letter ballot |  | WG Motion 13.2.2.4 | If comment resolutions are ready, but not all changes are made to the draft yet.
S7.6 | Form of CRG for letter ballot |  |  | OM 5.2, must be voting members, no company or organization can majority (25% or over)
S7.7 | TG motion to create CRG for Letter ballot |  | TG Motion 13.3.1
S7.8 | WG motion to create CRG for Letter ballot |  | WG Motion 13.3.1
S7.9 | WG chair starts the recirculation letter ballot
S7.10 | TG chair will keep track of all votes cast during the recirculation ballot, and marks them up in the ballot pool sheet.
S7.11 | TG chair collecs all comments submitted during the letter ballot period
S7.12 | After the ballot closes the TG chair will submit current tally of the votes cast to the WG chair, and WG chair announces it to the 802.15 WG reflector |  |  | Record results on the “Letter ballot results” tab in this sheet.
S7.13 | TG chair or techincal editor creates a combined sheet of comments received and posts it to mentor |  |  | Remove email addresses, phone numbers etc before posting
S7.14 | Resolve the comments either in CRG, or during the meeting.
S7.15 | TG/CRG motion to approval of comment responses.
S7.16 | Create new version of the draft
S7.17 | Repeat S6 as many times as needed
S8 | Standard association ballot |  |  | Initial ballot is 30 days
S8.1 | WG chair grants permission for the TG chair or designee to run standard association process in the myproject
S8.2 | MEC review |  |  | Can take up to 4 weeks, can be done during the letter ballot phase too.
S8.3 | Sponsor pool formation |  |  | At minimum 30 days, and it is valid for 6 months.
S8.4 | LMSC package creation |  |  | Includes letter ballot vote and comment summaries, plus list of unresolved comments from remaining no voters. Use the informaton in “Letter ballot result” tab of this sheet
S8.5 | TG motion when the draft is ready for unconditional submittal for Standards Association ballot |  | TG Motion 13.4.1.2 | Draft has finished letter ballots and is ready for standard association ballot.
S8.6 | TG motion when the draft needs conditional submittal for Standards Association ballot |  | TG Motion 13.4.1.1 | We still have work to be do, for example fnish editing, or close up the last or second last letter ballot. You can still have one more letter ballot going after getting this permission.
S8.7 | Form of CRG for standards association ballot |  |  | OM 5.2, must be voting members, no company or organization can majority (25% or over)
S8.8 | TG motion to create CRG for standards association ballot |  | TG Motion 13.3.2
S8.9 | WG motion when the draft is ready for unconditional submittal for Standards Association ballot |  | WG Motion 13.4.2.2 | Draft has finished letter ballots and is ready for standard association ballot.
S8.10 | WG motion when the draft needs conditional submittal for Standards Association ballot |  | WG Motion 13.4.2.1 | We still have work to be do, for example fnish editing, or close up the last or second last letter ballot. You can still have one more letter ballot going after getting this permission.
S8.11 | WG motion to create CRG for standards association ballot |  | WG Motion 13.3.2
S8.12 | TG chair request a sponsor ballot initiation
S8.13 | PM approves and starts the sponsor ballot
S8.14 | After the ballot finishes the TG chair will check the results from myproject |  |  | Record results on the “Standard association results” tab in this sheet.
S8.15 | TG chair or technical editor creates a combined sheet of comments received and posts it to mentor |  |  | Remove email addresses, phone numbers etc before posting
S8.16 | Resolve the comments either in CRG, or during the meeting.
S8.17 | TG/CRG motion to approval of comment responses.
S9 | Standard association recirculation ballot |  |  | Recirculations are 10 days
S9.1 | TG motion when draft is completed and ready for 1st recirculation Standards Association ballot |  | TG Motion 13.4.1.3 | If draft is ready use this motion, if it needs to be edited, use next one.
S9.2 | TG motion when draft needs to be editied prior 1st recirculation Standards Association ballot |  | TG Motion 13.4.1.4 | If comment resolutions are ready, but not all changes are made to the draft yet.
S9.3 | WG motion when draft is completed and ready for 1st recirculation Standards Association ballot |  | WG Motion 13.4.2.3 | If draft is ready use this motion, if it needs to be edited, use next one.
S9.4 | WG motion when draft needs to be editied prior 1st recirculation Standards Association ballot |  | WG Motion 13.4.2.4 | If comment resolutions are ready, but not all changes are made to the draft yet.
S9.5 | TG chair request a sponsor ballot initiation
S9.6 | PM approves and starts the sponsor ballot
S9.7 | After the ballot finishes the TG chair will check the results from myproject |  |  | Record results on the “Standard association results” tab in this sheet.
S9.8 | TG chair or techincal editor creates a combined sheet of comments received and posts it to mentor |  |  | Remove email addresses, phone numbers etc before posting
S9.9 | Resolve the comments either in CRG, or during the meeting.
S9.10 | TG/CRG motion to approval of comment responses.
S9.11 | Create new version of the draft
S9.12 | Repeat S9 as many times as needed
S10 | Revcom Submission
S10.1 | Create presentation for going to RevCom |  |  | 15-21-0624-00-0mag-template-for-ec-to-revcom-presentation.pptx
S10.2 | TG motion for unconditional submittal for revcom |  | TG Motion 13.5.1.1 | Draft has finished letter ballots and is ready for RevCom.
S10.3 | TG motion for conditional submittal for revcom |  | TG Motion 13.5.1.2 | We still have work to be do, for example fnish editing, or close up the last or second last standard association ballot. You can still have one more standard association ballot going after getting this permission.
S10.4 | WG motion for unconditional submittal for revcom |  | TG Motion 13.5.2.1 | Draft has finished letter ballots and is ready for RevCom.
S10.5 | WG motion for conditional submittal for revcom |  | TG Motion 13.5.2.2 | We still have work to be do, for example fnish editing, or close up the last or second last standard association ballot. You can still have one more standard association ballot going after getting this permission.
S10.6 | Address any comments received from RevCom
S10.7 | RevCom approval
S10.8 | TG chair sends a list of people who should be revarded / recognized to WG chair
S11 | IEEE Editor phase
S11.1 | IEEE editor edits the document
S11.2 | WG chair needs to send the list of WG members to IEEE editors to be included in the draft.
S11.3 | IEEE editor sends comments and edits to TG Chair and TG technical editor for approval
S11.4 | IEEE publishes the document

## Letter ballot results
| Ballot start date | Ballot end date | Voters | Voted | Yes | Abstrain | No | % Voters | % Yes | % Abstain | Draft version | # Comments | # Technical Comments | # Editorial Comments
Initial letter ballot
1st recirculation letter ballot
2nd recirculation letter ballot
3rd recirculation letter ballot
4th recirculation letter ballot
5th recirculation letter ballot
6th recirculation letter ballot
7th recirculation letter ballot
8th recirculation letter ballot
9th recirculation letter ballot

## Sponsor ballot results
| Ballot start date | Ballot end date | Ballot group members | Return ballots | Approval rate | Approve | Disapprove With MBS Comment(s) | Disapprove Without MBS Comment(s) | Abstentions | Total Comments
Initial standard association ballot
1st standard association recirculation ballot
2nd standard association recirculation ballot
3rd standard association recirculation ballot
4th standard association recirculation ballot
5th standard association recirculation ballot
6th standard association recirculation ballot
7th standard association recirculation ballot
8th standard association recirculation ballot
9th standard association recirculation ballot