## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: TG 15.4ab Agenda and Meeting Slides
Date Submitted: 14 February 2023
Source: Benjamin A. Rolfe (Blind Creek Associates)
Contact:
Voice: +1 408 395 7207, E-Mail: ben.rolfe @ ieee.org
Re: Task Group 4ab: 802.15.4 UWB Next Generation
Abstract: Teleconference (WebEx) Agenda and Meeting Slides
Purpose: Continue project progress
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
Notes: Jul 12, 2010
Page 1

## Slide 2: Task Group 15.4ab Next Generation UWB Amendment
Teleconference / Virtual Meeting
February 14th, 2023

## Slide 3: Task Group Rules
Discussion: Everyone present is welcome
Straw polls: Everyone present may vote
Formal motions: WG voters
  To make, second and vote
Patent policy for PAR activities applies
All the usual rules of conduct
Please identify yourself on first contact with name and affiliation

## Slide 4: IEEE-SA Patent, Copyright, and Participation Policies
See: https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Patent Slides for Standards Development Meetings (.pdf)
https://development.standards.ieee.org/myproject/Public/mytools/mob/slideset.pdf
IEEE-SA Standards Board Patent Committee (PatCom) home page
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Working Group Copyright Materials
https://standards.ieee.org/ipr/copyright-materials.html
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/ieee-sa-copyright-policy-2019.pdf

## Slide 5: Participants have a duty to inform the IEEE
  Participants shall inform the IEEE (or cause the IEEE to be informed) of the identity of each holder of any potential Essential Patent Claims of which they are personally aware if the claims are owned or controlled by the participant or the entity the participant is from, employed by, or otherwise represents
  Participants should inform the IEEE (or cause the IEEE to be informed) of the identity of any other holders of potential Essential Patent Claims
  Early identification of holders of potential Essential Patent Claims is encouraged

## Slide 6: Ways to inform IEEE
Cause an LOA to be submitted to the IEEE SA (patcom@ieee.org); or
Provide the chair of this group with the identity of the holder(s) of any and all such claims as soon as possible; or
Speak up now and respond to this Call for Potentially Essential Patents
If anyone in this meeting is personally aware of the holder of any patent claims that are potentially essential to implementation of the proposed standard(s) under consideration by this group and that are not already the subject of an Accepted Letter of Assurance, please respond at this time by providing relevant information to the WG Chair
08 June 2021 – Slide 2

## Slide 7: Other Guidelines for IEEE Working Group Meetings
All IEEE SA standards meetings shall be conducted in compliance with all applicable laws, including antitrust and competition laws.
  Don’t discuss the interpretation, validity, or essentiality of patents/patent claims.
  Don’t discuss specific license rates, terms, or conditions.
    Relative costs of different technical approaches that include relative costs of patent licensing terms may be discussed in standards development meetings.
      Technical considerations remain the primary focus.
  Don’t discuss or engage in the fixing of product prices, allocation of customers, or division of sales markets.
  Don’t discuss the status or substance of ongoing or threatened litigation.
  Don’t be silent if inappropriate topics are discussed. Formally object to the discussion immediately.
---------------------------------------------------------------
For more details, see IEEE SA Standards Board Operations Manual, clause 5.3.10 and Antitrust and Competition Policy: What You Need to Know at http://standards.ieee.org/develop/policies/antitrust.pdf

## Slide 11: IEEE SA Copyright Policy
By participating in this activity, you agree to comply with the IEEE Code of Ethics, all applicable laws, and all IEEE policies and procedures including, but not limited to, the IEEE SA Copyright Policy.
    Previously Published material (copyright assertion indicated) shall not be presented/submitted to the Working Group nor incorporated into a Working Group draft unless permission is granted.
    Prior to presentation or submission, you shall notify the Working Group Chair of previously Published material and should assist the Chair in obtaining copyright permission acceptable to IEEE SA.
    For material that is not previously Published, IEEE is automatically granted a license to use any material that is presented or submitted.

## Slide 12: IEEE SA Copyright Policy
    The IEEE SA Copyright Policy is described in the IEEE SA Standards Board Bylaws and IEEE SA Standards Board Operations Manual
      IEEE SA Copyright Policy, see Clause 7 of the IEEE SA Standards Board Bylaws https://standards.ieee.org/about/policies/bylaws/sect6-7.html#7 Clause 6.1 of the IEEE SA Standards Board Operations Manual https://standards.ieee.org/about/policies/opman/sect6.html
    IEEE SA Copyright Permission
      https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/permissionltrs.zip
    IEEE SA Copyright FAQs
      https://standards.ieee.org/faqs/copyrights/
    IEEE SA Best Practices for IEEE Standards Development
    http://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/best_practices_for_ieee_standards_development_051215.pdf
    Distribution of Draft Standards (see 6.1.3 of the SASB Operations Manual)
      https://standards.ieee.org/about/policies/opman/sect6.html

## Slide 13: IEEE 802 Ground Rules
Respect … give it, get it
NO product pitches
NO corporate pitches
NO prices
NO restrictive notices – (no confidentially notices in email)
Presentations must be openly available

## Slide 14: Proposed Agenda
Opening and meeting preamble
Technical work items
  Review Revise MMS-NBA merged TFD [15-22-0381-02]
  General status (help needed?)
Editor’s corner
Next steps
  Next weeks meeting
  March planning
Any other Business

## Slide 15: Recap

## Slide 16: 5.2.b Scope of the project (As approved):
This amendment enhances the Ultra Wideband (UWB) physical layers (PHYs) medium access control (MAC), and associated ranging techniques while retaining backward compatibility with enhanced ranging capable devices (ERDEVs). Areas of enhancement include:
  additional coding, preamble and modulation schemes to additional coding, preamble and modulation schemes to support improved link budget and/or reduced air-time relative to IEEE Std 802.15.4 UWB;
  additional channels and operating frequencies;
  interference mitigation techniques to support greater device density and higher traffic use cases relative to the IEEE Std 802.15.4 UWB;
  improvements to accuracy, precision and reliability and interoperability for high-integrity ranging; schemes to reduce complexity and power consumption;
  definitions for tightly coupled hybrid operation with narrowband signaling to assist UWB;
  enhanced native discovery and connection setup mechanisms;
  sensing capabilities to support presence detection and environment mapping;
  and mechanisms supporting low-power low-latency streaming as well as high data-rate streaming allowing at least 50 Mb/s of throughput.
Support for peer-to-peer, peer-to-multi-peer, and station-to-infrastructure protocols are in scope, as are infrastructure synchronization mechanisms. This amendment includes safeguards so that the high throughput data use cases do not cause significant disruption to low duty-cycle ranging use cases.
https://development.standards.ieee.org/myproject-web/app#viewpar/9081

## Slide 17: Project Schedule (working baseline)
Notes: SASB/RevCom schdule for 2024 a guess
Proposed project schedule |  | May-22 | Jun-22 | Jul -22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov24 | Dec 25 | Jan 26 | Feb 26 | Mar 26 | Apr 26 | 
Hear and evaluate proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, PHY features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, MAC features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate poposals/contributions into TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft from TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG draft review and revision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Working group pre-ballot review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-ballot review and comment resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First letter ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 1st recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional approval for SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 2nd recirc and final recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, first SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, SA recirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 2nd SA recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional or unconditional approval to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Optional 3rd SA recirc if needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RevCom meets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | `
You are Here

## Slide 18: Schedule Major Milestones
Call for proposals | November 2021
Cut-off for new features (high level feature set), PHY | May 2022
Cut-off for new features (high level feature set), MAC | July 2022
Draft 0 | Post-January 2023
TG draft review and revision complete | February - March 2023
Working group pre-ballot review commence | March – May 2023 (following March meeting)
First letter ballot | June 2023 (following meeting)
… | 
Near Term Working Milestones

## Slide 19: Technical Discussion

## Slide 20: MMS-NBA
Following discussion and input on the ad hoc last week, rev 2 has been posted:
https://mentor.ieee.org/802.15/dcn/22/15-22-0381-02-04ab-nba-uwb-ranging-text-proposal-for-15-4ab-tfd.docx

## Slide 21: General Status
Any areas that appear “stuck”?
Any crossroads ahead?
Straw poll or motions to bring?
Areas ready to integrate?
Any questions for the TE, Chair, Vice Chairs?

## Slide 22: Editor’s corner

## Slide 23: Next Steps

## Slide 24: Next week: Working Session
Candidate to work next week ??

## Slide 25: Other Stuff
Joint sessions with TG6a:
TG6a chair has proposed joint Webexs, one in a TG6a time slot and one in the TG4ab time slot:
  5am PT/ 8am ET Monday Feb 20th
  6am PT/9am ET Tuesday March 7th
General topic: UWB PHY for 802.15.6

## Slide 26: Interim Webex Schedule
February ‘23 |  |  |  |  |  | 
S | M | T | W | T | F | S
. | . | . | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 |  |  |  | 
March ‘23 |  |  |  |  |  | 
S | M | T | W | T | F | S
 |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 | 29 | 30 | 31 | 
Every other week on Tuesday (3 calls)
Time: 06:00 PT
Commence 31-January at 06:00 PT
Note1: Alternate Tuesdays a WG Webex will be setup for ad hoc working sessions (in between TG calls)
Note 2: TG6a chair has proposed joint calls: one will use TG6a time (5am PT) and one will use TG4ab time
802 Plenary
Next Call: TBD
Working Call: TBD
Joint w/TG6a
Joint w/TG6a
Today

## Slide 27: Coming Attractions
March Plenary in Atlanta, GA, USA

## Slide 28: Other Business?

## Slide 29: Adjourned Thanks