## IEEE Cover
March 2025 |  | Doc: P802.15-23-0361-11-6ma
IEEE 802.15
Wireless Specialty Networks
Title | TG6ma Timeline
Date submitted | March 13th, 2025
Source | Marco Hernandez; YRP-IAI, Japan, CWC Oulu Univ. Finland
Ryuji Kohno; YRP-IAI, Japn, YNU, Japan
Purpose | TG timeline
Notice | This document has been prepared to assist the IEEE P802.15.6ma as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and IEEE P802.15 may make it publicly available.

## TG Schedule
Topic item | Deadline | Action items | Notes
Std Draft D3 WG letter ballot circulation.(LB210) | November 10/2024 | Disposition of comments. | Assignments of resolutions and discussion of changes.
Towards the January 2025 meeting | January/2025 | Comments Resolution | Discussion of pending resolutions. Some resolutions are easy, but some others will take time to implement.
1st letter ballot(LB212) recirculation | March 5/2025 | Prepare the next draft release before the March meeting | Resolutions of comments. At this stage, we expect few comments.
Towards the March 2025 meeting | March/2025 | Comment Resolution | Resolutions of comments. At this stage, we expect few comments.
2nd LB recirculation | April/2025 | Prepare the next draft release before the July meeting | At this stage, the draft should be stable (after July no more changes)
Towards the May 2025 meeting | May/2025 | Comment Resolution | Resolutions of comments. At this stage, we expect few comments.
Conditional approval for Standard Association(SA)Sponsor Ballot | July/2025 | No draft changes. Request approval for sponsor ballot submission to the EC | Preparation for sponsor ballot submission. IEEE SA editorial review.
IEEE SA Sponsor Ballot submission | August/2025
1st SA recirculation | September/2025
Submission to RevCom | October/2025