## List
Std | Status | Information Motion |  | Draft/STD liaised |  | Adoption Motion |  | STD | 60-day |  | Comments Motion |  | 5-month |  | Comments Motion |  | Comments
|  | WG | LMSC |  |  | WG | LMSC | sent | pre-ballot |  | Motion | Sent | FDIS ballot |  | Motion | Sent
802.15.3 | Completed | done | done |  |  | done | done | Y | Passed | 2016-10-01 | n/a | n/a | Passed | 2017-09-01 | n/a | n/a
802.15.3-2016 | No need | done | 7-Jun-2022 | No need | - | done | 7-Jun-2022 |  | No need | - | - | - | No need | - | - | -
802.15.3d-2017 | in .3-2023 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.3e-2017 | in .3-2023 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.3f-2017 | in .3-2023 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.3-2023 | In 60 day ballot | 2023-11-16 | 2023-11-17 | Std | Feb 2024 | 2024-05-16 | 2024-07-19 | Y | Closes | 2024-11-27
802.15.4 | Completed | [6 empty] | Y | Passed | 2017-04-01 | n/a | n/a | Passed | 2018-01-01 | n/a | n/a
802.15.4x-2019 | in .4-2020 | done | 7-Jun-2022 | No need | - | - | - |  | No need | - |  |  | No need
802.15.4-2020 | Completed | done | 7-Jun-2022 | Std | Jan 2023 | done | 7-Jun-2022 | Y | Passed | 2023-11-12 | comments from India | comments from India | Passed | 2024-07-24
802.15.4w-2020 | in .4-2024 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.4y-2021 | in .4-2024 | 2023-11-16 | 2023-11-17 | Std | Jan 2024 | hold | - | - | - | - | - | - | - | - | - | -
802.15.4z-2020 | in .4-2024 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.4aa-2022 | in .4-2024 | done | 7-Jun-2022 | Std | Jan 2023 | hold | - | - | - | - | - | - | - | - | - | -
802.15.4-2024 | Draft needs to be sent | 2024-05-16 | 2024-06-04 | D03 |  |  | 2025-03-01
802.15.6 | Completed | done | done | Std | Nov 2016 | done | done | Y | Passed | 2016-11-23 |  |  | Passed | 2017-09-07 | Jul 2019 | Jul 2019
802.15.6ma | Negative LOA for .6
802.15.7-2018 | replied to comments in 60 day |  | 2022-11-18 | Std | 2024-05-01 | done | 2022-11-18 | Y | Passed | 2024-07-24 | Nov 2024 |  | Waiting | - | - | -
802.15.7a-2024 | Draft needs to be sent | 2024-05-16 | 2024-06-04 | D7
802.15.9-2021 | replied to comments in FDIS |  | 7-Jun-2022 | Std | Jan 2023 | done | 7-Jun-2022 | Y | Passed | 2023-11-12 | Jan 2024 | Feb 2024 | Closes | 2024-11-08 | Nov 2024
802.15.13 | Negative LOA | 2024-05-16 | 2024-06-04 | Std | Sept 2024 |  |  |  |  | - | - | - |  | - | - | -
[5 empty] | - |  |  |  |  | - | - | - |  | - | - | -
[5 empty] | - |  |  |  |  | - | - | - |  | - | - | -
[5 empty] | - |  |  |  |  | - | - | - |  | - | - | -
[5 empty] | - |  |  |  |  | - | - | - |  | - | - | -
[5 empty] | - |  |  |  |  | - | - | - |  | - | - | -

## key
Color coding | 802.15 action | IEEE SA action
Std |  | Name of the Standard
Status |  | Current Status (free form) | Completed | in Progress | Status | No Need - could be due to roll up.
Information Motion |  | example in motions | sending the draft or STD for information to ISO (prepare them that it will be coming for adoption)
WG |  | date
LMSC |  | date
Draft/STD liaised |  | What was liaised | STD | waiting for next step
date
Adoption Motion |  | example in motions | sending the STD for adoption
WG |  | date
LMSC |  | date
STD |  | when STD sent to ISO | Y, ? Or date
sent |  | for adoption
Last draft liaised |  | What was liaised | STD | waiting for next step
date
60-day |  | Status | Passed | waiting for next step
pre-ballot |  | date
Comments Motion |  | Motions for sending comments back.
WG |  | date
LMSC |  | date
5-month |  | Status | STD | waiting for next step
FDIS ballot |  | date
Comments Motion |  | Motions for sending comments back.
WG |  | date
LMSC |  | date
Comments

## schedule
What/When | Do | who | spreadsheet | notes
STD is at least in SA ballot | Add STD to spreadsheet | 802.15 | Update
| Create a WG motion for Information (motion tab) | 802.15
| Create an LMSC motion for Information (motion tab) | 802.15
| submit WG and LMSC motions | 802.15 | Update
IF draft | WG chair sends draft to ISO with cover letter | 802.15 |  | if in SA ballot - submit the name of the draft = and 802.15 sends the draft
if STD | IEEE staff sends STD to ISO | IEEE Staff | Update | last draft liaised
| Create WG motion for Adoption (motion tab) | 802.15
| Create LMSC motion for Adoption (motion tab) | 802.15
30 days after sent to ISO | submit WG and LMSC adoption motions | 802.15 | Update
Liaison statement & STD sent to ISO |  | IEEE Staff | Update | last draft liaised
60 day from pre-ballot | check for updates | IEEE Staff | Update when ready
5 month FDIS ballot | check for updates | IEEE Staff | Update when ready