## Opening
Calendar: | [7 empty] | TG4ab Interim Meeting, Sept through November, 2024
Sun | Mon | Tue | Wed | Thr | Fri | Sat |  | Virtual (WebEx)
|  |  | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 |  | Commence on 24-Sept-2024
2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 |  | Weekly Tuesdays 06:00 PT (1 hour)
2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 |  | Thursdays 15:00 PT (1 hour)
2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 |  | September 24 through November 7th.
2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19
2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26
2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 |  | Meeting Slides:
2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09
2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | Plenary Session
[7 empty] | Notices: | The meeting will commence April 26, and adjourn on May 7th.
Prior to the opening and each time slot please review the meeting requirements:
https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Standards Board Patent Committee (PatCom) home page:
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Working Group Copyright Materials
https://standards.ieee.org/ipr/copyright-materials.html
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/ieee-sa-copyright-policy-2019.pdf
Formulas:
Thr = [Wed]+1
Fri = [Thr]+1
Sat = [Fri]+1

## Summary
Call Date | Proposed Main Theme(s) | Hour | Lead | Notes | Start (PDT)
2024-09-24 | Comment Resolution | 1 |  |  | 6:00
2024-09-26 | Comment Resolution | 1 |  |  | 15:00
2024-10-01 | Comment Resolution | 1 |  |  | 6:00
2024-10-03 | Comment Resolution | 1 |  |  | 15:00
2024-10-08 | Comment Resolution | 1 |  |  | 6:00
2024-10-10 | Comment Resolution | 1 |  |  | 15:00
2024-10-15 | Comment Resolution | 1 |  |  | 6:00
2024-10-17 | Comment Resolution | 1 |  |  | 15:00
2024-10-22 | Comment Resolution | 1 |  |  | 6:00
2024-10-24 | Comment Resolution | 1 |  |  | 15:00
2024-10-29 | Comment Resolution | 1 |  |  | 6:00
2024-10-31 | Comment Resolution | 1 |  |  | 15:00
2024-11-05 | Comment Resolution | 1 |  |  | 6:00
2024-11-07 | Comment Resolution | 1 |  |  | 15:00
Formulas:
Call Date = [Call Date, row above]+2

## Agenda Details
|  | TG4ab Interim Meeting, Sept through November, 2024 | UTC offset: | -7
Agenda Details
Call Date | Item | Description | Duration | Start PDT | UTC | Presenter/Lead |  | Document link
2024-09-24 |  | 24-Sep Comment Resolution |  | 6:00 | 13:00
| 1 | Opening and policy reminders | 10 | 6:00 |  | Chair
| 2 | Status update | 10 | 6:10 |  | Chaplin, Verso | 15-24-0371 | https://mentor.ieee.org/802.15/dcn/24/15-24-0371-14-04ab-consolidated-comments-draft-1-0.xlsm
| 3 | Proposed Resolution for Bitmap-based Slot Scheduling | 20 | 6:20 |  | Kangjin | 15-24-0504 | https://mentor.ieee.org/802.15/dcn/24/15-24-0504-01-04ab-proposed-resolution-for-bitmap-based-slot-scheduling.docx
| 4 | Review and Confirm: Hyper-block comments | 2 | 6:40 |  | Rojan | 15-24-0477 | https://mentor.ieee.org/802.15/dcn/24/15-24-0477-01-04ab-proposed-resolution-for-hyper-block-comments.docx
| 5 | Review and Confirm: common message fields | 3 | 6:42 |  | Rojan | 15-24-0505 | https://mentor.ieee.org/802.15/dcn/24/15-24-0505-01-04ab-proposed-resolutions-for-common-message-fields.docx
| 6 | Hyper-block comments, part 2 | 5 | 6:45 |  | Rojan | 15-24-0550 | https://mentor.ieee.org/802.15/dcn/24/15-24-0550-00-04ab-proposed-resolution-for-hyper-block-comments-part2.docx
| 7 | Multiple Comment Resolutions in Doc 514 (part 1) | 10 | 6:50 |  | Alex | 15-24-0514 | https://mentor.ieee.org/802.15/dcn/24/15-24-0514-00-04ab-lb207-d01-comment-resolution-revise-cids-74-76-77-78-243-244-514-546-653-654-661-662-663-929-1000-1005-1006-1007-1009-1010-1011-1135-1136-1213-1374-1375-1395.docx
|  | Recess |  | 7:00 |  | Chair
2024-09-26 |  | 26-Sep Comment Resolution |  | 15:00 | 22:00
| 8 | Opening and reminders | 5 | 15:00 |  | Chair
| 9 | Multiple Comment Resolutions in Doc 514 (part 2) | 25 | 15:05 |  | Alex | 15-24-0514 | https://mentor.ieee.org/802.15/dcn/24/15-24-0514-00-04ab-lb207-d01-comment-resolution-revise-cids-74-76-77-78-243-244-514-546-653-654-661-662-663-929-1000-1005-1006-1007-1009-1010-1011-1135-1136-1213-1374-1375-1395.docx
| 10 | Contnue discussion on Doc 0452 (r2) | 15 | 15:30 |  | Xiliang | 15-24-0452 | https://mentor.ieee.org/802.15/dcn/24/15-24-0452-02-04ab-proposed-resolutions-for-cid-93-174-etc.docx
| 11 | Packet format configuration | 15 | 15:45 |  | Verso | 15-24-0552 | https://mentor.ieee.org/802.15/dcn/24/15-24-0552-00-04ab-uwb-packet-format-configuration.docx
| 12 | Recess |  | 16:00 |  | Chair
2024-10-01 |  | 01-Oct Comment Resolution |  | 6:00 | 13:00
| 13 | Opening and reminders | 5 | 6:00 |  | Chair
| 14 | Follow-up on 0514 | 15 | 6:05 |  | Alex
| 15 | Comment Resolution | 35 | 6:20 |  | Alex | 15-24-0533 | https://mentor.ieee.org/802.15/dcn/24/15-24-0553-00-04ab-uwb-packet-format-configuration.docx
| 16 | Review | 5 | 6:55 |  | Chaplin
| 17 | Recess | 0 | 7:00 |  | Chair
2024-10-03 |  | 03-Oct Comment Resolution |  | 15:00 | 22:00
| 18 | Opening and reminders | 5 | 15:00 |  | Chair
| 19 | Comment Resolution | 25 | 15:05 |  | TBD
| 20 | Comment Resolution | 25 | 15:30 |  | TBD
| 21 | Review | 5 | 15:55 |  | Chaplin
| 22 | Recess | 0 | 16:00 |  | Chair
23
2024-10-08 |  | 08-Oct Comment Resolution |  | 6:00 | 13:00
| 24 | Opening and reminders | 5 | 6:00 |  | Chair
| 25 | Status on pending resolution documents | 25 | 6:05 |  | Chaplin
| 26 | Continue discussion on packet format comments | 25 | 6:30 |  | Alex
| 27 | Status review | 5 | 6:55 |  | Chair
| 28 | Recess |  | 7:00 |  | Chair
2024-10-10 |  | 10-Oct Comment Resolution
| 28 | Opening and reminders | 5 | 15:00 | 22:00 | Chair
| 29 | Comments 1381 et al | 20 | 15:05 |  | Xiliang | 15-24- 0490 | https://mentor.ieee.org/802.15/dcn/24/15-24-0490-00-04ab-proposed-resolutions-for-cid-279-885-etc.docx
| 30 | Comment 187 (tentative) | 30 | 15:25 |  | Wenzheng | 15-24-0470 | https://mentor.ieee.org/802.15/dcn/24/15-24-0470-00-04ab-proposed-resolution-for-cid-187.docx
| 31 | Editor Updates, Comment Status | 5 | 15:55 |  | Chaplin, Verso
| 32 | Recess | 0 | 16:00 |  | Chair
2024-10-15 |  | 15-Oct Comment Resolution |  | 6:00 | 13:00
| 33 | Opening and reminders | 4 | 6:00 |  | Chair
| 34 | Review of pending acceptance (doc 0490) | 1 | 6:04 |  | Xiliang | 15-24-0490 | https://mentor.ieee.org/802.15/dcn/24/15-24-0490-01-04ab-proposed-resolutions-for-cid-279-885-etc.docx
| 35 | UWB Packet Format Primitive (discussion) | 20 | 6:05 |  | Verso
| 36 | Non-interleaved MMS comments | 20 | 6:25 |  | Riku | 15-24-0532 | https://mentor.ieee.org/802.15/dcn/24/15-24-0532-01-04ab-non-interleaved-mms-comment-resolution.pptx
| 37 | HCS generation for Dynamic PHR | 15 | 6:45 |  | Vinod | 15-24-0558 | https://mentor.ieee.org/802.15/dcn/24/15-24-0558-01-04ab-hcs-generation-for-dynamic-phr.pptx
| 38 | Recess | 0 | 7:00 |  | Chair
2024-10-17 |  | 17-Oct Comment Resolution |  | 15:00 | 22:00
| 39 | Opening and reminders | 5 | 15:00 |  | Chair
| 40 | Proposed resolution for Discovery | 20 | 15:05 |  | Kangjin | 15-24-0411 | https://mentor.ieee.org/802.15/dcn/24/15-24-0411-02-04ab-proposed-resolution-for-discovery.docx
| 41 | HCS generation for Dynamic PHR | 20 | 15:25 |  | Vinod | 15-24-0558 | https://mentor.ieee.org/802.15/dcn/24/15-24-0558-01-04ab-hcs-generation-for-dynamic-phr.pptx
| 42 | PoC Status | 15 | 15:45 |  | Chaplin | 15-24-0371 | https://mentor.ieee.org/802.15/dcn/24/15-24-0371-20-04ab-consolidated-comments-draft-1-0.xlsm
| 43 | Recess |  | 16:00 |  | Chair
2024-10-22 |  | 22-Oct Comment Resolution |  | 6:00 | 13:00
| 44 | Opening and reminders | 5 | 6:00 |  | Chair
| 45 | CIDs 1000-929-1395-514-546 | 20 | 6:05 |  | Panpan | 15-24-0562 | https://mentor.ieee.org/802.15/dcn/24/15-24-0562-00-04ab-draft-1-0-comment-resolution-cids-1000-929-1395-514-546.docx
| 46 | Comment Resolution | 20 | 6:25 |  | TBD
| 47 | Review | 10 | 6:45 |  | TBD
| 48 | Review | 5 | 6:55 |  | Chaplin
| 49 | Recess |  | 7:00 |  | Chair
2024-10-24 |  | 24-Oct Comment Resolution |  | 15:00 | 22:00
| 50 | Opening and reminders | 5 | 15:00 |  | Chair
| 51 | PoC Status reports | 25 | 15:05 |  | Chaplin
| 52 | Comment Resolution | 25 | 15:30 |  | TBD
| 53 | Review of November Session requests | 5 | 15:55 |  | Chaplin
| 54 | Recess |  | 16:00 |  | Chair
2024-10-29 |  | 29-Oct Comment Resolution |  | 6:00 | 13:00
| 55 | Opening and reminders | 5 | 6:00 |  | Chair
| 56 | TBD Comment resolution | 25 | 6:05 |  | TBD
| 57 | TBD Comment resolution | 25 | 6:30 |  | TBD
| 58 | Review | 5 | 6:55 |  | Chaplin
| 59 | Recess | 0 | 7:00 |  | Chair
2024-10-31 |  | 31-Oct Comment Resolution |  | 15:00 | 22:00
| 1 | Opening and reminders | 5 | 15:00 |  | Chair
| 2 | TBD Comment resolution | 20 | 15:05 |  | TBD
| 3 | TBD Comment resolution | 20 | 15:20 |  | TBD
| 4 | TBD Comment resolution | 10 | 15:40 |  | TBD
| 5 | Recess | 0 | 15:50 |  | Chair
2024-11-05 |  | 05-Nov Comment Resolution |  | 6:00 | 13:05 | Chair
| 6 | Opening and reminders | 5 | 6:00 |  | Chair
| 7 | Comment #856 resolution and related | 10 | 6:05 |  | Larry | 15-24-0563 | https://mentor.ieee.org/802.15/dcn/24/15-24-0563-00-04ab-draft-1-0-proposed-le-phy-comments-resolution-cid-856.docx
| 8 | Comment #187 update and review | 10 | 6:15 |  | Wenzheng | 15-24-0470 | https://mentor.ieee.org/802.15/dcn/24/15-24-0470-01-04ab-proposed-resolution-for-cid-187.docx
| 9 | Comment resolution - 31, 40, 137, 957, 1400, 958, 671, 963 | 20 | 6:25 |  | Riku | 15-24-0576 | https://mentor.ieee.org/802.15/dcn/24/15-24-0576-00-04ab-comment-resolution-31-40-137-957-1400-958-671-963.docx
| 10 | Editor Updates, Comment Status, Meeting planning | 10 | 6:45 |  | Chaplin, Verso
| 11 | draft 1.0 comment resolution cids 965-1421-1422-1278 | 0 | 6:55 |  | Panpan | 15-24-0578 | https://mentor.ieee.org/802.15/dcn/24/15-24-0578-00-04ab-draft-1-0-comment-resolution-cids-965-1421-1422-1278.docx
| 12 | Recess | 0 | 6:55 |  | Chair
2024-11-07 |  | 07-Nov Comment Resolution |  | 15:00 | 22:00
| 13 | Opening and reminders | 5 | 15:00 |  | Chair
| 14 | Proposed Resolution for MMS – Public part 2 | 20 | 15:05 |  | Hongwon | 15-24-0569 | https://mentor.ieee.org/802.15/dcn/24/15-24-0569-00-04ab-proposed-resolution-for-mms-public-part-2.docx
| 15 | Comment Resolution - Part 1 | 25 | 15:25 |  | Youngwan | 15-24-0577 | https://mentor.ieee.org/802.15/dcn/24/15-24-0577-00-04ab-comment-resolution-part-1.docx
| 16 | November Joint .11 Coex and .15.4ab | 10 | 15:50 |  | Chair
| 17 | Adjourn |  | 16:00 |  | Chair
Standby:
|  | Draft 1.0 comment resolution_frequency stitching | 15 |  |  | Panpan | 14-24-0579 | https://mentor.ieee.org/802.15/dcn/24/15-24-0579-00-04ab-draft-1-0-comment-resolution-frequency-stitching.pptx

## Time zone helper
PDT, BST and CEST
First hour | UTC | 13:00
Local Time | Time Zone | UTC Offset
Tuesday, October 15, 2024 at 6:00:00 am | PDT | UTC-7 hours
Tuesday, October 15, 2024 at 9:00:00 am | EDT | UTC-4 hours
Tuesday, October 15, 2024 at 2:00:00 pm | BST | UTC+1 hour
Tuesday, October 15, 2024 at 3:00:00 pm | CEST | UTC+2 hours
Tuesday, October 15, 2024 at 9:00:00 pm | CST | UTC+8 hours
Tuesday, October 15, 2024 at 10:00:00 pm | KST | UTC+9 hours
Second hour | UTC | 22:00
Local Time | Time Zone | UTC Offset
Thursday, October 17, 2024 at 3:00:00 pm | PDT | UTC-7 hours
Thursday, October 17, 2024 at 6:00:00 pm | EDT | UTC-4 hours
Thursday, October 17, 2024 at 11:00:00 pm | BST | UTC+1 hour
Friday, October 18, 2024 at 12:00:00 midnight | CEST | UTC+2 hours
Friday, October 18, 2024 at 6:00:00 am | CST | UTC+8 hours
Friday, October 18, 2024 at 7:00:00 am | KST | UTC+9 hours