## IEEE_Cover
February 2025 |  | 15-25-0100-00-006a | Instructions: Fill in month and year at B1 Update doc# in D1 Fill in TG project number in C7 Fill in date in C8. Fill in your name and address in C9:D11 Update TG project number in C15 For each LB Duplicate the LBxxx_template sheet Rename the copied sheet as LBxxx, where xxx is the letter ballot number (or LBxxx_Rogue for rogue comments). Do not use spaces in the sheet names.
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | CRG Comments Resolution for Letter Ballot LB210 of draft P802.15.6ma_D03
Date Submitted | 2025-02-14
Source
Re:
Abstract | CRG approved Comments Resolution for Letter Ballot LB210 of IEEE P802.15.6ma Draft D03
Purpose | This document is the comments resolution for 802.15 Letter Ballot LB210 of draft P802.15.6ma_D03, which is approved by CRG. This is prepareed for recirculation.
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## LBxxx_template
INSTRUCTIONS: Duplicate this template, and rename it to match the LBxxx where xxx is the letter ballot number. Copy all comments from submitted comment sheets to this sheet by using copy and Paste Special / Paste Text Only them starting from B3 cell. Then add “i-1”, “r1-1”, “r2-1” etc (initial, recirculation1, recirculation2 etc) to the A2 column and drag lover right corner to cover all comments, so each comment gets comment id assigned. Before posting this to the mentor delete column D. Other1, other2, other3 etc can be used for keeping track of your own things, like “Comment group”, “Person assigned to”, “Status in document”. If the Dispotion status is Revised or Rejected you need to have Dispotion detail, and if it is Accepted you can’t have Dispotion status (sheet will show red error in those cases). Remove this line 1 after you have read the instructions as it is no longer needed, and will just unnecessarely consume screen estate. After deleting line 1, freeze first line and column.
Comment ID | Name | Affiliation | Email (remove this column before posting to mentor) | Page | Sub-clause | Line # | Comment | Proposed Change | Category | Must Be Satisfied? | Disposition Status | Disposition Detail | Other1 | Other2 | Other3
i-1

## LB210
Comment ID | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Category | Must Be Satisfied? | Disposition Status | Disposition Detail | Other1 | Other2 | Other3
i-1 | Stephan Sand | German Aerospace Center (DLR) | 1 | 0 | 26 | p. xi. The annexes A to G are not listed in the TOC | Please add the annexes A to G to the TOC | Editorial |  | Accepted |  | Done.
i-2 | Seong-Soon Joo | KPST | 1 | introduction | 14 | p. ix. In the sentence, "The standard specifies sensing and feedback control loop delay", how to specify the feedback control loop delay is not well understood. It needs to be revised for providing more clear scope of the specification. |  | General |  | Revised | The standard specifies the coexistence of multiple piconets, including inter-body area network (inter-BAN) interference and inter-piconets interference; simple and reliable MAC protocol corresponding to required quality of service (QoS) or priority levels; and sensing and feedback control loop delay. | Done.
i-3 | Seong-Soon Joo | KPST | 12 | 1.1 | 6 | The sentence, "adds support for vehicle body area networks (VBAN), a coordinator in a vehicle with devices around the cabin room, operating under strict compliance to standards and limits for electromagnetic compatibility (EMC) and electromagnetic interference (EMI)", is not well understood. It needs to be revised for introducing the VBAN as an enhancement. . |  | General |  | Rejected | 1.1 Scope and 1.2 Purpose should be the same as PAR and CSD | Done.
i-4 | Seong-Soon Joo | KPST | 12 | 1.1 | 9 | The sentence, "Areas of enhancement: multiple piconets coexisting, which includes inter-BAN interference and inter-piconets interference; simpler and more reliable MAC protocol; sensing and feedback control loop delay.", is not complete. 1.1 Scope subclause needs to be revised. |  | General |  | Rejected | 1.1 Scope and 1.2 Purpose should be the same as PAR and CSD | Done.
i-5 | Seong-Soon Joo | KPST | 12 | 1.2 | 27 | The sentence, "Some usecase of vehicle BAN(VBAN) requriing high QoS with enhanced dependability are a harness of sensing and controlling of vehicles under a dense of coexisting piconets.", is not well understood. It needs to be revised. |  | General |  | Rejected | 1.1 Scope and 1.2 Purpose should be the same as PAR and CSD | Done.
i-6 | Seong-Soon Joo | KPST | 14 | 3.1 | 5 | "coordinatorcoordinator" | Chnage to "a coordinator" | Editorial |  | Accepted |  | Done.
i-7 | Seong-Soon Joo | KPST | 14 | 3.1 | 14 | The term, beacon access phase (BAP), is not appeared in the draft. | Delete the definition of beacon access phase (BAP) | Technical |  | Accepted |  | Done.
i-8 | Seong-Soon Joo | KPST | 19 | 3.2 | 7 | The term, BAP, is not appeared in the draft. | Delete the acronym of beacon access phase | Technical |  | Accepted |  | Done.
i-9 | Stephan Sand | German Aerospace Center (DLR) | 20 | 3.2 | 9 | There is an additional identation after HARQ, HBAN and VBAN. Also VBAN should be listed at the end of the acronym list | Please remove the additional identation and lsit VBAN at the end of the acronym list | Editorial |  | Accepted |  | Done.
i-10 | Huan-Bang Li | NICT | 23 | 4.2 | 11 | The meaning of 'There is to be' is confusing. For mandatory features, it should be written as 'There shall be'. For optional features, it should be written as ' There may be'. | modify the sentence | Technical |  | Revised | There is to be' has been replaced with 'There shall be'. | Done.
i-11 | Seong-Soon Joo | KPST | 23 | 4.2 | Figure 1 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "H1, H2, H, hub" in the Figure 1 into "C1, C2, C, coordinator" respectively. | Technical |  | Accepted |  | Done.
i-12 | Seong-Soon Joo | KPST | 23 | 4.2 | 21 | C2C communication and C2C ranging are the optional features for the dependable BAN. It needs to describe that. | Change paragraph as follows: "As dependable BAN optional mechanisms for coexistence and interference mitigating between adjacent or overlapping BANs, Coordinator-to-Coordinator (C2C) communication and C2C ranging are provided. To identify if communication ranges of multiple BANs are overlapped or not, each coordinator keeps broadcasting beacons periodically every superframe to range distance with neighboring BANs." | Technical |  | Accepted |  | Done.
i-13 | Huan-Bang Li | NICT | 24 | 4.2 | 7 | There is extra space in the word 'Communic ation' | delete the space | Editorial |  | Accepted |  | Done.
i-14 | Huan-Bang Li | NICT | 24 | 4.2 | 11 | There is an unnecessary line in the caption of Fig. 2. | delete the line | Editorial |  | Accepted |  | Done.
i-15 | Seong-Soon Joo | KPST | 24 | 4.3 | Figure 3 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Hub Management Entity, HME" in the Figure 3 into "CoordinatorHub Management Entity, CME" respectively. | Technical |  | Accepted |  | Done.
i-16 | Huan-Bang Li | NICT | 25 | 4.4 | 17 | The sentence start from 'the coordinator needs to communicate' describe a mandatory feature and should be described using 'shall'. | change the sentence start from 'the coordinator shall communicate' | Technical |  | Accepted |  | Done.
i-17 | Stephan Sand | German Aerospace Center (DLR) | 29 | 4.7. | 11 | Acronym HBC is only used here. | Please replace HBC with human body communications (HBC) | Editorial |  | Accepted |  | Done.
i-18 | Huan-Bang Li | NICT | 29 | 4.7 | 11 | Narrow band PHYs are also included in the legacy standard. Are they provided with backward compatibility in this amendament? | add corresponding descriptions | General |  | Revised | Additional description in 4.7 as follows; 'This revision supports some backward compatibility with P802.15.6-2012 as much as possible but not all of them in PHY and MAC for enhanced dependability. Particularly, this revision focuses on only UWB in PHY and only time structure mode in MAC as mentioned in 1.1. Particularly, this revision does not support deprecated FM-UWB PHY and human body communications (HBC).' | Done.
i-19 | Huan-Bang Li | NICT | 29 | 4.7 | 16 | What is the meaning of 'traffic priority (QoS)'? Are 'traffic priority' and 'QoS' equal? Are they related each other? | add corresponding descriptions | General |  | Revised | Paragraph in 4.7 has been revised as; 'The combination of technologies for the revised UWB PHY and MAC depends on required Quality of Services (QoS) levels or priority orders of packets and the coexistence scenario with other BANs and wireless networks operating in the same spectrum. Hence, a classification of coexistence classes and QoS levels are defined. ' | Done.
i-20 | Huan-Bang Li | NICT | 30 | 4.7.1 | 5 | What does '15.' stand for in the second column of Table 1? Does it represent all 802.15 standards? | modify it | General |  | Revised | original text '15.'has been replaced with '15.6ma' | Done.
i-21 | Huan-Bang Li | NICT | 31 | 4.7.1 | 14 | Replace 'depend of' by 'depends on'. | make changes | Editorial |  | Revised | depend of' has been replaced with 'depends on'. | Done.
i-22 | Huan-Bang Li | NICT | 32 | 4.7.2 | 8 | The contents of this paragraph don't match with the current subclause. It is unsusal to discribe Figure 6 here. | modify acoordingly | Technical |  | Revised | This operation will be described in 6.5' Described in 6.5 | Done.
i-23 | Huan-Bang Li | NICT | 32 | 4.7.2 | 11 | This paragraph repeats the contents of the first paragraph of this subclause. | unify the contents | Technical |  | Revised | Theparagraph has been revised as; 'The standard supports BANs operating with high reliability (coexistence class 0) and coexisting in dense environments with intra-system interference and inter-system interference (coexistence class 1 to 7), where intra-system interference is mutual interference within the same standard systems while inter-system interference is interference among different standard systems . Figure 7 shows the state transition between several classes of coexistence environments defined in Table 1.' | Done.
i-24 | Seong-Soon Joo | KPST | 32 | 4.7.2 | 8 | The sentence "In Figure 6, the state transition probabilities are approximated in consecutive superframes" is not well understood. It needs to revise the sentence. Figure 6 is not related to state transition. | Change "In Figure 6" into "In Figure 7" | Technical |  | Accepted |  | Done.
i-25 | Seong-Soon Joo | KPST | 32 | 4.7.2 | 9 | The senrence "duration of the CAP and CFP are determined by the type of QoS associated with every superframe, or group frame and available resources to avoid congestion" is not well understood. It needs to revise the sentence. CFP is appeared without the term defintion. In this draft, CAP stands for contention access phase. If it wants to use CAP as the acronym of "contention access period", it needs to change the acronym of "contention access phase". |  | Technical |  | Revised | P14 L.11-13 contention access period phase (CAP): A time span set aside by a coordinator and announced via a preceding non-beacon frame for contention access to the medium by the nodes in the body area network (BAN) of the coordinator. And adding contention free period (CFP): A time span set aside by a coordinator and announced via a preceding non-beacon frame for contention free to the medium by BAN coordinator's preserving for the nodes.. Attention: CAP and CFP were contention access phase and contention free phase in std.IEEE802.15.6-2012. | Done.
i-26 | Seong-Soon Joo | KPST | 32 | 4.7.2 | 11,12 | The terms, " intra-interference and inter-interference" are not described before using the terms. |  | Technical |  | Revised | The paragraph has been modified as follows. The standard supports BANs operating with high reliability (coexistence class 0) and coexisting in dense environments with intra-system interference and inter-system interference (coexistence class 1 to 7), where intra-system interference is mutual interference within the same standard systems while inter-system interference is interference among different standard systems . Figure 7 shows the state transition between several classes of coexistence environments defined in Table 1. | Done.
i-27 | Huan-Bang Li | NICT | 36 | 5.3.3.1.1 | 4 | Multicast needs to be addressed in Table 3 but it is not addressed. | add description for multicast | Technical |  | Revised | Table 3 has been updated with additional description as; The Destination Address field is set to all ones for transmit not to specified receivers(broadcast ). The recipient MAC entity may ignore parsing the Destination Address field. | Done.
i-28 | Huan-Bang Li | NICT | 38 | 5.3.3.1.5 | 3 | This paragraph describes two different cases represented by 7 and 7.3 respectively. However, 7.3 is part of 7. | resolve the conflict. | Technical |  | Revised | described in 7' has been replased with 'described in 7.1' | Done.
i-29 | Huan-Bang Li | NICT | 38 | 5.3.3.1.7 | 11 | The first two rows are duplicated. | delete one | General |  | Accepted |  | Done.
i-30 | Huan-Bang Li | NICT | 39 | 5.3.3.1.9 | 7 | Add a period at the end of the paragraph. | add a period | Editorial |  | Accepted |  | Done.
i-31 | Huan-Bang Li | NICT | 41 | 5.3.3.3.2 | 15 | MMPDU is not defined in the document. I guess that it is a TYPO of MPDU. | modify accordingly | Editorial |  | Accepted |  | Done.
i-32 | Huan-Bang Li | NICT | 46 | 5.3.4 | 5 | clearing operation is neither defined nor described in the document. | add definition or description | Technical |  | Revised | The paragraph revised as; 'Control frames intend to perform clearing operations for contention access in which non accepted packets due to contentions are removed . channel acquisition, CCA maintenance functions, and positive acknowledgment of received data. Control and Data frames work together to deliver data reliably.' | Done.
i-33 | Huan-Bang Li | NICT | 47 | 5.4.1.2 | 6 | In Table 15, description of bit b0 includes values of b1. | modify the description | Technical |  | Accepted |  | Done.
i-34 | Seong-Soon Joo | KPST | 49 | 5.5.3 | 22 | QoS Control field is not defined in 9.2.1. |  | Technical |  | Revised | Cross reference has been modified as; 'The QoS Control field is defined in 5.3.3.4. The presence of the QoS Control field is indicated in the Frame Control field in 5.3.3.1.' | Done.
i-35 | Seong-Soon Joo | KPST | 49 | 5.5.3 | 23 | The presence of the QoS Control field is not indicated in the Frame Control field4 in 9.2.4. |  | Technical |  | Revised | Cross reference has been modified as; 'The QoS Control field is defined in 5.3.3.4. The presence of the QoS Control field is indicated in the Frame Control field in 5.3.3.1.' | Done.
i-36 | Huan-Bang Li | NICT | 52 | 5.6.2.2 | 8 | Spectrum Measurements and Link Measurements measures' should be written in plural form. | replace 'measures' by 'measure' | Editorial |  | Accepted |  | Done.
i-37 | Huan-Bang Li | NICT | 54 | 5.6.4 | 3 | In Table 25, column of 'bits' are empty. | add corresponding bits information | Technical |  | Revised | 'Bits' column has been removed. | Done.
i-38 | Huan-Bang Li | NICT | 56 | 5.6.4 | 3 | In Table 29, field name and description for b2-b7 and b8-b15 are not correctly formated. | modify accordingly | Technical |  | Revised | Field name has been added; "Supported channel number" | Done.
i-39 | Huan-Bang Li | NICT | 59 | 5.6.5.2 | 7 | In Table 35, most fields of description colume are empty | add corresponding descriptions | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-40 | Seong-Soon Joo | KPST | 91 | 5.8.6 | Figure 35 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Former Hub Address IE" in the Figure 35 into "Former Coordinator Address IE" respectively. | Technical |  | Accepted |  | Done.
i-41 | Seong-Soon Joo | KPST | 93 | 5.8.6.6 | Figure 37 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub ACK Data, Hub ACK" in the Figure 37 into "Coordinator ACK Data, Coordinator ACK" respectively. | Technical |  | Accepted |  | Done.
i-42 | Seong-Soon Joo | KPST | 100 | 5.8.8 | Figure 41 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "New Hub Adress, ..." in the Figure 41 into "New Coordinator Adress, .." respectively. | Technical |  | Accepted |  | Done.
i-43 | Seong-Soon Joo | KPST | 111 | 5.11.1 | Figure 50 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Hub Clock, Relayed Hub" in the Figure 50 into " Coordinator Hub Clock, Relayed Coordinator" respectively. | Technical |  | Accepted |  | Done.
i-44 | Yasuharu Amezawa | Mobile Techno.Corp. | 127 | 6 | 15 | It is difficult to understand because two MACs are written on the same hierarchy. | For example, 6.2 HRP MAC 6.2.1 General 6.2.2 Superframe structure 6.3 MAC functions legacy 6.3.1 General | Editorial |  | Revised | Clauses and subclauses have been modified as; 6. MAC functions 6.1 MAC functions and IEEE Std 802.15.6-2012 6.2 HRP MAC 6.2.1 General 6.2.2 Control Channel and Data Channel 6.2.3 Superframe structure 6.3 Channel access … 6.4 MAC Services … 6.5 MAC functions legacy 6.5.1 General ... | Done.
i-45 | Yasuharu Amezawa | Mobile Techno.Corp. | 127 | 6.1 | 17 | The HRP UWB PHY is described in clause 9.1, not in clause 9.2. | 9.1 instead of 9.2 | Editorial |  | Accepted |  | Done.
i-46 | Yasuharu Amezawa | Mobile Techno.Corp. | 127 | 6.1 | 18 | The MAC functional description for the PHYs of IEEE Std 802.15.6-2012 is described in clause 6.7, not in clause 6.3. | 6.3 instead of 6.7 | Editorial |  | Accepted |  | Done.
i-47 | Seong-Soon Joo | KPST | 127 | 5.12.14 | Figure 66 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Former Hub Address" in the Figure 66 into "Former Coordinator Address" respectively. | Technical |  | Accepted |  | Done.
i-48 | Seong-Soon Joo | KPST | 127 | 6.1 | 17 | HRP UWB PHY described in clause 9.1, not clause 9.2 | Change "clause 9.2" into "clause 9.1" | Technical |  | Accepted |  | Done.
i-49 | Seong-Soon Joo | KPST | 128 | 6.2 | 1, 5 | The terms, "coordination channel" and "data channel" are used without defining the terms. These two terms are not used in the draft after introducing. |  | Technical |  | Revised | "coordination channel" has been replaced with "control channel" | Done.
i-50 | Seong-Soon Joo | KPST | 128 | 6.3 | 12 | The terms, "time slot" and "period" are used without defining the terms. |  | Technical |  | Revised | desriptions have been added as; 'specific time slots and periods such as CAP and CFP to each BAN, which helps to prevent frame collisions,' | Done.
i-51 | Seong-Soon Joo | KPST | 128 | 6.3 |  | The clause 6.3 is not suitable for the standard documentation. It needs to be rewritten for providing formal overview of HRP MAC. |  | General |  | Revised | Clauses and subclauses have been modified as; 6. MAC functions 6.1 MAC functions and IEEE Std 802.15.6-2012 6.2 HRP MAC 6.2.1 General 6.2.2 Control Channel and Data Channel 6.2.3 Superframe structure 6.3 Channel access … 6.4 MAC Services … 6.5 MAC functions legacy 6.5.1 General ... | Done.
i-52 | Seong-Soon Joo | KPST | 128 | 6.3 | 31 | HRP MAC operates only in beacon mode. The case that the value of macBeaconOrder = 15 will not occurred. |  | Technical |  | Revised | Descriptions have been added as; 'Beacon Request command from a coordinator of coexisting BAN which does not know that the value of macBeaconOrder has already been 14.' | Done.
i-53 | Seong-Soon Joo | KPST | 128 | 6.4 | 32 | Beacon Request command is not defined in the draft. |  | Technical |  | Revised | in 6.2.3, definition and description has been added as; ～～Beacon Request command from a coordinator of coexisting BAN which does not know that the value of macBeaconOrder has already been 14. The value of macSuperframeOrder shall be ignored if macBeaconOrder = 15. | Done.
i-54 | Yasuharu Amezawa | Mobile Techno.Corp. | 129 | 6.4 | 20 | Is it possible to send only one MAC frame in one slot? Can the same node send multiple MAC frames? | Please describe in detail | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-55 | Yasuharu Amezawa | Mobile Techno.Corp. | 129 | 6.4 | 23 | In which messages are the MAC superframe attributes listed in Table 70 set and reported? | Please describe in detail | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-56 | Seong-Soon Joo | KPST | 129 | 6.4 | 13 | GTS is not defined in the draft. |  | Technical |  | Revised | GTS' has been defined in 'Acronyms and abbreviations' | Done.
i-57 | Seong-Soon Joo | KPST | 129 | 6.4 | 8 | NAP is not defined in the draft. |  | Technical |  | Revised | NAP' has been replaced with ‘Inactive period’ | Done.
i-58 | Seong-Soon Joo | KPST | 129 | 6.4 | Figure 68 | Two slots are assigend to Beacon. It needs to describe the usage of time slots for a beacon. |  | Technical |  | Revised | Figure 68 shows an example of N slot times. It does not asign two slot times to a beacon. This has been explained as NOTE below figure 68. | Done.
i-59 | Yasuharu Amezawa | Mobile Techno.Corp. | 130 | 6.4.1 | 10 | What formula does the device use to know that transmission will be completed within the CAP ? | Please describe in detail. It should be described a way how to determine whether a packet will be sent in a next CAP or not. With math formula. In adition, it should be described a way how to determine lengths and a ratio of CFP and CAP with foumula. | Technical |  | Rejected | Timing description has been added in 6.3.1.1.4. | Done.
i-60 | Yasuharu Amezawa | Mobile Techno.Corp. | 130 | 6.4.3 | 16 | Does Frame in Inter-Frame spacing mean MAC Frame? If correct, is it the spacing on the Air of the MAC Frame? What is the relationship to slot boundaries? | Please describe in detail It is hard to understand inter-frame spacing is in MAC or Air in PHY. Please descibe inter-frame spacing in more detail. | Technical |  | Revised | Figure 70 has been modified. Inter-frame spacing is not MAC frame. Timing description is described on modified Figure 70. | Done.
i-61 | Yasuharu Amezawa | Mobile Techno.Corp. | 130 | 6.4.3 | 21 | PD is not defined. | Please define PD. | Editorial |  | Revised | packet data (PD) | Done.
i-62 | Seong-Soon Joo | KPST | 130 | 6.4.2 | 14 | GTS is not defined in the draft. |  | Technical |  | Revised | GTS' has been defined in 'Acronyms and abbreviations' | Done.
i-63 | Seong-Soon Joo | KPST | 130 | 6.4.1 | 4 | NAP is not defined in the draft. |  | Technical |  | Revised | NAP' has been replaced with ‘Inactive period’ | Done.
i-64 | Seong-Soon Joo | KPST | 130 | 6.4.1 | 3 | CAP is used as acronym of contention access phase and contention access period concurrently. |  | Technical |  | Revised | contantion access period | Done.
i-65 | Seong-Soon Joo | KPST | 130 | 6.4.3 | 24, 25 | PLDE-TXEND.confirm, PLDE-TXSTART.confirm, PLDE-RXSTART.indication, and PLDE-RXEND.indication are not defined in the draft. |  | Technical |  | Revised | Definition and description have been added in 6.3.2. | Done.
i-66 | Yasuharu Amezawa | Mobile Techno.Corp. | 131 | 6.4.3 | 24 | PLDE-TXEND.confirm, PLDE-TXSTART.confirm, PLDE-RXSTART.indication and PLDE-RXEND.indication are not defined. | Please define PLDE-TXEND.confirm, PLDE-TXSTART.confirm, PLDE-RXSTART.indication and PLDE-RXEND.indication. | Editorial |  | Revised | Definition and description have been added in 6.3.2. | Done.
i-67 | Yasuharu Amezawa | Mobile Techno.Corp. | 131 | 6.4.5 | 11 | p-EIED is not defined. | Please define p-EIED. | Editorial |  | Revised | IFSs descriptions have been modified in 6.3.1.1.3. p-EIED has been removed. | Done.
i-68 | Yasuharu Amezawa | Mobile Techno.Corp. | 131 | 6.4.6 | 22 | CS is not defined. | Please define CS. | Editorial |  | Revised | IFSs descriptions have been modified in 6.3.1.1.3. CS has been removed. | Done.
i-69 | Yasuharu Amezawa | Mobile Techno.Corp. | 131 | 6.4.6 | 23 | NAV is not defined. | Please define NAV. | Editorial |  | Revised | IFSs descriptions have been modified in 6.3.1.1.3. NAV has been removed. | Done.
i-70 | Seong-Soon Joo | KPST | 131 | 6.4.7 | 35, 36 | PLDE-TXEND.confirm, PLDE-TXSTART.confirm, PLDE-RXSTART.indication, and PLDE-RXEND.indication are not specified in clause 9.1.1. |  | Technical |  | Revised | Definition and description have been added in 6.3.2 Cross-reference has been corrected. | Done.
i-71 | Yasuharu Amezawa | Mobile Techno.Corp. | 132 | 6.4.7 | 70 | Where does IFS timing relationships define time? | Air? |  |  | Rejected | Unclear question. | Done.
i-72 | Yasuharu Amezawa | Mobile Techno.Corp. | 133 | 6.5.1.1 | 17 | MLME-SCAN is not defined. | Please define MLME-SCAN. | Editorial |  | Revised | Descriptions and definitions have been added in "6.3.4" | Done.
i-73 | Yasuharu Amezawa | Mobile Techno.Corp. | 133 | 6.5.1.1 | 19 | In which messages are phyCurrentChannel, phyCurrentPage, ScanDuration and phyCurrentCode set? | Please describe in detail | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-74 | Seong-Soon Joo | KPST | 133 | 6.5.1.1 | 26 | Beacon Request command is not defined in the draft. |  | Technical |  | Revised | The MAC does not handle beacon request command. | Done.
i-75 | Seong-Soon Joo | KPST | 133 | 6.5.1.1 | 21, 22 | MLME-SCAN.request and MLME-SCAN.confirm are not defined in the draft. |  | Technical |  | Revised | Descriptions and definitions have been added in "6.3.4" | Done.
i-76 | Seong-Soon Joo | KPST | 134 | 6.5.2 | 18 | Trigger Frame (TF) is not defined in the draft. |  | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-77 | Seong-Soon Joo | KPST | 134 | 6.5.2 | 17 | In the refence (see 6.11), clause 6.11 is related to the legacy MAC, not HRP MAC clause. |  | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-78 | Seong-Soon Joo | KPST | 134 | 6.5.2 | 24 | Request to Send (R2S) frame is not defined in the draft. |  | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-79 | Seong-Soon Joo | KPST | 134 | 6.5.2 | 36 | Trigger Frame Allocation (TFA) frame is not defined in the draft. |  | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-80 | Seong-Soon Joo | KPST | 135 | 6.5.2 | Figure 71 | TF, TFA, R2S are not defined in the draft. |  | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-81 | Seong-Soon Joo | KPST | 136 | 6.5.3 | 5 | The terms, "control channel" and "data channel" are used without defining the terms. |  | Technical |  | Revised | Descriptions and definitions have been added in "6.2.2" | Done.
i-82 | Yasuharu Amezawa | Mobile Techno.Corp. | 138 | 6.6 | 1 | This clause only describes the mode of a single data channel for all MAC frames. I would like to see a description of the processing of modes that use multiple channels. | Please describe in detail | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-83 | Huan-Bang Li | NICT | 138 | 6.6 | 2 | The first senstence is grammarly wrong. | Rewrite the sentence as 'A dependable BAN may coexist with other dependable BANs within interfering range.' | Editorial |  | Accepted |  | Done.
i-84 | Seong-Soon Joo | KPST | 138 | 6.6.1 | 17 | Acronyms GCP, GAP are not defined in clause 3.1 and not listed in clause 3.2. |  | Technical |  | Revised | Definitions and acronyms have been added in 3.1 and 3.2. | Done.
i-85 | Seong-Soon Joo | KPST | 138 | 6.6.1 | 29 | Acronyms GBI is not defined in clause 3.1 and not listed in clause 3.2. |  | Technical |  | Revised | Definitions and acronyms have been added in 3.1 and 3.2. | Done.
i-86 | Yasuharu Amezawa | Mobile Techno.Corp. | 138 | 6.6.1 | 35 | In Figure 73, Group superframe structure is just described only a mode of multiple BANs merging in time domain although in previous version, different BANs can share slots in the same superframe so that frequency efficiency can be improved. It is a big advantage of previous version. In current version, once a BAN belongs to Group BAN, system performance such as throughput and delay may significantly degradate. So, it is little advantage at all. |  | Technical |  | Revised | The advantage of control channel in different UWB band channel has been described in "6.2.2" | Done.
i-87 | Huan-Bang Li | NICT | 139 | 6.6.2.1 | 10 | the node cannot find ...' is based on assumption that a coexisting BAN or a group BAN does exist. That is not true. | replace 'cannot' by 'doesn't' | Technical |  | Accepted |  | Done.
i-88 | Huan-Bang Li | NICT | 139 | 6.6.2.1 | 10 | any of above' should be 'any of the above'. | make changes | Editorial |  | Accepted |  | Done.
i-89 | Yasuharu Amezawa | Mobile Techno.Corp. | 141 | 6.6.4.2 | 18 | I think there should be a procedure to inform the group BAN coordinator when the superframe structure of the BAN is changed. | Submit a change request at the GC in GCP. | Technical |  | Revised | If there is any comment in this CID after recirculation, it will be reconsidered. | Done.
i-90 | Yasuharu Amezawa | Mobile Techno.Corp. | 146 | 6.6.74 | 1 | CWC is not defined. | Please define CWC. | Editorial |  | Revised | CWC' has been replaced with 'C2C' | Done.
i-91 | Seong-Soon Joo | KPST | 146 | 6.7 | 146 | Clause 6.7 is empty. |  | Technical |  | Revised | Clause and subclauses structure has been corrected as; 6.5 MAC functions legacy 6.5.1 General 6.5.2 Frame processing … | Done.
i-92 | Seong-Soon Joo | KPST | 153 | 6.9.9.2 | Figure 75 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 75 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-93 | Seong-Soon Joo | KPST | 153 | 6.9.9.3 | Figure 76 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 76 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-94 | Seong-Soon Joo | KPST | 155 | 6.9.9.4 | Figure 77 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 77 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-95 | Seong-Soon Joo | KPST | 159 | 6.11.2 | Figure 82 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub " in the Figure 82 into " Coordinator " respectively. | Technical |  | Accepted |  | Done.
i-96 | Seong-Soon Joo | KPST | 160 | 6.11.2 | Figure 83 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 83 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-97 | Seong-Soon Joo | KPST | 160 | 6.11.3 | Figure 84 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub " in the Figure 84 into " Coordinator " respectively. | Technical |  | Accepted |  | Done.
i-98 | Seong-Soon Joo | KPST | 168 | 6.13.1 | Figure 89 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 89 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-99 | Seong-Soon Joo | KPST | 171 | 6.13.1 | Figure 90 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 90 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-100 | Seong-Soon Joo | KPST | 174 | 6.13.2.2 | Figure 92 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 92 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-101 | Seong-Soon Joo | KPST | 177 | 6.14.2 | Figure 94 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 94 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-102 | Seong-Soon Joo | KPST | 177 | 6.14.2 | Figure 95 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 95 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-103 | Seong-Soon Joo | KPST | 186 | 6.16.1 | Figure 96 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 96 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-104 | Seong-Soon Joo | KPST | 187 | 6.16.2.1 | Figure 97 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 97 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-105 | Seong-Soon Joo | KPST | 188 | 6.16.2.2 | Figure 98 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 98 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-106 | Seong-Soon Joo | KPST | 189 | 6.16.3 | Figure 99 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change " Hub transmits" in the Figure 99 into " Coordinator transmits" respectively. | Technical |  | Accepted |  | Done.
i-107 | Seong-Soon Joo | KPST | 190 | 6.17 | Figure 100 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "hub, H " in the Figure 100 into "coordinator, C " respectively. | Technical |  | Accepted |  | Done.
i-108 | Seong-Soon Joo | KPST | 191 | 6.17.1 | Figure 102 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Hub, hub" in the Figure 102 into "Coordinator, coordinator" respectively. | Technical |  | Accepted |  | Done.
i-109 | Seong-Soon Joo | KPST | 197 | 6.17.3 | Figure 103 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Target hub" in the Figure 103 into "Target coordinator" respectively. | Technical |  | Accepted |  | Done.
i-110 | Seong-Soon Joo | KPST | 198 | 6.17.5 | Figure 104 | Hub is not defined in the draft. It is needed that the hub is changed into coordinator. | Change "Target hub, Hub" in the Figure 104 into "Target coordinator, Coordinator" respectively. | Technical |  | Accepted |  | Done.
i-111 | Stephan Sand | German Aerospace Center (DLR) | 340 | D.1 | 13 | Figure numbering in the annexes is incosistent. For example on P337L7 it is C.2, but on P341L2 it is 180 | Please us for all figures in the annex the same numbering convention, e.g. C.2. | Editorial |  | Accepted |  | Done.
i-112 | Stephan Sand | German Aerospace Center (DLR) | 348 | G.1 | 5 | Figure 189 is reference, but Figure 185 is shown below. | Please change the reference to Figure G.1 and the caption on P348L8 to G.1. | Editorial |  | Accepted |  | Done.
i-113 | Stephan Sand | German Aerospace Center (DLR) | 348 | G.1 | 11 | Figure 190 is reference, but Figure 186 is shown below. | Please change the reference to Figure G." and the caption on P349L2 to G.2. | Editorial |  | Accepted |  | Done.
i-114
i-115
i-116
i-117
i-118
i-119
i-120
i-121
i-122
i-123
i-124
i-125
i-126
i-127
i-128
i-129
i-130
i-131
i-132
i-133
i-134
i-135
i-136
i-137
i-138

## Statistics
|  | Category |  |  |  | Disposition status
Letter ballot | Total | Editorial | Technical | General | Unknown | Accepted | Revised | Rejected | Unresolved
LB210 | 113 | 25 | 78 | 9 | 1 | 51 | 57 | 5 | 0
Instructions:
In column B type in the sheet name containing letter ballot comments to get statistics from that sheet. Note, that spaces are not allowed in the sheet names.