## Opening
Calendar: | [7 empty] | TGab agenda August 2025 through Sept 2025
Sun | Mon | Tue | Wed | Thr | Fri | Sat |  | Virtual (WebEx)
Commence on August 12th until [done with comments ¦ Sept 9th] Weekly Tuesdays 06:00 PT (1.5 hours) Subsequent meetings will be cancelled if/when recirculation ballot begins
|  | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09
2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16
2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23
2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | Ballot Open? | To complete 15 day recirculation by opening of the September session, ballot must open by 30 August
2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06
2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13
2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | Interim Session
2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27
2025-09-28 | 2025-09-29 | 2025-09-30
[7 empty] | Notices: | The meeting will commence August 12th and continue until adjourned
Prior to the opening and each time slot please review the meeting requirements:
https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Standards Board Patent Committee (PatCom) home page:
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Working Group Copyright Materials
https://standards.ieee.org/ipr/copyright-materials.html
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/ieee-sa-copyright-policy-2019.pdf
Participation is conditioned on acceptance of and commitment to comply with all of the above
Formulas:
Wed = [Tue]+1
Thr = [Wed]+1

## Summary
Call Date | Proposed Main Theme(s) | Hour | Lead | Notes | Start (PDT)
2025-08-12 | Comment Resolution | 1.5 |  |  | 6:00
2025-08-19 | Comment Resolution | 1.5 |  |  | 6:00
2025-08-26 | Comment Resolution | 1.5 |  |  | 6:00
2025-08-28 | Special CRG prior to RB for Sept | 1.5 |  |  | 6:00 | To be deterimined on 12-Aug
2025-09-02 | Comment Resolution | 1.5 |  |  | 6:00
2025-09-09 | Comment Resolution | 1.5 |  |  | 6:00
Formulas:
Call Date = [Call Date, row above]+7

## Agenda Details
|  | TGab agenda August 2025 through Sept 2025 | UTC offset: | -7
Agenda Details
Call Date | Item | Description | Duration | Start PDT | UTC | Presenter/Lead |  | Document link | Notes
2025-08-12 |  | 12-Aug Comment Resolution |  | 6:00 | 13:00
| 1 | Opening and policy reminders | 10 | 6:00 |  | Chair
| 2 | Update: Proposed Resolution Sensing Comments | 30 | 6:20 |  | Pooria | 15-25-0339 | https://mentor.ieee.org/802.15/dcn/25/15-25-0339-00-04ab-proposed-comments-resolution-for-15-4ab-d2-0-sensing-comments.docx
| 3 | Comment Resoultion TBD | 30 | 6:50 |  | TBD
| 4 | Review of Comment Status | 10 | 6:10 |  | Chaplin
| 5 | Next steps: Call planning and Schedule | 10 | 7:20 |  | Chair
|  | Recess |  | 7:30
2025-08-19 |  | 19-Aug Comment Resolution |  | 6:00 | 13:00
| 6 | Opening and reminders | 10 | 6:00 |  | Chair
| 7 | Update: Proposed Resolution Sensing Comments | 5 | 6:10 |  | Pooria | 15-25-0339 | https://mentor.ieee.org/802.15/dcn/25/15-25-0339-02-04ab-proposed-comments-resolution-for-15-4ab-d2-0-sensing-comments.docx
| 8 | Proposed resolution for CID 159 | 5 | 6:15 |  | Mickael | 15-25-0411 | https://mentor.ieee.org/802.15/dcn/25/15-25-0411-00-04ab-proposed-resolution-for-cid-159.docx
| 9 | MMS ranging procedure with fixed reply time | 15 | 6:20 |  | Mickael | 15-25-0396 | https://mentor.ieee.org/802.15/dcn/25/15-25-0376-01-04ab-mms-ranging-procedure-with-fixed-reply-time.docx
| 10 | LB213 comment index 120 | 15 | 6:35 |  | Billy | 15-25-0407 | https://mentor.ieee.org/802.15/dcn/25/15-25-0407-00-04ab-lb213-comment-index-120.docx
| 11 | Draft 1.0 comment resolution_frequency stitching | 15 | 6:50 |  | Panpan | 15-25-0579 | https://mentor.ieee.org/802.15/dcn/24/15-24-0579-03-04ab-draft-1-0-comment-resolution-frequency-stitching.pptx
| 12 | Editor's issues | 5 | 7:05 |  | Billy
| 11 | LB213 - Proposed Resolutions for Security - Part 2 | 10 | 7:10 |  | Alex | 15-25-0354 | https://mentor.ieee.org/802.15/dcn/25/15-25-0345-01-04ab-lb213-proposed-resolutions-for-security-part-2.docx
| 12 | LB213/D02 comment resolution -- various CIDs | 10 | 7:20 |  | Alex | 15-25-0404 | https://mentor.ieee.org/802.15/dcn/25/15-25-0404-01-04ab-lb213-d02-comment-resolution-various-cids.docx
| 12 | Recess |  | 7:30 |  | Char
2025-08-26 |  | 26-Aug Comment Resolution |  | 6:00 | 13:00
| 13 | Opening and reminders | 5 | 6:00 |  | Chair
| 14 | CI 254 proposed resolution | 5 | 6:05 |  | Ben | 15-25-0270 | https://mentor.ieee.org/802.15/dcn/25/15-25-0270-03-04ab-ci-254-proposed-resolution.docx
| 15 | Proposed Resolutions for 15.4ab D02 CIDs 584, 585, 586 | 20 | 6:10 |  | Ankur | 15-25-0405 | https://mentor.ieee.org/802.15/dcn/25/15-25-0405-00-04ab-proposed-resolutions-for-15-4ab-d02-cids-584-585-586.docx
| 16 | Resolution to CIDs 1, 2, 3, 8, 11, 13, 236, 237, 250, 251, 271, 292, 308, 309, 313 for 15.4ab Draft 2.0 | 30 | 6:30 |  | Pooria | 15-25-0426 | https://mentor.ieee.org/802.15/dcn/25/15-25-0426-00-04ab-resolution-to-cids-1-2-3-8-11-13-236-237-250-251-271-292-308-309-313-for-15-4ab-draft-2-0.docx
| 17 | Proposed Resolutions for LB213 CID 604,605 | 15 | 7:00 |  | Panpan | 15 25 0410 | https://mentor.ieee.org/802.15/dcn/25/15-25-0410-00-04ab-proposed-resolution-for-cid-604-605.docx
| 18 | Status and CRG Business | 15 | 7:15
| 19 | Recess | 0 | 7:30 |  | Chair
2025-08-28 |  | 28-Aug Special CRG prior to RB for Sept |  | 6:00 | 13:00
| 20 | Opening and reminders | 10 | 6:00 |  | Chair
| 21 | Proposed Resolutions for Remaining misc | 10 | 6:10 |  | Rojan | 15-25-0416 | https://mentor.ieee.org/802.15/dcn/25/15-25-0416-00-04ab-lb213-proposed-resolutions-for-remaining-miscel-cids.docx
| 22 | Proposed Resolutions for Remaining Security | 15 | 6:20 |  | Rojan | 15-25-0415 | https://mentor.ieee.org/802.15/dcn/25/15-25-0415-00-04ab-lb213-proposed-resolutions-for-remaining-security-cids.docx
| 23 | Channel Access Proposal | 20 | 6:35 |  | Alex | 15-25-0427 | https://mentor.ieee.org/802.15/dcn/25/15-25-0427-01-04ab-lb213-d02-comment-resolution-lbt-related-comments-and-crg-motion-for-approval.docx
| 24 | More channel access discussion | 35 | 6:55 |  | Alex et al
| 25 | Status and CRG Business | 0 | 7:30 |  | Chair
| 26 | Recess | 0 | 7:30 |  | Chair
2025-09-02 |  | 02-Sep Comment Resolution |  | 6:00 | 13:00
| 27 | Opening and reminders | 10 | 6:00 |  | Chair
| 28 | DCN 430: Resolution to CID 104 on D2.0 | 20 | 6:10 |  | Pooria | 15-25-0430
| 29 | LB213/D02 comment resolution -- NHL channel map updates -- CIDs 504, 505 | 15 | 6:30 |  | Alex | 15-25-0425 | https://mentor.ieee.org/802.15/dcn/25/15-25-0425-00-04ab-lb213-d02-comment-resolution-nhl-channel-map-updates-cids-504-505.docx
| 30 | LB213/D02 comment resolution -- Mandatory support for UNII-3 -- CID 167 | 15 | 6:45 |  | Alex | 15-25-0424
| 31 | Channel Access Proposal, update and summary | 10 | 7:00 |  | Alex | 15-25-0427 | https://mentor.ieee.org/802.15/dcn/25/15-25-0427-01-04ab-lb213-d02-comment-resolution-lbt-related-comments-and-crg-motion-for-approval.docx
| 32 | CRG Business | 20 | 7:10 |  | TBD
| 33 | Recess | 0 | 7:30 |  | Chair
2025-09-09 |  | 09-Sep Comment Resolution
| 34 | Opening and reminders | 5 | 6:00 | 13:00 | Chair
| 35 | Comment Resolution | 20 | 6:05 |  | Chaplin
| 36 | Comment Resoultion TBD | 20 | 6:25 |  | TBD
| 37 | Comment Resoultion TBD | 20 | 6:45 |  | TBD
| 38 | Comment Resoultion TBD | 5 | 7:05 |  | TBD
| 39 | CRG Business | 20 | 7:10 |  | TBD
| 40 | Recess | 0 | 7:30 |  | Chair
Standby or Pending:
|  | CI 254 proposed resolution | 10 |  |  | Ben | 15-25-0270
|  | Proposed Resolution for CID 604, 605 |  |  |  | Panpan | 15-25-0410 | https://mentor.ieee.org/802.15/dcn/25/15-25-0410-00-04ab-proposed-resolution-for-cid-604-605.docx
|  | Revist on CID 576 |  |  |  | Youngwan
Rojan
Rojan
0

## Time zone helper
First hour | UTC | 13:00
Local Time | Time Zone | UTC Offset
Tuesday, April 8, 2025 at 6:00:00 am | PDT | UTC-7 hours
Tuesday, April 8, 2025 at 9:00:00 am | EDT | UTC-4 hours
Tuesday, April 8, 2025 at 2:00:00 pm | IST | UTC+1 hour
Tuesday, April 8, 2025 at 3:00:00 pm | CEST | UTC+2 hours
Tuesday, April 8, 2025 at 9:00:00 pm | CST | UTC+8 hours
Tuesday, April 8, 2025 at 10:00:00 pm | KST | UTC+9 hours
Tuesday, April 8, 2025 at 10:00:00 pm | JST | UTC+9 hours
Second hour | UTC | 22:00
Local Time | Time Zone | UTC Offset
Thursday, April 3, 2025 at 3:00:00 pm | PDT | UTC-7 hours
Thursday, April 3, 2025 at 6:00:00 pm | EDT | UTC-4 hours
Thursday, April 3, 2025 at 11:00:00 pm | IST | UTC+1 hour
Friday, April 4, 2025 at 12:00:00 midnight | CEST | UTC+2 hours
Friday, April 4, 2025 at 6:00:00 am | CST | UTC+8 hours
Friday, April 4, 2025 at 7:00:00 am | KST | UTC+9 hours
Friday, April 4, 2025 at 7:00:00 am | JST | UTC+9 hours

## Schedule Work
Action | Date
Approve comment resolutions and RC2 | 2025-09-18
Sitart RC2 | 2025-09-19
Close RC2 | 2025-10-04
Approve comment resolutions CRG | 2025-10-07
Close SA ballot | 2025-10-09
Prepare SA ballot comments | 2025-11-08
Start Nov Plenary | 2025-11-10