## Opening
Calendar: | [7 empty] | TGab agenda Sept 2025 through Nov 2025
Sun | Mon | Tue | Wed | Thr | Fri | Sat |  | Virtual (WebEx)
Commence on August 12th until [done with comments ¦ Sept 9th] Weekly Tuesdays 06:00 PT (1.5 hours) Subsequent meetings will be cancelled if/when recirculation ballot begins
|  | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04
2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11
2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18
2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | Ballot Open? | To complete 15 day recirculation by opening of the September session, ballot must open by 30 August
2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01
2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08
2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | Interim Session
2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22
2025-11-23 | 2025-11-24 | 2025-11-25
[7 empty] | Notices: | The meeting will commence August 12th and continue until adjourned
Prior to the opening and each time slot please review the meeting requirements:
https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Standards Board Patent Committee (PatCom) home page:
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Working Group Copyright Materials
https://standards.ieee.org/ipr/copyright-materials.html
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/ieee-sa-copyright-policy-2019.pdf
Participation is conditioned on acceptance of and commitment to comply with all of the above
Formulas:
Wed = [Tue]+1
Thr = [Wed]+1

## Summary
Call Date | Proposed Main Theme(s) | Hour | Lead | Notes | Start (PDT)
2025-10-07 | Comment Resolution | 1.5 |  |  | 6:00
2025-10-09 | Comment Resolution | 1 |  |  | 14:00
2025-10-14 | Comment Resolution / CRG Approval | 1.5 |  |  | 6:00
2025-10-16 | Comment Resolution / CRG Approval | 1 |  |  | 14:00
2025-10-21 | Comment Resolution / CRG Approval | 1.5 |  |  | 6:00
2025-10-28 | Comment Resolution | 1.5 |  |  | 6:00
2025-11-04 | Comment Resolution | 1.5 |  |  | 6:00
Formulas:
Call Date = [Call Date, row above]+7

## Agenda Details
|  | TGab agenda Sept 2025 through Nov 2025 | UTC offset: | -7
Agenda Details
Call Date | Item | Description | Duration | Start PDT | UTC | Presenter/Lead |  | Document link | Notes
2025-10-07 |  | 07-Oct Comment Resolution |  | 6:00 | 13:00
| 1 | Opening and policy reminders | 20 | 6:00 |  | Chair
| 2 | Ballot review and comment first look | 30 | 6:20 |  | Chair/VC
| 3 | Triage and volunteers | 30 | 6:50 |  | TBD
| 4 | Editors Corner | 20 | 7:20 |  | Billly
| 5 | CRG Business | 10 | 7:40 |  | Chair
| 6 | Next steps: Call planning and Schedule | 10 | 7:50 |  | Chair
| 7 | Recess |  | 8:00
2025-10-09 |  | 09-Oct Comment Resolution |  | 14:00 | 21:00
| 8 | Opening and policy reminders | 5 | 14:00 |  | Chair
| 9 | General Comments and Editor's report | 15 | 14:05 |  | Billy
| 10 | More triage and PoC volunteers | 15 | 14:20 |  | Clint C. | 15-25-0509 | https://mentor.ieee.org/802.15/dcn/25/15-25-0509-01-04ab-consolidated-comments-draft-3-0.xlsm
| 11 | Rogue comment discussion | 5 | 14:35 |  | Chair
| 12 | LB225/D03 comment resolution -- CIDs 23 and 30 | 5 | 14:40 |  | Alex | 15-25-0513 | https://mentor.ieee.org/802.15/dcn/25/15-25-0513-00-04ab-lb225-d03-comment-resolution-cids-23-and-30.docx
| 13 | LB225/D03 comment resolution -- Channel access related comments | 15 | 14:45 |  | Alex | 15-25-0510 | https://mentor.ieee.org/802.15/dcn/25/15-25-0510-01-04ab-lb225-d03-comment-resolution-channel-access-related-comments.docx
| 14 | Recess |  | 15:00
2025-10-14 |  | 14-Oct Comment Resolution / CRG Approval |  | 6:00 | 13:00
| 15 | Opening and reminders | 10 | 6:00 |  | Chair
| 16 | Rogue comment procedural decision | 15 | 6:10 |  | Chair
| 17 | Continue comment triage | 10 | 6:25 |  | Clint C.
| 18 | LB225/D03 comment resolution -- Channel access related comments | 20 | 6:35 |  | Alex | 15-25-0510 | https://mentor.ieee.org/802.15/dcn/25/15-25-0510-02-04ab-lb225-d03-comment-resolution-channel-access-related-comments.docx
| 19 | LB225/D03 comment resolution -- CID 175 | 5 | 6:55 |  | Alex | 15-25-0522 | https://mentor.ieee.org/802.15/dcn/25/15-25-0522-01-04ab-lb225-d03-comment-resolution-cid-175.docx
| 20 | LB225/D03 comment resolution -- CID 27 and 6 | 5 | 7:00 |  | Alex | 15-25-0523 | https://mentor.ieee.org/802.15/dcn/25/15-25-0523-00-04ab-lb225-d03-comment-resolution-cid-27-and-6.docx
| 21 | LB225/D03 comment resolution -- CID 8 | 5 | 7:05 |  | Alex | 15-25-0524 | https://mentor.ieee.org/802.15/dcn/25/15-25-0524-00-04ab-lb225-d03-comment-resolution-cid-8.docx
| 22 | LB225/D03 comment resolution -- CID 115 | 5 | 7:10 |  | Alex | 15-25-0525 | https://mentor.ieee.org/802.15/dcn/25/15-25-0525-01-04ab-lb225-d03-comment-resolution-cid-115.docx
| 23 | LB225/D03 comment resolution -- CID 7 | 5 | 7:15 |  | Alex | 15-25-0526 | https://mentor.ieee.org/802.15/dcn/25/15-25-0526-00-04ab-lb225-d03-comment-resolution-cid-7.docx
| 24 | LB225/D03 comment resolution -- CID 9 | 5 | 7:20 |  | Alex | 15-25-0527 | https://mentor.ieee.org/802.15/dcn/25/15-25-0527-00-04ab-lb225-d03-comment-resolution-cid-9.docx
| 25 | Comment Status | 5 | 7:25 |  | Clint C.
| 26 | Recess |  | 7:30 |  | Char
2025-10-16 |  | 16-Oct Comment Resolution / CRG Approval |  | 14:00 | 21:00
| 27 | Opening and reminders | 10 | 14:00 |  | Chair
| 28 | Comment Resolution TBD | 20 | 14:10 |  | TBD
| 29 | Comment Resolution TBD | 20 | 14:30 |  | TBD
| 30 | CRG Business | 10 | 14:50 |  | TBD
| 31 | Recess |  | 15:00 |  | Char
2025-10-21 |  | 21-Oct Comment Resolution / CRG Approval |  | 6:00 | 13:00
| 27 | Opening and reminders | 10 | 6:00 |  | Chair
| 28 | Comment Resolution TBD | 20 | 6:10 |  | TBD
| 29 | Comment Resolution TBD | 20 | 6:30 |  | TBD
| 30 | Comment Resolution TBD | 20 | 6:50 |  | TBD
| 31 | Status and CRG Business | 15 | 7:10 |  | TBD
| 32 | Next steps | 5 | 7:25 |  | Chair
| 33 | Recess | 0 | 7:30 |  | Chair
2025-10-28 |  | 28-Oct Comment Resolution |  | 6:00 | 13:00
| 34 | Opening and reminders | 10 | 6:00 |  | Chair
| 35 | Comment Resolution TBD | 5 | 6:10 |  | TBD
| 36 | Comment Resolution TBD | 20 | 6:15 |  | TBD
| 37 | Comment Resolution TBD | 10 | 6:35 |  | TBD
| 38 | Comment Resolution TBD | 10 | 6:45 |  | TBD
| 39 | Comment Resolution TBD | 10 | 6:55 |  | TBD
| 40 | Comment Resolution TBD | 10 | 7:05 |  | TBD
| 41 | CRG Business | 15 | 7:15 |  | Chair
| 42 | Recess | 0 | 7:30 |  | Chair
2025-11-04 |  | 04-Nov Comment Resolution
| 43 | Opening and reminders | 10 | 6:00 | 13:00 | Chair
| 44 | Comment Resolution TBD | 20 | 6:10 |  | TBD
| 45 | Comment Resolution TBD | 15 | 6:30 |  | TBD
| 46 | Comment Resolution TBD | 20 | 6:45 |  | TBD
| 47 | CRG Business | 15 | 7:05 |  | Chair
| 48 | November Interim Planning | 10 | 7:15 |  | Chair
| 49 | Recess | 0 | 7:30 |  | Chair
Standby or Pending:

## Time zone helper
First hour | UTC | 13:00
Local Time | Time Zone | UTC Offset
Tuesday, April 8, 2025 at 6:00:00 am | PDT | UTC-7 hours
Tuesday, April 8, 2025 at 9:00:00 am | EDT | UTC-4 hours
Tuesday, April 8, 2025 at 2:00:00 pm | IST | UTC+1 hour
Tuesday, April 8, 2025 at 3:00:00 pm | CEST | UTC+2 hours
Tuesday, April 8, 2025 at 9:00:00 pm | CST | UTC+8 hours
Tuesday, April 8, 2025 at 10:00:00 pm | KST | UTC+9 hours
Tuesday, April 8, 2025 at 10:00:00 pm | JST | UTC+9 hours
Second hour | UTC | 22:00
Local Time | Time Zone | UTC Offset
Thursday, April 3, 2025 at 3:00:00 pm | PDT | UTC-7 hours
Thursday, April 3, 2025 at 6:00:00 pm | EDT | UTC-4 hours
Thursday, April 3, 2025 at 11:00:00 pm | IST | UTC+1 hour
Friday, April 4, 2025 at 12:00:00 midnight | CEST | UTC+2 hours
Friday, April 4, 2025 at 6:00:00 am | CST | UTC+8 hours
Friday, April 4, 2025 at 7:00:00 am | KST | UTC+9 hours
Friday, April 4, 2025 at 7:00:00 am | JST | UTC+9 hours

## Schedule Work
Action | Date
Approve comment resolutions and RC2 | 2025-10-23
Sitart RC3 | 2025-10-24
Close RC3 | 2025-11-08
Start Nov Plenary | 2025-11-10