## Title Page
2013-03-21 |  | IEEE P802.19.1-12/0204r9
IEEE P802.19.1
Project | IEEE P802.19.1
Title | IEEE 802.19 Letter Ballot on DF3.02 Comments
Date Submitted | 2013
Source | Mika Kasslin | Voice:
| Nokia | Fax: [ ]
E-mail: mika.kasslin@nokia.com
Re:
Abstract
Purpose | This document contains comments received in WG LB on DF3.02 and resolutions to the comments.
Notice | This document has been prepared to assist the IEEE P802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Revision 0 | All the comments categorized and prepared for resolutions in the San Antonio meeting
Revision 1 | Comment resolution status after Wednesday in San Antonio, November 2012
Revision 2 | Comment resolution proposals added for comments with CID within the range of 148 through 166
Revision 3 | Comment resolution status after Thursday AM meetings in San Antonio, November 2012
Revision 4 | Comment resolution status after November 2012 plenary in San Antonio, TX
Revision 5 | Comment resolution status after AM2 Wednesday in Vancouver, January 2013. Vancouver meeting resolutions highlighted with blue.
Revision 6 | Comment resolution status after Wednesday in Vancouver, January 2013. Vancouver meeting resolutions highlighted with blue.
Revision 7 | Editorial fixes to comment resolutions from the Vancouver meeting
Revision 8 | Comment resolutions status after Wednesday in Orlando, March 2013. Orlando meeting resolutions highlighed with yellow.
Revision 9 | Comment resolutions status after Thursday AM1 in Orlando, March 2013. Orlando meeting resolutions highlighed with yellow.

## comments and resolutions
CID | SA PIN | Name | Vote (Y/N/A) | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | Must Be Satisfied | Response | Status | AssignedTo | E Status | T Status | G Status | Editorial Notes
1) TECHNICAL COMMENTS
1.1) Draft structure and style
1 | 14928 | Stanislav Filin | Y | Primitives are defined using tables and messages are defined using ASN.1. Need to be consistent to improve the understanding of the draft. | Technical |  | 5.2 |  | Define primitives using ASN.1. |  | Accept in principle Create a normative annex "Primitive Definition" for ASN.1 definitions of the primitives using contribution 19-13/0040r0 and 19-13/0049r0. Primitive descriptions in section 5 reference model to be deleted once the normative annex is in place. | C |  |  | C
2 | 14928 | Stanislav Filin | Y | Data type definition for SAP and data type definition for messages are largerly overlapped. But they are in two different sections which creates inconsistency. | Technical |  | 5.3 |  | Merge data type definitions and put into normative annex. |  | Accept | C |  |  | C
3 | 14928 | Stanislav Filin | Y | Data type definition for SAP and data type definition for messages are largerly overlapped. But they are in two different sections which creates inconsistency. | Technical |  | 6.5 |  | Merge data type definitions and put into normative annex. |  | Accept in principle Create normative annex Data Type Definitions for ASN.1 defintions of merged datat types used in primitives and messages Remove data type description from section 5 reference model subsection 5.3 datat type definitions once the new annex is in place. Use contributions 19-13/0039r0 and 19-13/0050r0 for data type definitions. Remove datat type description from section 6, subsection 6.3 once the new annex is in place. Create a normative annex Message Definitions for ASN.1 definition of the messages using contributions 19-13/0041r0 and 19-13/0048r0. Remove message description from section 6, subsection 64 once the new annex is in place. | C |  |  | C
4 | 60941 | Donghun Lee | Y | There are no consistency between section of 6 and 7. Additional description is necessary in section 7 for improving consistency | Technical | 100 | 7 | 30 | Add additional description for improving consistency |  | Accept in principle Modify the draft as described in 19-13/0046r1, 19-13/0024r2 and 19-13/0042r0 | C |  |  | C
5 | 24144 | Hyunduk Kang | Y | CE entity operation should be revised to be in consistency with clause 6 | Technical | 100 | 7 | 30 | Revise clause 7 |  | Accept in principle Modify the draft as described in 19-13/0046r1, 19-13/0024r2 and 19-13/0042r0 | C |  |  | C
6 | 62099 | Jari Junell | N | Section 7 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle Modify the draft as described in 19-13/0046r1, 19-13/0024r2 and 19-13/0042r0 | C |  |  | C
7 | 14928 | Stanislav Filin | Y | CE state diagrams are outdated and too complicated. | Technical |  | 7 |  | Update CE state diagrams. |  | Accept in principle Modify the draft as described in 19-13/0046r1, 19-13/0024r2 and 19-13/0042r0 | C |  |  | C
8 | 60941 | Donghun Lee | Y | There are no consistency between section of 6 and 8. Additional description is necessary in section 8 for improving consistency | Technical | 124 | 8 | 9 | Add additional description for improving consistency |  | Accept in principle A new section 7 will have descriptions on each entity. CM description is, however, missing and needs more work. | C |  |  | C
9 | 24144 | Hyunduk Kang | Y | CM entity operation should be revised to be in consistency with clause 6 | Technical | 124 | 8 | 9 | Revise clause 8 |  | Accept in principle A new section 7 will have descriptions on each entity. CM description is, however, missing and needs more work. | C |  |  | C
10 | 62099 | Jari Junell | N | Section 8 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle A new section 7 will have descriptions on each entity. CM description is, however, missing and needs more work. | C |  |  | C
11 | 14928 | Stanislav Filin | Y | CM state diagrams are outdated and too complicated. | Technical |  | 8 |  | Update CM state diagrams. |  | Accept in principle A new section 7 will have descriptions on each entity. CM description is, however, missing and needs more work. | C |  |  | C
12 | 60941 | Donghun Lee | Y | There are no consistency between section of 6 and 9. Additional description is necessary in section 9 for improving consistency | Technical | 166 | 9 | 3 | Add additional description for improving consistency |  | Accept in principle Modify the draft as described in 19-13/0047r1 and 19-13/0043r0. Add text from contribution 19-13/0044r0 to section 10. | C |  |  | C
13 | 24144 | Hyunduk Kang | Y | CDIS entity operation should be revised to be in consistency with clause 6 | Technical | 166 | 9 | 3 | Revise clause 9 |  | Accept in principle Modify the draft as described in 19-13/0047r1 and 19-13/0043r0. Add text from contribution 19-13/0044r0 to section 10. | C |  |  | C
14 | 62099 | Jari Junell | N | Section 9 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle Modify the draft as described in 19-13/0047r1 and 19-13/0043r0. Add text from contribution 19-13/0044r0 to section 10. | C |  |  | C
15 | 14928 | Stanislav Filin | Y | CDIS state diagrams are outdated and too complicated. | Technical |  | 9 |  | Update CDIS state diagrams. |  | Accept in principle Modify the draft as described in 19-13/0047r1 and 19-13/0043r0. Add text from contribution 19-13/0044r0 to section 10. | C |  |  | C
16 | 14928 | Stanislav Filin | Y | Currently, in section 10 many disconnected topics are mixed. This makes impossible to understand how to implement what is written in Section 10. For example, why measurements are inside Section 10? | Technical |  | 10 |  | Section 10 shall be restructured. Measurements shall be separate. The best place is Informative Annex. |  | Accept Measurement description sub-section in section 10 will be replaced by an informative annex as described in 19-13/0035r0 | C |  |  | C
17 | 14928 | Stanislav Filin | Y | Based on the discussion in the WG, all algorithms are optional and given as examples. But when they are inside normative section 10, this is not so clear. | Technical |  | 10 |  | Move algorithms to Informative Annex. |  | Accepted in principle See a motion on algorithm descriptions on November 15, 2012 | C |  |  | C
18 | 14928 | Stanislav Filin | Y | Section 10 contains many introductory text similar to what mentioned in section 4. | Technical |  | 10 |  | Move introductory text from 10 to 3 with merging. Then, all technical part shall go to annexes and section 10 is not needed. |  | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms. | C | TG editor |  | C
19 | 24144 | Hyunduk Kang | Y | Subclause 9.5.4 is not an algorithm but explanation of two types of coexistence discovery, i.e., intra-CM and inte-CM coexistence discovery, that are already described on sub-clause 4.5.3. | Technical | 228 | 10.5.6 | 1 | Delete sub-clause 10.5.6 |  | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms. | C |  |  | C
20 | 24144 | Hyunduk Kang | Y | Sub-clause 9.5.5 is not an algorithm but explanation of coexistence discovery service that is already described on sub-clause 4.5.3 | Technical | 228 | 10.5.6.1 | 16 | Delete sub-clause 10.5.6.1 |  | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms. | C |  |  | C
21 | 6111 | Mika Kasslin | Y | Language and style in section 10.4 doesn't meet requirements of an industry standard. There is way too much text which belongs to documents like implementation guidelines and implementation specification. | General | 175 | 10.4 | 9 | Rewrite the whole section. | 0 | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms. | C |  |  |  | C
22 | 24144 | Hyunduk Kang | Y | PICS proforma is needed to be discussed if it is appropriate or not for the draft. | Technical | 240 | Annex B | 1 | Discuss it |  | Accept in principle Remove annex B on PICS | C |  |  | C
23 | 6111 | Mika Kasslin | Y | PICS is incomplete. | Technical | 240 | B | 1 | Update the PICS as proposed in 19-12/0201r0. | 0 | Accept in principle Remove annex B on PICS | C |  |  | C
24 | 62099 | Jari Junell | N | PICS incomplete | Technical | 241 | Annex B |  | Specify which features and protocols are mandatory and which are optional | 1 | Accept in principle Remove annex B on PICS | C |  |  | C
25 | 14928 | Stanislav Filin | Y | Primitives, messages, data types, procedures, have many options for different solutions. For the reader it is unclear wich options work with each other. | General |  |  |  | There is a need to show one or several profiles to explain some simple solutions which can be used by the implementers of the standard. It is not nesessary to stick to PICS format for defining profiles. Other option could be state diagrams, which will help to simplify them a lot. |  | Accept in principle Updated entity operations describe profiles. | C |  |  |  | C
26 | 24144 | Hyunduk Kang | Y | The draft needs to have normative texts on profiling | Technical |  |  |  | Add proper normative texts |  | Accept in principle Updated entity operations describe profiles. | C |  |  | C
27 | 6111 | Mika Kasslin | Y | MIB would be really useful addition to the draft as it would make it more clear what information each entity needs to maintain. | Technical | 241 | C | 8 | Add MIB as proposed in 19-12/0202r0. | 0 | Accept in principle Adopt text in contribution 19-13/0029r1 as informative annex. | C |  |  | C
28 | 14928 | Stanislav Filin | Y | It may be beneficial to have CM MIB example. | General |  |  |  | Add informative annex with CM MIB example in ASN.1. |  | Accept in principle Adopt text in contribution 19-13/0029r1 as informative annex. | C |  |  |  | C
29 | 14928 | Stanislav Filin | Y | It may be beneficial to have CDIS MIB example. | General |  |  |  | Add informative annex with CDIS MIB example in ASN.1. |  | Accept in principle Adopt text in contribution 19-13/0029r1 as informative annex. | C |  |  |  | C
1.2) CDIS design
30 | 6111 | Mika Kasslin | Y | In some countries and areas it is illegal for a service provider to release location of a customer and thus the current operating model in which a CM registers WSO location to CDIS for coexistence discovery is illegal in some countries. | General | 5 | 4.3.3 | 26 | Modify the system so that a CM doesn't have to release location of a WSO to CDIS. Redesign the coexistence discovery so that the CDIS doesn't need to know actual location but it can still support the CM in coexistence discovery. | 0 | Withdrawn | C |  |  |  | C
31 | 62099 | Jari Junell | N | Coexistence discovery is broken | Technical | 228 | 10.5.6 |  | See document 19-12/0200r0 | 1 | Accept in principle See contributions 19-13/0044r0, 19-13/0043r0 and 19-13/0047r1. | C |  |  | C
32 | 14928 | Stanislav Filin | Y | There will be multiple CDISs. How to ensure that they provide consistent answers to CMs? | Technical |  | 4.2 |  | CDIS-CDIS interface needs to be defined including corresponding procedures, messages, data types, and state diagrams. |  | Withdrawn | C | Stanislav Filin |  | C
33 | 24144 | Hyunduk Kang | Y | The draft needs to have normative texts on interaction between CDISs | Technical |  |  |  | Add proper normative texts |  | Withdrawn | C |  |  | C
1.3) New features
34 | 14928 | Stanislav Filin | Y | In some radio regulatory regimes, there could be several types of secondary users with different priorities. Current draft does not support such scenario. | General |  |  |  | To increase accaptance of the 802.19.1 in different countries, it is better to update draft to support secondary users with multiple priorities. |  | Accept in principle See contributions from 19-13/0039 through 19-13/0044. | C | Stanislav Filin |  |  | C
35 | 14928 | Stanislav Filin | Y | In some cases several WSOs can be managed by some entity outside of 802.19.1. Example is RLSS. To extand the market for 802.19.1, the coexistence protocol should support such scenario. | Technical |  | 6.4 |  | Updates to several clauses are needed. For example, authentication and subscription should support one procedure for multiple WSOs in case one external entity subscribes to coexistence services on behalf of several WSOs. Then registration could be done by each WSO. |  | Accepted in principle The 802.19.1 system architecture is modified to allow a CE to represent multiple WSOs. Message and data type definitions and primitive descriptions to be updated accordingly as proposed in 19-13/0008r0, 19-13/0007r0 and 19-13/0005r0, respectively. | C |  |  | C
36 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to inform its mobility status to the CE during registration. | Technical | 23 | 5.2.2.3.2 | 14 | Include WSO mobility information parameter in "GetRegInfo.response" primitive | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
37 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to inform its mobility status to the CE during registration. | Technical | 24 | 5.2.2.3.2 | 1 | Define mobility information parameter in Table 15 | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
38 | 65892 | Tsuyoshi Shimomura | N | WSO mobility information should be specified during update registartion. | Technical | 25 | 5.2.2.3.4 | 16 | Include WSO mobility information parameter in "NewRegInfo.indication" primtive | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
39 | 65892 | Tsuyoshi Shimomura | N | WSO mobility information should be specified during update registartion. | Technical | 26 | 5.2.2.3.4 | 1 | Define mobility information parameter in Table 17 | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
40 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to inform its mobility status to the CE for resource reconfiguration. According to some regulations (e.g. FCC), WSO may also provide a region defined by multiple locations. | Technical | 33 | 5.2.2.6.3 | 17 | Include the choice of WSO mobility information parameter and list of geolocations in "ResourceReconfiguration.request" primitive | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
41 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to inform its mobility status to the CE for resource reconfiguration . | Technical | 33 | 5.2.2.6.3 | 26 | Define mobility information parameter in Table 32 | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
42 | 65892 | Tsuyoshi Shimomura | N | CE shall be able to request WSO mobility information | Technical | 42 | 5.3.2 | 14 | Include WSO mobility information in "reqInfoDescrElement" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
43 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to prviode its mobility information upon CE request | Technical | 42 | 5.3.2 | 27 | Include WSO mobility information in "reqInfoValueType" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
44 | 65892 | Tsuyoshi Shimomura | N | WSO mobility measurement should be supported. | Technical | 42 | 5.3.2 | 45 | Include "mobility" in "MeasurementCapability" | 1 | Withdrawn | C |  |  | C
45 | 65892 | Tsuyoshi Shimomura | N | WSO mobility measurement should be supported. | Technical | 43 | 5.3.2 | 19 | Include "mobility" in "MeasurementType" | 1 | Withdrawn | C |  |  | C
46 | 65892 | Tsuyoshi Shimomura | N | WSO mobility report should be defined. | Technical | 44 | 5.3.2 | 16 | Define it | 1 | Withdrawn | C |  |  | C
47 | 65892 | Tsuyoshi Shimomura | N | WSO mobility measurement report should be supported. | Technical | 44 | 5.3.2 | 17 | Include "mobilityReport" in "MeasurementReport" | 1 | Withdrawn | C |  |  | C
48 | 65892 | Tsuyoshi Shimomura | N | WSO mobility information should be specified during the CM registartion. | Technical | 80 | 6.4 | 51 | Include WSO mobility information parameter in "CMRegistrationRequest" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
49 | 65892 | Tsuyoshi Shimomura | N | WSO mobility information should be specified during the CE registartion. | Technical | 79 | 6.4 | 52 | Include WSO mobility information parameter in "CERegistrationRequest" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
50 | 65892 | Tsuyoshi Shimomura | N | CE shall be able to send its WSOmobility status to the CM for resource reconfiguration. According to some regulations (e.g. FCC), WSO may also provide a region defined by multiple locations. | Technical | 90 | 6.4 | 16 | Include WSO mobility information parameter and list of geolocatios in "ResourceReconfigurationRequest" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
51 | 65892 | Tsuyoshi Shimomura | N | CE shall be able to request WSO mobility information | Technical | 95 | 6.5 | 54 | Include WSO mobility information in "reqInfoDescrElement" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
52 | 65892 | Tsuyoshi Shimomura | N | WSO shall be able to prviode its mobility information upon CE request | Technical | 96 | 6.5 | 11 | Include WSO mobility information in "reqInfoValue" | 1 | Accept in principle See 19-13/0001r3. | C |  |  | C
53 | 65892 | Tsuyoshi Shimomura | N | WSO mobility measurement should be supported. | Technical | 96 | 6.5 | 45 | Include "mobility" in "MeasurementType" | 1 | Withdrawn | C |  |  | C
54 | 65892 | Tsuyoshi Shimomura | N | WSO mobility report should be defined. | Technical | 97 | 6.5 | 42 | Define it | 1 | Withdrawn | C |  |  | C
55 | 65892 | Tsuyoshi Shimomura | N | WSO mobility measurement report should be supported. | Technical | 97 | 6.5 | 43 | Include "mobilityReport" in "MeasurementReport" | 1 | Withdrawn | C |  |  | C
1.4) Misc
56 | 23144 | Ivan Reede | N | To change my vote from Disapprove to Approve, include a behavioural model of the coexistence conflict resolution process in the form of algorithms or procdeures or flow charts or state diagrams or other with accompnaying text and provide demonstration via simulation that a standards compliant coexistence system converges toward a stable resolution who's outcome (although it may not be perfect and always converge) demonstrates that coexistence of transceivers/networks implementing such is significantly improved and that such networks do not abdict to other devices not implementing the coexistence standard... i.e. the reason for which one would want to comply rather than not comply. | Technical | iv | 1 | 1 | The difference between the AmeriSys proposal and the current draft makes that I cannot envision a converging solution at this time with the defined protocols and algorithms. Therefore, I expect that when a converging proposal is made, many protocoland algorithm alterations may be required to make a coexistence system that demonstrably improves the coexistnce situation of devices implementing the standard in comparison to devices not implementing the standard. I therefore leave the resolution of this comment and the required changes open to the proponents of the proposed protocols in the task group for lack of technical expertise in the use of what is propsed in the draft. | 1 | Accept in principle More work is needed | C |  |  | C
57 | 6111 | Mika Kasslin | Y | Interfaces A and C are between an IEEE 802.19.1 specified and an external element like WSO and TVBD DB. A specific implementation of those interfaces can not be mandated by the IEEE 802.19.1. | Technical | 6 | 4.4 | 1 | Make it clear in the specification that the interfaces A and C are logical and the IEEE 802.19.1 specification doesn't mandate a specific implementation. Consider deleting all the procedures and message definitions related to the interface C and specify the interface with primitives similarly with the interface A. | 0 | Accept in principle IETF PAWS is used in the interface C. See corresponding straw polls and motions. | C |  |  | C
58 | 24144 | Hyunduk Kang | Y | A term"exposed interface" is newly added. | Technical | 6 | 4.4.2 | 19 | Clarify it |  | Withdrawn | C |  |  | C
59 | 24144 | Hyunduk Kang | Y | More use cases is needed to explain how each procedures is interconnected each other based on various use cases. | Technical | 237 | Annex A | 1 | Add more use cases. |  | Accept See 19-12/0216r0 | C |  |  | C
1.5) SAPs and related data types
60 | 14928 | Stanislav Filin | Y | Transport SAP does not have mechanisms to detect disconnection Also, transport SAP should handle TCP/IP fragmentation and concatenation | Technical |  | 5.2.1 |  | Update Transport SAP. Update to some other parts may be needed |  | Accepted in prinicple Update TR SAP general description as specified in 19-13/0004r2. Update TR SAP primitive definition as specified in 19-13/0005r0. Update CxMessage and CxHeader definitions as specified in 19-13/0007r0. Creat subsections Common Entity Operations, Transport SAP Operation and Processing CxMessage Header as specified in 19-13/0009r1. | C |  |  | C
61 | 60941 | Donghun Lee | Y | The payload of transportPref and its data type in CP_PACKET_RECEIVE.indication needs consistency with other primitives | Technical | 17 | 5.2.1.3 | 11 | Replace transportPref and TransportPref with transportPreference and TransportType, respectively |  | Accepted | C |  |  | C
62 | 60941 | Donghun Lee | Y | Since TV channel mode needs the current occupancy and current Tx power, these data types should be added at datatype of listOfOperatingChNumber in GetRegInfo.response | Technical | 24 | 5.2.2.3.2 | 1 | Revise it as commented |  | Accepted See 19-12/0220r0 | C |  |  | C
63 | 60941 | Donghun Lee | Y | Since TV channel mode needs the current occupancy and current Tx power, these data types should be added at datatype of listOfOperatingChNumber in NewRegInfo.indication | Technical | 26 | 5.2.2.3.4 | 1 | Revise it as commented |  | Accepted See 19-12/0220r0 | C |  |  | C
64 | 60941 | Donghun Lee | Y | The data type of listOfNetworkID is wrong | Technical | 30 | 5.2.2.4.7 | 1 | Replace it with SEQUENCE OF OCTET STRING |  | Accepted See 19-12/0220r0 | C |  |  | C
65 | 60941 | Donghun Lee | Y | The datatype of MeasurementResult is not defined | Technical | 32 | 5.2.2.5.2 | 12 | Add the datatype of MeasurementResult |  | Accepted See 19-12/0220r0 | C |  |  | C
66 | 65892 | Tsuyoshi Shimomura | N | List of operating frequencies should be supported for WSO resource reconfiguration request to CE. | Technical | 33 | 5.2.2.6.3 | 26 | Replace FrequencyRange --> ListOfOperatingFrequencies in newOperatingResource datatype in Table 32 | 1 | Withdrawn | C |  |  | C
67 | 65892 | Tsuyoshi Shimomura | N | List of operating frequencies should be supported in resource reconfiguration response to from CE to WSO . | Technical | 34 | 5.2.6.4 | 11 | Replace FrequencyRange --> ListOfOperatingFrequencies in the newOperatingResource datatype in Table 33. | 1 | Accept in principle See 19-12/0221r0 | C |  |  | C
68 | 65892 | Tsuyoshi Shimomura | N | The minimum scaling step for the supported frequncies should be specified. | Technical | 38 | 5.3.2 | 10 | Revise the definition of "ListOfSupportedFrequencies" as follows, ListOfSupportedFrequencies ::= SEQUENCE OF SEQUENCE { frequencyRange FrequencyRange, scalingStep REAL, --kHz } | 1 | Accept in principle See 19-12/0226r5 Have the figures in the proposal included in a new informative annex that contains explanatory notes. | C |  |  | C
69 | 60941 | Donghun Lee | Y | Since the datatype of ConstOfChUses is defined as sequence, SEQUENCE OF ConstOfChUses is wrong | Technical | 41 | 5.3.2 | 37 | Repliace listOfconstOfChUses and SEQUENCE OF ConstOfChUses with constOfChUses and ConstOfChUses, respectively |  | Accepted See 19-12/0220r0 | C |  |  | C
1.6) Procedure descriptions
70 | 60941 | Donghun Lee | Y | The subsection of 6.2 Inter-entity communication with 6.2.1 Keep alive mechanism is newly added based on the 19-23/84r0. However, the discussion about its normative text is not enough | Technical | 46 | 6.2 | 9 | More discussion is necessary for the normative text in subsection of 6.2 Inter-entity communication with 6.2.1 Keep alive mechanism |  | Accept in principle The specification needs to define when the keep alive mechanism shall be initiated and whether profiles can determine whether to use it. | C |  |  | C
71 | 24144 | Hyunduk Kang | Y | Why 5 consecutive KeepAliveRequest messages is proposed? Why the specific number,"5" is considered? | Technical | 46 | 6.2.1 | 32 | The group is needed to discuss to determine the number if it is required to be specified |  | Accept in principle The mechanism is modified so that the expiry time in the request determines also time during which the responding entity needs to respond to a request in order to keep itself available. The rule on 5 consecutive requests without response is deleted. | C |  |  | C
72 | 6111 | Mika Kasslin | Y | Authentication and deauthentication procedures and related messages as well as data types are useless since the specification mandates use of SSH and TLS. | Technical | 47 | 6.3.1 | 2 | Delete all the procedures dealing with authentication and deauthentication and update rest of the draft accordingly. | 0 | Accept in principle Profile N and O don't use authentication procedure. Profile E will be revised accordingly. | C |  |  | C
73 | 60941 | Donghun Lee | Y | The description of 6.3.2.3 CM subscription procedure is different from the contribution (19-12/175r1). The description should be the same as in the contribution (19-12/175r1) | Technical | 51 | 6.3.2.3 | 18 | Revise it as commented |  | Accepted | C |  |  | C
74 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0175r1). | Technical | 51 | 6.3.2.3 | 18 | Replace it with the original contribution. |  | Accepted | C |  |  | C
75 | 60941 | Donghun Lee | Y | The description of 6.3.2.4 CM subscription update procedure is different from the contribution (19-12/176r1). The description should be the same as in the contribution (19-12/176r1) | Technical | 52 | 6.3.2.4 | 11 | Revise it as commented |  | Accepted | C |  |  | C
76 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0176r1). | Technical | 52 | 6.3.2.4 | 11 | Replace it with the original contribution. |  | Accepted | C |  |  | C
77 | 60941 | Donghun Lee | Y | The description of 6.3.2.5 WSO subscription change procedure is different from the contribution (19-12/177r1). The description should be the same as in the contribution (19-12/177r1) | Technical | 52 | 6.3.2.5 | 27 | Revise it as commented |  | Accepted | C |  |  | C
78 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0177r1). | Technical | 52 | 6.3.2.5 | 27 | Replace it with the original contribution. |  | Accepted | C |  |  | C
79 | 60941 | Donghun Lee | Y | The description of 6.3.4.1 Obtaining coexistence set information is different from the contribution (19-12/178r1). The description should be the same as in the contribution (19-12/178r1) | Technical | 55 | 6.3.4.1 | 20 | Revise it as commented |  | Accepted | C |  |  | C
80 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0178r1). | Technical | 55 | 6.3.4.1 | 20 | Replace it with the original contribution. |  | Accepted | C |  |  | C
81 | 60941 | Donghun Lee | Y | The description of 6.3.4.2 Obtaining coexistence report is different from the contribution (19-12/179r1). The description should be the same as in the contribution (19-12/179r1) | Technical | 56 | 6.3.4.2 | 6 | Revise it as commented |  | Accepted | C |  |  | C
82 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0179r1). | Technical | 56 | 6.3.4.2 | 6 | Replace it with the original contribution. |  | Accepted | C |  |  | C
83 | 62099 | Jari Junell | N | Organise section 6.3.4 to be consistent | Technical | 55 | 6.3.4 |  | Change section 6.3.4.3 as section 6.3.4.2, make a new section 6.3.4.3 Obtaining coexistence set element information (request/response between CMs), shift section 6.3.7.3 as 6.3.4.4 Providing coexistence set element information, shift section 6.3.4.2 as section 6.3.4.5 and shift section 6.3.4.4 as section 6.3.4.6. | 1 | Accept in principle See 19-12/0197r1 | C |  |  | C
84 | 62099 | Jari Junell | N | CM-CM procedure in 6.3.4 missing | Technical | 55 | 6.3.4 |  | See document 19-12/0197r0 | 1 | Accept in principle See 19-12/0197r1 | C |  |  | C
85 | 6111 | Mika Kasslin | Y | The procedure description is incomplete. | Technical | 58 | 6.3.5.1 | 2 | Update the description as proposed in 19-12/0191r0. | 0 | Accepted | C |  |  | C
86 | 24144 | Hyunduk Kang | Y | More explanation is needed for "obtaining available channel list from WSO procedure" | Technical | 58 | 6.3.5.1 | 2 | Revise normative text |  | Accepted See resolution to CID85 | C |  |  | C
87 | 6111 | Mika Kasslin | Y | Procedure description is incomplete. | Technical | 58 | 6.3.5.2 | 7 | Update the description as proposed in 19-12/0192r0. | 0 | Accepted | C |  |  | C
88 | 24144 | Hyunduk Kang | Y | More explanation is needed for "announcing available channel list change by WSO procedure" | Technical | 58 | 6.3.5.2 | 7 | Revise normative text |  | Accepted See resolution to CID87 | C |  |  | C
89 | 60941 | Donghun Lee | Y | Subection of 6.3.5.1 Annnouncing available channel list change by WSO procedure and 6.3.5.2 Obtaining available channel list from TVWS database procedure needs additional description | Technical | 58 | 6.3.5 | 1 | Add the additional description |  | Accepted See resolutions to CID85 and CID87 | C |  |  | C
90 | 60941 | Donghun Lee | Y | The description of 6.3.5.3 Obtaining available channel list from TVWS database procedure is different from the contribution (19-12/167r1). The description should be the same as in the contribution (19-12/167r1) | Technical | 58 | 6.3.5.3 | 12 | Revise it as commented |  | Accepted | C |  |  | C
91 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0167r1). | Technical | 58 | 6.3.5.3 | 12 | Replace it with the original contribution. |  | Accepted | C |  |  | C
92 | 60941 | Donghun Lee | Y | The description of 6.3.5.4 Announcing available channel list change by TVWS database procedure is different from the contribution (19-12/168r1). The description should be the same as in the contribution (19-12/168r1) | Technical | 59 | 6.3.5.4 | 13 | Revise it as commented |  | Accepted | C |  |  | C
93 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0168r1). | Technical | 59 | 6.3.5.4 | 13 | Replace it with the original contribution. |  | Accepted | C |  |  | C
94 | 65892 | Tsuyoshi Shimomura | N | The expression of this sentence is not approriate as it imposes a requirement on the TVWS database. | Technical | 59 | 6.3.5.4 | 14 | Change "performs" to "may perform". | 1 | Accept in principle See motion on interface C on November 14, 2012 | C |  |  | C
95 | 60941 | Donghun Lee | Y | The description of 6.3.6.1 Obtaining channel classification information by CM procedure is different from the contribution (19-12/181r1). The description should be the same as in the contribution (19-12/181r1) | Technical | 60 | 6.3.6.1 | 2 | Revise it as commented |  | Accepted | C |  |  | C
96 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0181r1). | Technical | 60 | 6.3.6.1 | 2 | Replace it with the original contribution. |  | Accepted | C |  |  | C
97 | 60941 | Donghun Lee | Y | The description of 6.3.6.2 Obtaining channel classification information by CE procedure is different from the contribution (19-12/182r1). The description should be the same as in the contribution (19-12/182r1) | Technical | 60 | 6.3.6.2 | 23 | Revise it as commented |  | Accepted | C |  |  | C
98 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0182r1). | Technical | 60 | 6.3.6.2 | 23 | Replace it with the original contribution. |  | Accepted | C |  |  | C
99 | 60941 | Donghun Lee | Y | The description of 6.3.6.4 Announcing channel classification information update to CE procedure is different from the contribution (19-12/184r1). The description should be the same as in the contribution (19-12/184r1) | Technical | 62 | 6.3.6.4 | 4 | Revise it as commented |  | Accepted | C |  |  | C
100 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0184r1). | Technical | 62 | 6.3.6.4 | 4 | Replace it with the original contribution. |  | Accepted | C |  |  | C
101 | 60941 | Donghun Lee | Y | The description of 6.3.7.1 Obtaining information from WSO procedure is different from the contribution (19-12/169r1). The description should be the same as in the contribution (19-12/169r1) | Technical | 62 | 6.3.7.1 | 20 | Revise it as commented |  | Accepted | C |  |  | C
102 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0169r1). | Technical | 62 | 6.3.7.1 | 20 | Replace it with the original contribution. |  | Accepted | C |  |  | C
103 | 60941 | Donghun Lee | Y | The description of 6.3.7.2 Obtaining information from another CM procedure is different from the contribution (19-12/170r1). The description should be the same as in the contribution (19-12/170r1) | Technical | 63 | 6.3.7.2 | 15 | Revise it as commented |  | Accepted | C |  |  | C
104 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0170r1). | Technical | 63 | 6.3.7.2 | 15 | Replace it with the original contribution. |  | Accepted | C |  |  | C
105 | 62099 | Jari Junell | N | Shift section 6.3.7.3 to section 6.3.4 as a subsection. There is missing in that section a CM to CM communication to inform relevant information of coexistence elements, their capabilities etc and also the environment view of reported CE. | Technical | 64 | 6.3.7.3 | 6 | Shift section 6.3.7.3 as a subsection of 6.3.4 | 1 | Accept in principle See 19-12/0197r1 | C |  |  | C
106 | 6111 | Mika Kasslin | Y | Procedure description is incomplete. | Technical | 64 | 6.3.8.1 | 32 | Update the description as proposed in 19-12/0193r0. | 0 | Accept in principle See 19-12/0193r1 | C |  |  | C
107 | 24144 | Hyunduk Kang | Y | More explanation is needed for "requesting measurements procedure" | Technical | 64 | 6.3.8.1 | 32 | Revise normative text |  | See CID106 | C |  |  | C
108 | 6111 | Mika Kasslin | Y | Procedure description is incomplete. | Technical | 65 | 6.3.8.2 | 6 | Update the description as proposed in 19-12/0194r0. | 0 | Accepted | C |  |  | C
109 | 24144 | Hyunduk Kang | Y | More explanation is needed for "obtaining one-time measurement procedure" | Technical | 65 | 6.3.8.2 | 6 | Revise normative text |  | Accepted See resolution to CID108 | C |  |  | C
110 | 6111 | Mika Kasslin | Y | Procedure description is incomplete. | Technical | 65 | 6.3.8.3 | 11 | Update the description as proposed in 19-12/0195r0. | 0 | Accepted See 19-12/0195r1 | C |  |  | C
111 | 24144 | Hyunduk Kang | Y | More explanation is needed for "obtaining scheduled measurements procedure" | Technical | 65 | 6.3.8.3 | 11 | Revise normative text |  | Accepted See resolution to CID110 | C |  |  | C
112 | 60941 | Donghun Lee | Y | Subection of 6.3.8 requesting and obtaining measurements procedure needs additional description | Technical | 64 | 6.3.8 | 31 | Add the additional description |  | Accepted See resolutions to CID108 and CID110 | C |  |  | C
113 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0171r1). | Technical | 66 | 6.3.9.1 | 3 | Replace it with the original contribution. |  | Accepted | C |  |  | C
114 | 60941 | Donghun Lee | Y | The description of 6.3.9.1 Negotiation between CMs without announcement is different from the contribution (19-12/171r1). The description should be the same as in the contribution (19-12/171r1) | Technical | 66 | 6.3.9.1 | 8 | Revise it as commented |  | Accepted | C |  |  | C
115 | 24144 | Hyunduk Kang | Y | More explanation is needed for " msater CM selection by CMs procedure" | Technical | 69 | 6.3.10.2 | 3 | Revise normative text |  | Accepted in priniciple More text is needed to the procedure description. | C |  |  | C
116 | 24144 | Hyunduk Kang | Y | More explanation is needed for " master CM selection by CDIS procedure" | Technical | 68 | 6.3.10.1 | 17 | Revise normative text |  | Accepted in priniciple More text is needed to the procedure description. | C |  |  | C
117 | 24144 | Hyunduk Kang | Y | More explanation is needed for " master/slave CM configuration by CDIS procedure" | Technical | 69 | 6.3.10.3 | 10 | Revise normative text |  | Accepted in priniciple More text is needed to the procedure description. | C |  |  | C
118 | 24144 | Hyunduk Kang | Y | More explanation is needed for " master/slave CM configuration by CMs procedure" | Technical | 70 | 6.3.10.4 | 3 | Revise normative text |  | Accepted in priniciple More text is needed to the procedure description. | C |  |  | C
119 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0172r1). | Technical | 71 | 6.3.11.2 | 15 | Replace it with the original contribution. |  | Accepted | C |  |  | C
120 | 24144 | Hyunduk Kang | Y | More explanation is needed for " sending resource reconfiguration request forom CE to CM procedure" | Technical | 72 | 6.3.11.3 | 1 | Revise normative text |  | Accepted in priniciple More text is needed to the procedure description. | C |  |  | C
121 | 60941 | Donghun Lee | Y | The description of 6.3.12.1 Sending event indication from CE to CM is different from the contribution (19-12/173r1). The description should be the same as in the contribution (19-12/173r1) | Technical | 72 | 6.3.12.1 | 6 | Revise it as commented |  | Accepted | C |  |  | C
122 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0173r1). | Technical | 72 | 6.3.12.1 | 6 | Replace it with the original contribution. |  | Accepted | C |  |  | C
123 | 24144 | Hyunduk Kang | Y | Normative text is not the same as the original contribution (19-12/0174r1). | Technical | 73 | 6.3.12.2 | 1 | Replace it with the original contribution. |  | Accepted | C |  |  | C
124 | 60941 | Donghun Lee | Y | The subsection of 6.3.14 Keep alive procedure is newly added based on the 19-23/84r0. However, the discussion about its normative text is not enough | Technical | 74 | 6.3.14 | 12 | More discussion is necessary for the normative text in subsection of 6.3.14 Keep alive procedure |  | Withdrawn | C |  |  | C
125 | 24144 | Hyunduk Kang | Y | Keep alive procedure is originally proposed as in 19-12/0084r1. New normative text which is not in 19-12/0084r1 is added and it is needed to be clarifed. | Technical | 74 | 6.3.14 | 12 | Clarify the newly added normative text and have a group discussion if it is appropriate |  | Withdrawn | C |  |  | C
126 | 62099 | Jari Junell | N | Procedure description of a method of handling at least 2 concurrent resource allocations by different CMs to the same WSO missing | Technical | 75 | 6.3 | 7 | See document 19-12/0196r0 | 1 | Accept in principle This has to be resolved. | C |  |  | C
1.7) Messages and related data types
127 | 14928 | Stanislav Filin | Y | PAWS interface is evolving. Current message definition in the draft maybe not up to date. | Technical |  | 6.4 |  | Check and update if needed. |  | Agreed in principle IETF PAWS will be referenced in the specification with respect to the interface C. See corresponding motion. | C |  |  | C
128 | 65892 | Tsuyoshi Shimomura | N | "ListOfGeolocation" is listed as a message. It is not a messgae. | General | 76 | 6.4 | 4 | Remove it from the list. |  | Accept Item removed | C |  |  |  | C
129 | 60941 | Donghun Lee | Y | The datatype of ListOfOperatingChNumber should be added at IMPORTS in 6.4 Messages | Technical | 75 | 6.4 | 16 | Revise it as commented |  | Accept | C |  |  | C
130 | 60941 | Donghun Lee | Y | Since the datatype of ConstOfChUses is defined as sequence, SEQUENCE OF ConstOfChUses is wrong in AvailableChannelAnnouncement | Technical | 85 | 6.4 | 18 | Repliace listOfconstOfChUses and SEQUENCE OF ConstOfChUses with constOfChUses and ConstOfChUses, respectively |  | Accept Editorial update: Extend the Const in the data type definition to Constraint | C |  |  | C
131 | 60941 | Donghun Lee | Y | Since the datatype of ConstOfChUses is defined as sequence, SEQUENCE OF ConstOfChUses is wrong in AvailableChannelResponse | Technical | 84 | 6.4 | 44 | Repliace listOfconstOfChUses and SEQUENCE OF ConstOfChUses with constOfChUses and ConstOfChUses, respectively |  | Accept Editorial update: Extend the Const in the data type definition to Constraint | C |  |  | C
132 | 65892 | Tsuyoshi Shimomura | N | List of operating frequencies should be supported for WSO resource reconfiguration request from CE to CM. | Technical | 90 | 6.4 | 26-29 | Replace FrequencyRange --> ListOfOperatingFrequencies in the ResourceReconfigurationRequest message | 1 | Withdrawn | C |  |  | C
133 | 65892 | Tsuyoshi Shimomura | N | List of operating frequencies should be supported in resource reconfiguration response from CM to CE. | Technical | 90 | 6.4 | 45-48 | Replace FrequencyRange --> ListOfOperatingFrequencies in the ResourceReconfigurationResponse message | 1 | Accept in principle The message shall be modified to allow indication of multiple channel numbers or frequency ranges. The channels or the frequency ranges do not need to be adjacent. | C |  |  | C
134 | 65892 | Tsuyoshi Shimomura | N | "ListOfGeolocation" is listed as a data type but it is not defined anywhere. | General | 92 | 6.5 | 6 | Define it. |  | Accept in principle The data type is not present. | C |  |  |  | C
135 | 65892 | Tsuyoshi Shimomura | N | Include "listofGeolocation" in DiscoveryInformation data type | Technical | 93 | 6.5 | 15 | include the following: listOfGelolocation ListOFGeolocation | 1 | Accept in principle The data type is not present. | C |  |  | C
136 | 60941 | Donghun Lee | Y | As discussed in IEEE 802.19-12/0018r5, the payload of expectedlLoad is changed into desiredOccupancy. | Technical | 94 | 6.5 | 25 | Replace the channelLoad with desiredOccupancy |  | Accepted | C |  |  | C
137 | 65892 | Tsuyoshi Shimomura | N | The minimum scaling step for the supported frequncies should be specified. | Technical | 93 | 6.5 | 32 | Revise the definition of "ListOfSupportedFrequencies" as follows, ListOfSupportedFrequencies ::= SEQUENCE OF SEQUENCE { startFreq REAL, stopFreq REAL, scalingStep REAL, --kHZ } | 1 | Accept in principle See 19-12/0226r5 Have the figures in the proposal included in a new informative annex that contains explanatory notes. | C |  |  | C
138 | 62099 | Jari Junell | N | Message definitions are very unclear and hard to read. There are also some amount of errors and missing messages. The order of messages needs som changes. | Technical | 75 | 6.4 |  | Modify the message definitions as proposed in 19-12/0199r0 | 1 | Accept in principle See contributions on message definitions 19-13/0048r0 and 19-13/0041r0. | C |  |  | C
139 | 62099 | Jari Junell | N | Data type definitions are very unclear and hard to read. The order of data types do es not follow the order of messages. Some data types are missing, some do not belong to certain messages. | Technical | 91 | 6.5 |  | Modify the data type definitions as proposed in 19-12/0199r0 | 1 | Accept in principle See contributions on data type definitions 19-13/0050r0 and 19-13/0039r0. | C |  |  | C
1.8) Coexistence mechanisms and algorithms
1.8.1) Coexistence decision algorithm in section 10.4.1
140 | 14928 | Stanislav Filin | Y | The proposed algorithm is not scalable. | Technical | 175 | 10.4.1 |  | Needs to be updated to enable scalability and stable operation with large number of CEs. Also, corresponding updates to protocol may be needed. |  | Accept in principle See contributions 19-13/0039, 19-13/0040 and 19-13/0041. | C |  |  | C
141 | 60941 | Donghun Lee | Y | Some Arrows of flow chart in Fig 179 are opposite direction | Technical | 176 | 10.4.1.1 | 1 | Need correction |  | Accepted | C |  |  | C
142 | 24144 | Hyunduk Kang | Y | The direction of arrows in Figure 179 looks like wrong. It seems that the direction of arrow betwwen steps are reversed. | Technical | 176 | 10.4.1.1 | 1 | Fix the Figure. |  | Accepted See resolution of CID141 | C |  |  | C
143 | 60941 | Donghun Lee | Y | In general, independent channel use is higher priority than scheduling. However, Step 4 and Step 5 are opposite. The priority of assining unoccupied frequency bands for neighbors of the subject network in step 5 is lower than assining a frequency band which are occupied by the network of the same type of the subject network in step 4. In this regard, more explanation is necessary | Technical | 178 | 10.4.1.2 | 7 | Clarify why Step 4 has higher priority than Step 5 |  | Counter Step 3 and 4 consider CE/WSO served by the CM itself. Steps 5 and 6 involve CE/WSO servied by other CMs. | C |  |  | C
144 | 60941 | Donghun Lee | Y | I thought that Step 4,6 and 7 consider the channel sharing by scheduling. However, Step 7 only checks whether subject network can support scheduling. Then, it seems different channel sharing mechanism for Step 4,6 and 7 | Technical | 178 | 10.4.1.2 | 7 | Clarify why Step 4 and 6 do not check whether subject network can support scheduling |  | Counter Steps 4 and 6 consider sharing a frequency band by WSOs of same type. Then time sharing is not considered. Step 7 considers sharing a frequency band by WSO of different types with scheduling. The figure needs to be updated to clarify the differences between the steps. | C | Stanislav Filin to update the figure. |  | C
145 | 60941 | Donghun Lee | Y | I thought that Step 4, 6 and 7 consider the channel sharing by scheduling. These steps, however, do not explain how scheduling is performed. In this regard, more description is necessary | Technical | 178 | 10.4.1.2 | 7 | Clarify how scheduling is performed for step 4, 6 and 7 |  | Accepted in principle On steps 4 and 6, see the response to CID144. Scheduling with step 7 needs to be clarified more in details in the draft. | C | Stanislav Filin to provide text describing how scheduling is done |  | C
146 | 60941 | Donghun Lee | Y | Why does step 5 go to the step 5 again if no frequency band can be cleared for subject network? | Technical | 178 | 10.4.1.2 | 21 | Clarity why step 5 go back to step 5 again |  | Accept in principle Change step 5 to step 6. | C |  |  | C
147 | 60941 | Donghun Lee | Y | Why does step 6 go to the step 5 if no frequency band can be cleared for subject network? | Technical | 178 | 10.4.1.2 | 32 | Clarity why step 6 go back to step 5 |  | Accept in principle Change step 5 to step 7. | C |  |  | C
1.8.2) Coexistence decision algorithm in section 10.4.7
148 | 24144 | Hyunduk Kang | Y | What is the meaning of "TVWS devices accociated to the WSO". Based on the definition of WSO which is described in sub-clause 2.1, the WSO is an entity that represents a television white space device or a network of TVWS devices. | Technical | 208 | 10.4.7.3 | 13 | Clarfiy the meaning of "TVWS devices accociated to the WSO", and if necessary revise the corresponding sentence. |  | Accept in principle The WSO is an entity that represents a TVWS white space device or a network of TVWS devices. The language will be clarified. | C |  |  | C
149 | 24144 | Hyunduk Kang | Y | What is the definition of peak node number and how it is evaluated? | Technical | 208 | 10.4.7.3 | 18 | Add the defintion of peak node number and describe how it is evaluated. |  | Accept Peak node number is the highest node count detected by the WSO and including itself during the time period of Ts (e.g. 30s) Definition will be added. | C |  |  | C
150 | 24144 | Hyunduk Kang | Y | What is the definition of channel utility value and how it is evaluated? | Technical | 208 | 10.4.7.3 | 18 | Add the defintion of channel utility value and describe how it is evaluated. |  | Accept The peak channel utility value is the highest channel occupancy level during the basic frame of that particular radio standard (e.g. beacon period in .11) divided by the allocated occupancy within Ts period. Definition will be added. | C |  |  | C
151 | 60941 | Donghun Lee | Y | As indicated in draft, F1 and F2 are average values over two time periods, T1 (short time period) and T2 (long term historic part). There are no descirptions how T1 and T2 are determined | Technical | 209 | 10.4.7.3 | 3 | Clarify how T1 and T2 are determined |  | Counter Default values for T1 and T2 are 1 min and 1 hour respectively. The description will be updated to clarify the intent. | C |  |  | C
152 | 60941 | Donghun Lee | Y | As indicated in draft, F1 and F2 are average values over two time periods, T1 (short time period and T2 long term historic part). I wonder the benefit of average over two time periods. | Technical | 209 | 10.4.7.3 | 3 | Clarify the benefit of average over two time periods |  | Counter The main purpose of this algorithm is to find channel locations for each WSO in such a way that within each channel the sum of CVs or resources of WSOs is balanced. The actual operation within each channel is done according to RAT specification. The purpose is not to make allocations to each individual link setup. | C |  |  | C
153 | 60941 | Donghun Lee | Y | The weighting factors (a, b,d,e) set 1 in the coexistence value formulation. Is it possible to set other values less than 1? If Yes, how are the values determined? | Technical | 209 | 10.4.7.3 | 3 | Clarify how the values are determined |  | Accept in principle As a clarification remove weighting factors (set them as 1) The description will be update to improve clarity. | C |  |  | C
154 | 60941 | Donghun Lee | Y | The node number and channel utility value are not linearly mapped. More explanation is necessary about it | Technical | 209 | 10.4.7.3 | 3 | Add the description of advantage for non-linear mapping |  | Accept in principle For bigger networks it is easier to use resources continuously (smaller variation in general). Therefore there is reduction in their mapping. The mapping of the channel utility "punishes" WSO less than having direct linear mapping. Its purpose is to decrease CV in some extent if all the allocated resources are not used. Description will be added. | C |  |  | C
155 | 24144 | Hyunduk Kang | Y | What is the definition of mapped node number and how it is evaluated? | Technical | 209 | 10.4.7.3 | 4 | Add the defintion of mapped node number and describe how it is evaluated. |  | Accept in principle F1 is calculated as follows: Calculate the average c1 of 2 latest peak node numbers and the average c2 of 120 previous peak node numbers. Take the average of c1 and c2, round it to the next bigger integer and map that according to following mapping: mapped node number = 0.2 (if number of nodes is 1), N-1 (if number of nodes N is 2,3,…,11) and 10 (if number of nodes N is >11). The clause will be updated to include description. | C |  |  | C
156 | 24144 | Hyunduk Kang | Y | What is the definition of mapped channel utility value and how it is evaluated? | Technical | 209 | 10.4.7.3 | 15 | Add the defintion of mapped channel utility value and describe how it is evaluated. |  | Accept in principle F2 is calculated as follows: calculate the average g1 of 2 latest peak utility values and the average g2 of 120 previous peak utility values. Take the average of g1 and g2 and map that according to the following mapping: mapped channel utility value = 0.4 (between channel utility value of 0-0.3), 1 (between channel utility value of 0.8-1), linearly changing between 0.4 to 1 (between channel utility value of 0.3-0.8). Transmission buffer full is always full channel utility. The clause will be updated to include description. | C |  |  | C
157 | 60941 | Donghun Lee | Y | The description "a sum of the spread factor and squrare of the width factor is less than a pre-defined threshold" is different from the equation | Technical | 211 | 10.4.7.4 | 1 | Clarify the description or the equation |  | Accept The description will be clarified e.g. as follows: is variance of normalized quality factor values and ... | C |  |  | C
158 | 60941 | Donghun Lee | Y | In draft, sigma is defined as variance of normalized quality factor values. If then, what does the sigma square mean? | Technical | 211 | 10.4.7.4 | 3 | Clarify the definition of sigma square |  | Accept in principle See typo correction in CID 172 | C |  |  | C
159 | 24144 | Hyunduk Kang | Y | The equation for variance, sigma, is wrong. It should be square of sigma not the sigma | Technical | 211 | 10.4.7.4 | 4 | Fix the equation |  | Accept in principle See typo correction in CID 172 | C |  |  | C
160 | 24144 | Hyunduk Kang | Y | What is the definition of planned resource allocation and how it is determined? | Technical | 211 | 10.4.7.4 | 6 | Add the defintion of planned resource allocation and describe how it is determined. |  | Accept in principle Planned resource allocation is an allocation, which CM has calculated to the WSO in the resource allocation analysis. The clause description will be updated and definition will be provided. | C |  |  | C
161 | 60941 | Donghun Lee | Y | I have no sense for the meaning of quality factor, normalized value and normalized quality factor | Technical | 211 | 10.4.7.4 | 8 | Add the description for the meaning of quality factor, normalized value and normalized quality factor |  | Accept in principle Quality factor describes how much resources are planned to be allocated to a WSOwith respect to its coexistence value. In the optimal balanced sharing case all WSOs involved have the same value (except if a WSO does not need so much resources it is entitled to). Normalization is done so that condition epsilon for balanced sharing solution is not dependent on number of WSOs. Description will be added to the clause. | C |  |  | C
162 | 24144 | Hyunduk Kang | Y | The equation for normalization value, nv, is broken | Technical | 211 | 10.4.7.4 | 9 | Fix the equation |  | Accept nv = sum(Ri /CVi ) | C |  |  | C
163 | 60941 | Donghun Lee | Y | I didn't clearly understand when the conflict handling happens. Why does two or multiple CMs make decision for a same WSO? | Technical | 212 | 10.4.7.5 | 5 | Clarify when the conflit handling happens |  | Accept in principle Any WSO can belong to many coexistence sets. Different WSOs can be served by different CMs. When CM is doing resource allocation calculations, it is doing this calculation to the target WSO and its coexistence set (or to those to which it is allowed to). When taking these 3 rules, there is a possibility that at least two CMs are calculating resources to the same WSO. The clause will be updated to clarify this. | C |  |  | C
164 | 60941 | Donghun Lee | Y | When a CM receives a ConflictInquiryRequest message from another CM, How does the CM decide whether its response is yes or no? There is no description about it | Technical | 212 | 10.4.7.5 | 11 | Clarify how a CM makes decision of ConflictInquiryResponse |  | Accept in principle The CM responds "yes" if it is calculating resources to the WSO under request. Otherwise it responds "no". The clause will be updated accordingly. | C |  |  | C
165 | 60941 | Donghun Lee | Y | What does mean the first coexistence set or second coecistence set? | Technical | 213 | 10.4.7.5 | 1 | Clarify the meaning of the first and second coexistence sets |  | Accept in principle The CM is calculating allocations to the WSO1 and its coexistence set (=first). When looking the coexistence set of an element of first coexistence set, there most probably are differences. So coexistence set of WSO1 is the first. Coexistence set of an element of the first coexistence set is the second. The clause will be updated to clarify the meaning of two sets. | C |  |  | C
166 | 60941 | Donghun Lee | Y | When receiving a conflict check request from each other conflict handling CM with their proposal, how the CM perform proposal ranking? | Technical | 213 | 10.4.7.5 | 15 | Clarify how the CM perform proposal ranking |  | Accept in principle If there are more than one CM making simultaneously allocation to the same WSO and these CMs perform proposal ranking, that ranking algorithm is left for implementer. The clause will be updated to provide clarification to the issue. | C |  |  | C
1.8.3) Coexistence decision algorithm in section 10.4.8
167 | 60941 | Donghun Lee | Y | The definitions of number of neighbor CM and amount of bandwidth allocated to a m CM is inverted | Technical | 214 | 10.4.8.1 | 4 | The definition should be corrected |  | Accepted | C |  |  | C
1.8.4) Coexistence discovery algorithm in section 10.5.6.2
168 | 14928 | Stanislav Filin | Y | The proposed algorithm is overprotaktive. It generates too many neighbors. | Technical | 228 | 10.5.6.2 |  |  |  | Accept in principle See contribution 19-13/0044r0 | C |  |  | C
169 | 60941 | Donghun Lee | Y | The interference level of 90% is refered as to coexistence set. Why 90%? | Technical | 229 | 10.5.6.2.2 | 17 | Add the description of why the interference level of 90% is considered |  | Accept in principle See contribution 19-13/0044r0 | C |  |  | C
1.8.5) Measurements
170 | 60941 | Donghun Lee | Y | The SINR value is scaled in step of 0.5 dB and covers the range from -10dB(value=0) to +117dB(value=254). Is there any reason to specify the measurement parameters? | Technical | 233 | 10.6.1 |  | Clarify the reason to specify the measurement parameters |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
171 | 60941 | Donghun Lee | Y | The FER value is scaled with 255. Is there any reason to specify the measurement parameter? | Technical | 233 | 10.6.2 |  | Clarify the reason to specify the measurement parameter |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
172 | 60941 | Donghun Lee | Y | The interference plus noise floor measurement value is scaled in step of 0.5 dBm and covers the range from -134dBm(value=0) to -7dBm(value=254). Is there any reason to specify the measurement parameters? | Technical | 233 | 10.6.3 |  | Clarify the reason to specify the measurement parameters |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
173 | 60941 | Donghun Lee | Y | The signal distribution measurement value is scaled with 255. Is there any reason to specify the measurement parameter? | Technical | 233 | 10.6.4 |  | Clarify the reason to specify the measurement parameter |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
174 | 60941 | Donghun Lee | Y | The spectrum measurement value is scaled in step of 0.5 dBm and covers the range from -134dBm(value=0) to -7dBm(value=254). Is there any reason to specify the measurement parameters? | Technical | 234 | 10.6.5 |  | Clarify the reason to specify the measurement parameters |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
175 | 60941 | Donghun Lee | Y | The own network channel occupancy measurement value is scaled with 255. Is there any reason to specify the measurement parameter? | Technical | 235 | 10.6.6.1 | 10 | Clarify the reason to specify the measurement parameter |  | Accept in principle See contribution 19-13/0035r0 that defines a new informative annex for measurement reporting. | C |  |  | C
2) EDITORIAL COMMENTS
176 | 6111 | Mika Kasslin | Y | The definitions section is missing definitions of terms which are used extensively in the section 10. | Editorial | 2 | 3.1 | 8 | Add definitions of terms used in section 10. | 0 |  | A | TG editor | A
177 | 65892 | Tsuyoshi Shimomura | N | There is inconsistency in the entity names shown in the Figure 1. Some entities are shown with their full descriptive names while WSO only as acronym. | Editorial | 4 | 4.2 |  | revise Figure 1: i) Add acronyms for all entities ii) include WSO full name |  |  | A | TG editor | A
178 | 24144 | Hyunduk Kang | Y | Each CM shall support both management service and management service, not CE | Editorial | 5 |  | 9 | Replace "Each CE shall support both~" with "Each CM shall support both~" |  |  | A | TG editor | A
179 | 62099 | Jari Junell | N | Spelling: informaiton | Editorial | 9 |  | 9 | information | 0 |  | A | TG editor | A
180 | 60941 | Donghun Lee | Y | The word of TVBD is wrong | Editorial | 10 | 4.6.2.2 | 26 | Replace it with WSO |  |  | A | TG editor | A
181 | 60941 | Donghun Lee | Y | The blank is needed between the Figure 6 and shows | Editorial | 14 | 5.1 | 1 | Revise it as commented |  |  | A | TG editor | A
182 | 60941 | Donghun Lee | Y | The payload of Status in Deauthentication.confirm primitive is wrong | Editorial | 20 | 5.2.2.1.4 | 17 | Revise it with status |  |  | A | TG editor | A
183 | 60941 | Donghun Lee | Y | Remove a full stop at the end of description sentence in Table 14 | Editorial | 23 | 5.2.2.2.6 | 1 | Revise it as commented |  |  | A | TG editor | A
184 | 65892 | Tsuyoshi Shimomura | N | GetRegInfo.response should be GetInfo.response | Editorial | 31 |  | 13 | Correct it |  |  | A | TG editor | A
185 | 65892 | Tsuyoshi Shimomura | N | GetAvailableChannelList.response should be GetMeasurement.response | Editorial | 32 | 5.2.2.5.2 | 7 | Correct it |  |  | A | TG editor | A
186 | 62099 | Jari Junell | N | Spelling: coexitence | Editorial | 55 | 6.3.4.1 | 23 | coexistence | 0 |  | A | TG editor | A
187 | 62099 | Jari Junell | N | Spelling: genereate | Editorial | 55 | 6.3.4.1 | 32 | generate | 0 |  | A | TG editor | A
188 | 65892 | Tsuyoshi Shimomura | N | The parameter "currentTxPower" is missing here. See Page 38 Line 16 | Editorial | 93 |  | 42 | Add parameter "currentTxPower" in "ListOfOperatingFrequencies" data type. |  |  | A | TG editor | A
189 | 14928 | Stanislav Filin | Y | Eventually, coexistence discovery algorithm is incide 10.5. This is very misleading. First, 10.5 starts from introductory text about CM. But coexistence discovery is run inside CDIS. Second, there are 2 key algorithms in 802.19.1: coexistence discovery and coexistence decision making. They shall have subsections of the second level. | Technical | 173 | 10.5 |  | Restructure section 10 to make clear that there are 2 key algorithms: discovery and decision making. For example, 10.1 Introduction, 10.2 Discovery, 10.3 Decision making, 10.4 Other. |  | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms. | C |  |  | C
190 | 65892 | Tsuyoshi Shimomura | N | Replace "9.2" to "10.2" | Editorial | 173 | 10.1 | 4 | revise it as commented | 0 |  | A | TG editor | A
191 | 50454 | Ryo Sawai | A | The bullet "Recalculation of local specific power for each WSO with the in-block/out-of-block interference effects from the other WSO(s), which could be calculated based on the results PTX(fjj, kk) of step 1 for each WSO, in the following form: ..." is unnecessary in explaning its mechanism, so this must be a typo in edditting this section. | Editorial | 207 | 10.4.6.4.2 | 2 | Remove all sentences and the equation in its bullet of ll.2-5, p.207. | 0 |  | A | TG editor | A
192 | 6111 | Mika Kasslin | Y | Language in the section is not normative text. | Editorial | 207 | 10.4.7 | 9 | Update the section as proposed in 19-12/0198r0. | 0 |  | A | TG editor | A
193 | 62099 | Jari Junell | N | Spelling: ï“ï€¨Ri /CVi ) | Editorial | 211 | 10.4.7.4 | 9 | sum(Ri /CVi ) | 1 |  | A | TG editor | A
194 | 62099 | Jari Junell | N | Spelling: ResourceReconfigurationRequest | Editorial | 226 | 10.5.5.1 | 34 | ReconfigurationRequest | 1 |  | A | TG editor | A
195 | 62099 | Jari Junell | N | p.226 row 35 and p.227 row 20: temporaryResourceReleaseAllowed does not match with section 6.5 tempReleaseAllowed. Change them according to section 6.5 | Editorial | 226.227 | 10.5.5.1 | 35 and 20 | tempReleaseAllowed | 1 |  | A | TG editor | A
196 | 62099 | Jari Junell | N | Spelling: ResourceReconfigurationRequest | Editorial | 227 | 10.5.5.1 | 1 and 3 | ReconfigurationRequest | 1 |  | A | TG editor | A
197 | 62099 | Jari Junell | N | If section 6.3.7.3 is shifted to section 6.3.4.3 then change that section number in section 10.5.5 | Editorial | 227 | 10.5.5.1 | 7 and 32 | 6.3.4.3 | 1 |  | A | TG editor | A

## Status
Editorial comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 21 | 100%
Closed | C | 0 | 0%
Total |  | 21
Technicalcomments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 0 | 0%
Closed | C | 168 | 100%
Total |  | 168
General comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 0 | 0%
Closed | C | 8 | 100%
Total |  | 8
Total # comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 21 | 10.66%
Closed | C | 176 | 89.34%
Total |  | 197
Initial tally
Editorial | E | 85
Technical | T | 183
General | G | 5
Total |  | 273