**IEEE P802.19**

**Wireless Coexistence**

|  |  |
| --- | --- |
| Project | IEEE P802.19 Wireless Coexistence WG |
| Title | **Timeline document of IEEE 802.19.1 Revision** |
| Date Submitted | September 12, 2017 |
| Source | Naotaka Sato (Sony Corporation) | E-mail: naotaka.sato@ieee.org |
| Re: | [] |
| Abstract | [This document contains target timeline for development of IEEE 802.19.1 Revision] |
| Purpose | [] |
| Notice | This document has been prepared to assist the IEEE P802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by IEEE P802.19. |

|  |  |  |  |
| --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |
|  | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 |
| Revision group formed | x |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop draft document | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Adoption of draft text (Draft1.0) |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit Draft 1.0 to Letter Ballot |  | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Comment resolutions in Letter Ballot |  |  | x |  |  |  |  |  |  |  |  |  |  |  |
| Submit Draft 2.0 to 1st Recirculation Ballot |  |  | x |  |  |  |  |  |  |  |  |  |  |  |
| Comment resolutions in 1st Recirculation Ballot |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Submit Draft 3.0 to Sponsor Ballot |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Comment resolutions in Sponsor Ballot |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Submit Draft 4.0 to 1st Recirculation Ballot |  |  |  |  | x |  |  |  |  |  |  |  |  |  |
| Comment resolutions in 1st Recirculation Ballot |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Submit Draft 5.0 to 2nd Recirculation Ballot |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Comment resolutions in 2nd Recirculation Ballot |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Final WG and 802 EC approval |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| IEEE-SA RevCom approval |  |  |  |  |  |  |  | x |  |  |  |  |  |  |